## Rack Delivery Plan
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AA | AB | AC | AD | AE | AF | AG | AH | AI | AJ | AK | AL
| MIM | [25 empty] | Menlo
Demand Source | Prod Site | File Date | POP Date | POP Week | Build ID | Project Code | Destination | Cluster | TLA Part Number | TLA Qty | Min Build Date | Max Build Date | Product Group | Product Type | Deliverable Part Number | Need Qty | MIM Shipped Qty | ReallocatedQTy | MIM Status | Slip Code | Slip Reason | Slip Concat | NPI Stage | NPI Flag | Estimated Completion Date | MIM Comments | Menlo Filled Qty | Menlo Status | Menlo Ord Num (s) | Date Upated | Required Rack Ship Date(ASM wk + 7 days) | Full Mat'l Rec'd Date(From MIM) | Actual Ship Date | Est Arrival Date | Required Arrival Date (Pop wk - 14 days) | Est Days Late | Menlo Comments
SERVER | AT | 2016-05-12 | 2017-01-16 | 2017W03 | 4350_25082 | 4350_25082 | SCL | CF | 86011028 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010807 | 6 | 6 | 0 | MIM-Shipped | NPI | demand dropped in within LT , FA required | NPI//demand dropped in within LT , FA required |  | N | 2016-01-22 09:01 | FA'S kit is at new ( XNRKIT408457 is at NEW ) | 6 | DONE | MORSC3884300483, MORSC3884314652 | 2016-01-26 | 2016-05-14 | 2016-01-26 |  | 2016-03-07 | 2017-01-02 | 0
SERVER | AT | 2016-05-12 | 2017-01-16 | 2017W03 | 4350_25082 | 4350_25082 | SCL | CF | 86011028 | 3 | 2016-12-19 | 2016-12-19 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-12-24 |  | 0 |  |  |  | 2016-12-24 |  |  |  | 2017-01-02 | 0
SERVER | AT | 2016-05-12 | 2017-01-23 | 2017W04 | 3737_25420 | 3737_25420 | CBF | JV | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007203 | 6 | 0 | 6 | MIM-Shipped |  |  |  |  | N |  |  | 6 | DONE | MORSC3889144945 | 2016-03-11 | 2016-05-14 | 2016-03-11 |  | 2016-09-05 | 2017-01-09 | 0
SERVER | AT | 2016-05-12 | 2017-01-23 | 2017W04 | 3737_25420 | 3737_25420 | CBF | JV | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007204 | 6 | 0 | 6 | MIM-Shipped |  |  |  |  | N |  |  | 6 | DONE | MORSC3889144945 | 2016-03-11 | 2016-05-14 | 2016-03-11 |  | 2016-09-05 | 2017-01-09 | 0
SERVER | AT | 2016-05-12 | 2017-01-23 | 2017W04 | 3737_25420 | 3737_25420 | CBF | JV | 86008863 | 6 | 2017-01-09 | 2017-01-09 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2017-01-14 |  | 0 |  |  |  | 2017-01-14 |  |  |  | 2017-01-09 | 0
NBP | AT | 2016-05-12 | 2016-04-04 | 2016W14 | NBP11602 |  | ATL |  | 86010992 | 4 | 2016-04-04 | 2016-04-04 | RACK-ASM | MRACK.IKEA3 | 86010992 | 4 | 0 | 0 |  | OTHER | NBP build | OTHER//NBP build | RHESUS PVT2 | Y | 2016-04-09 | Ali is in charge of NBP Don't build until Ali confirm | 0 |  |  | 2016-04-14 | 2016-04-09 |  |  |  | 2016-03-21 | 0
NBP | AT | 2016-05-12 | 2016-04-20 | 2016W16 | NBP11931 |  | ATL |  | 86008585 | 10 | 2016-04-20 07:00 | 2016-04-20 07:00 | RACK-ASM | MRACK.IKEA3 | 86008585 | 10 | 0 | 0 |  |  |  |  | FB TEST RACKS | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-25 07:00 |  |  |  | 2016-04-06 | 0
NBP | AT | 2016-05-12 | 2016-04-20 | 2016W16 | NBP11932 |  | ATL |  | 86011551 | 2 | 2016-04-20 | 2016-04-20 | RACK-ASM | MRACK.IKEA3 | 86011551 | 2 | 0 | 0 |  |  |  |  | FB TEST RACKS | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-25 |  |  |  | 2016-04-06 | 0
NBP | AT | 2016-05-12 | 2016-04-20 | 2016W16 | NBP11933 |  | ATL |  | 86009645 | 7 | 2016-04-20 | 2016-04-20 | RACK-ASM | MRACK.IKEA3 | 86009645 | 7 | 0 | 0 |  |  |  |  | FB TEST RACKS | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-25 |  |  |  | 2016-04-06 | 0
NBP | AT | 2016-05-12 | 2016-04-20 | 2016W16 | NBP11934 |  | ATL |  | 86004214 | 2 | 2016-04-20 | 2016-04-20 | RACK-ASM | MRACK.IKEA3 | 86004214 | 2 | 0 | 0 |  |  |  |  | FB TES RACKS | Y | 2016-04-23 |  | 0 |  |  |  | 2016-04-25 |  |  |  | 2016-04-06 | 0
NBP | AT | 2016-05-12 | 2016-04-20 | 2016W16 | NBP11935 |  | ATL |  | 86006940 | 2 | 2016-04-20 | 2016-04-20 | RACK-ASM | MRACK.IKEA2 | 86006940 | 2 | 0 | 0 |  |  |  |  | FB TEST RACKS | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-25 |  |  |  | 2016-04-06 | 0
NBP | AT | 2016-05-12 | 2016-05-02 | 2016W18 | NBP11341 | NPI0249 | ATL |  | 86011968 | 9 | 2016-05-02 07:00 | 2016-05-02 07:00 | BATTERY-BOX | ANTARES | 45000039-05 | 45 | 0 | 0 | Pull-from-Stock |  |  |  |  | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 07:00 |  |  |  | 2016-04-18 | 0
NBP | AT | 2016-05-12 | 2016-05-02 | 2016W18 | NBP11341 | NPI0249 | ATL |  | 86011968 | 9 | 2016-05-02 07:00 | 2016-05-02 07:00 | RACK-ASM | NRACK.IKEA3S | 86011967 | 9 | 0 | 0 |  | OTHER | NBP build | OTHER//NBP build |  | Y | 2016-05-07 | Ali is in charge of NBP Don't build until Ali confirm | 0 |  |  | 2016-04-14 | 2016-05-07 07:00 |  |  |  | 2016-04-18 | 0
NBP | AT | 2016-05-12 | 2016-05-02 | 2016W18 | NBP12000 | GCDPVT0002 | ATL |  | 86012388 | 2 | 2016-05-02 | 2016-05-02 | RACK-ASM | NRACK.IKEA3S | 86012388 | 2 | 0 | 0 |  |  |  |  | Ikea 3 Slim Edge DVT Racks | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-04-18 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3685_23436 | C1115 | TUL | OZ | 86003678 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2015-10-02 02:46 |  | 2 | DONE | MORSC444490617, MORSC444503018 | 2015-12-07 | 2016-05-14 | 2015-10-08 |  | 2015-10-12 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3685_23437 | C1115 | TUL | OZ | 86003679 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2015-10-05 18:25 |  | 2 | DONE | MORSC444483132 | 2015-12-07 | 2016-05-14 | 2015-10-08 |  | 2015-10-12 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3685_23881 | C1115 | TUL | OZ | 86003704 | 3 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000016-09 | 18 | 0 | 0 | Built-to-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 18 | DONE | MORSC169270502 | 2016-01-29 | 2016-04-30 | 2015-08-26 |  | 2015-08-28 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3685_23881 | C1115 | TUL | OZ | 86003704 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA1 | 86003680 | 3 | 3 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2015-11-04 12:22 |  | 5 | DONE | MORSC322539110, MORSC283272766, MORSC443780378 | 2015-12-07 | 2016-05-14 | 2015-10-01 |  | 2015-10-05 | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 3731_21742 | 3731_21742 | BRU | WS | 86008863 | 6 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 72 | DONE | MORSC3889087534 | 2016-03-08 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 3731_21742 | 3731_21742 | BRU | WS | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007203 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-09 16:46 |  | 6 | DONE | MORSC3889087410 | 2016-03-08 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 3731_21742 | 3731_21742 | BRU | WS | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007204 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-10 11:09 |  | 6 | DONE | MORSC3889087410 | 2016-03-08 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3733_18264 | C1395 | DLS | PJ | 86005444 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 28 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3733_18264 | C1395 | DLS | PJ | 86005444 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86005420 | 4 | 4 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-13 17:49 | last 2 in WIP | 4 | DONE | MORSC6602234804, MORSC1242989550 | 2016-04-14 | 2016-05-14 | 2016-04-14 |  | 2016-04-21 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3733_18264 | C1395 | DLS | PJ | 86009512 | 8 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 3733_18264 | C1395 | DLS | PJ | 86009512 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009511 | 8 | 8 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-08 17:03 |  | 8 | DONE | MORSC3889376087, MORSC3889389495, MORSC6574024088, MORSC3889399055, MORSC6602234804, MORSC6667971672 | 2016-04-11 | 2016-05-14 | 2016-04-11 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4015_21526 | 4015_21526 | GRQ | EC | 86008863 | 6 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4015_21526 | 4015_21526 | GRQ | EC | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007203 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-10 09:43 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4015_21526 | 4015_21526 | GRQ | EC | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007204 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-10 16:46 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4016_21697 | 4016_21697 | GRQ | ED | 86011084 | 6 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 72 | DONE | MORSC3889903207 | 2016-05-09 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4016_21697 | 4016_21697 | GRQ | ED | 86011084 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-10 21:33 |  | 6 | DONE | MORSC3889903207 | 2016-05-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4016_21697 | 4016_21697 | GRQ | ED | 86011084 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006052 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-11 08:31 |  | 6 | DONE | MORSC3889903207 | 2016-05-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4016_25076 | 4016_25076 | GRQ | ED | 86011083 | 9 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 108 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4016_25076 | 4016_25076 | GRQ | ED | 86011083 | 9 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 9 | 9 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-15 15:13 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4016_25076 | 4016_25076 | GRQ | ED | 86011083 | 9 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006052 | 9 | 9 | 0 | MIM-Shipped |  |  |  |  | N | 2016-02-15 21:31 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4018_20050 | C1188 | GRQ | EF | 86009512 | 8 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 32 | DONE | MORSC3889396415 | 2016-04-08 | 2016-04-30 |  | 2016-04-11 | 2016-04-11 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4018_20050 | C1188 | GRQ | EF | 86009512 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009511 | 8 | 8 | 0 | MIM-Shipped | EXE | Site readiness issue | EXE//Site readiness issue | OTHER | Y | 2016-02-10 10:34 | last 6 racks in WIP | 8 | DONE | MORSC3889396415 | 2016-04-08 | 2016-05-14 |  | 2016-04-11 | 2016-04-11 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4115_25054 | 4115_25054 | DLS | PC | 86010990 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 4 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4115_25054 | 4115_25054 | DLS | PC | 86010990 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3D | 86010910 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa required / Test pending from Google side | NPI//Fa required / Test pending from Google side | OTHER | Y | 2016-04-16 03:29 | Waiting on Neil to confirm to test (Google) | 1 | DONE | MORSC3889428524 | 2016-04-18 | 2016-05-14 | 2016-04-18 |  | 2016-04-22 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4115_25054 | 4115_25054 | DLS | PC | 86010990 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3D | 86010911 | 1 | 1 | 0 | MIM-Shipped | NPI | XPO loss inventory | NPI//XPO loss inventory | OTHER | Y | 2016-04-16 10:43 | in WIP | 1 | DONE | MORSC3889428524 | 2016-04-20 | 2016-05-14 | 2016-04-18 |  | 2016-04-22 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4225_21856 | 4225_21856 | CBF | PS | 86006528 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 14 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 14 | DONE | 733136 | 2015-08-25 | 2016-04-30 | 2015-05-18 |  | 2015-05-20 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4225_21856 | 4225_21856 | CBF | PS | 86006528 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86004103 | 1 | 1 | 0 | MIM-Shipped | OTHER | Rack in Transit | OTHER//Rack in Transit |  | N | 2015-05-29 10:12 |  | 1 | DONE | 741531 | 2015-12-07 | 2016-05-14 | 2015-06-03 |  | 2015-06-05 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4267_22104 | C1135 | CBF | RE | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 7 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2015-11-04 09:34 |  | 4 | DONE | 726305, 727352 | 2015-12-07 | 2016-05-14 | 2015-05-07 |  | 2015-05-12 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4267_22104 | C1135 | CBF | RE | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2015-10-14 16:27 |  | 4 | DONE | 726305, 727352 | 2015-12-07 | 2016-05-14 | 2015-05-07 |  | 2015-05-12 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4466_23599 | C1212 | CBF | RI | 86002546 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000016-09 | 28 | 0 | 0 | Built-to-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 28 | DONE | MORSC444263975 | 2016-03-01 | 2016-04-30 | 2015-10-03 |  | 2015-10-07 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4466_23599 | C1212 | CBF | RI | 86002546 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA1 | 86002489 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2015-09-30 01:36 |  | 4 | DONE | MORSC441617690, MORSC444230703, MORSC444255545, MORSC444287512 | 2015-12-07 | 2016-05-14 | 2015-10-05 |  | 2015-10-07 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4667_24061 | 4667_24061 | CBF | RE | 86011467 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 64 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 64 | DONE | MORSC3882982663 | 2016-01-29 | 2016-04-30 | 2015-11-24 |  | 2015-11-25 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4667_24061 | 4667_24061 | CBF | RE | 86011467 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010633 | 4 | 4 | 0 | MIM-Shipped | MS | Bom Changed within LT , FA Required short 86008273-03 [NPI] | MS//Bom Changed within LT , FA Required short 86008273-03 [NPI] | OTHER | Y | 2016-01-07 17:38 | 1 completed but not shipped | 4 | DONE | MORSC3884209174, MORSC3884217737, MORSC3884227526 | 2016-01-12 | 2016-05-14 | 2016-01-12 |  | 2016-01-14 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4667_24061 | 4667_24061 | CBF | RE | 86011467 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010634 | 4 | 4 | 0 | MIM-Shipped | MS | Bom Changed within LT , FA Requiredshort 86008273-03 [NPI] | MS//Bom Changed within LT , FA Requiredshort 86008273-03 [NPI] | OTHER | Y | 2016-01-08 09:09 | 1 completed but not shipped | 4 | DONE | MORSC3884209174, MORSC3884217737 | 2016-01-11 | 2016-05-14 | 2016-01-11 |  | 2016-01-13 | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4683_24142 | 4683_24142 | LPP | LH | 86009186 | 4 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 16 | DONE | MORSC3889462027 | 2016-04-18 | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4683_24142 | 4683_24142 | LPP | LH | 86009186 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 464 | DONE | MORSC3889462027 | 2016-04-18 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4683_24142 | 4683_24142 | LPP | LH | 86009186 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 8 | 8 | 0 | MIM-Shipped | EXE | XPO to ship on schedule | EXE//XPO to ship on schedule |  | N | 2015-11-20 07:00 |  | 8 | DONE | MORSC3889462027 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4683_24144 | 4683_24144 | LPP | LH | 86008828 | 2 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 8 | DONE | MORSC3889462228 | 2016-04-18 | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4683_24144 | 4683_24144 | LPP | LH | 86008828 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 232 | DONE | MORSC3889462228 | 2016-04-18 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4683_24144 | 4683_24144 | LPP | LH | 86008828 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 4 | 4 | 0 | MIM-Shipped | EXE | XPO to ship on schedule | EXE//XPO to ship on schedule |  | N | 2015-11-18 14:00 |  | 4 | DONE | MORSC3889462228 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4685_24162 | C1266 | MRN | QN | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3884139445 | 2016-03-01 | 2016-04-30 | 2015-12-26 |  | 2015-12-27 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4685_24162 | C1266 | MRN | QN | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped | NPI |  | NPI// | DC_DEPLOY | Y | 2016-01-26 16:28 | The last 4 racks in WIP | 5 | DONE | MORSC3884159480, MORSC3884315592 | 2016-01-27 | 2016-05-14 | 2016-01-27 |  | 2016-01-29 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4685_24164 | C1264 | CHS | VG | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3884491470 | 2016-03-01 | 2016-04-30 | 2016-01-29 |  | 2016-02-02 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4685_24164 | C1264 | CHS | VG | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-05 05:03 |  | 5 | DONE | MORSC3884519997, MORSC3884525517, MORSC3381660883 | 2016-02-09 | 2016-05-14 | 2016-02-09 |  | 2016-02-10 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4685_24165 | C1263 | MRN | QS | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3884702503 | 2016-03-01 | 2016-04-30 | 2016-02-06 |  | 2016-02-08 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4685_24165 | C1263 | MRN | QS | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-17 09:20 |  | 5 | DONE | MORSC3884755034, MORSC3889044235 | 2016-03-01 | 2016-05-14 | 2016-03-01 |  | 2016-03-03 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24254 | C1287 | MRN | QJ | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3884991827 | 2016-03-01 | 2016-04-30 | 2016-02-23 |  | 2016-02-25 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24254 | C1287 | MRN | QJ | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-03-01 18:35 |  | 5 | DONE | MORSC3889043329, MORSC3889054118, MORSC3889055645 | 2016-03-02 | 2016-05-14 |  |  | 2016-03-04 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24256 | C1285 | DUB | DG | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3884914416 | 2016-02-25 | 2016-04-30 |  | 2016-02-26 | 2016-02-29 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24256 | C1285 | DUB | DG | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-15 16:25 |  | 5 | DONE | MORSC3884914416 | 2016-02-25 | 2016-05-14 |  | 2016-02-26 | 2016-02-29 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24259 | C1282 | LPP | LH | 86009690 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 3 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 0 | DONE | MORSC3889246611 | 2016-03-23 | 2016-04-30 |  | 2016-03-24 | 2016-03-29 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24259 | C1282 | LPP | LH | 86009690 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 1 | 0 | 1 | MIM-Shipped |  |  |  | DC_DEPLOY | Y |  |  | 0 | DONE | MORSC3889246611 | 2016-03-23 | 2016-05-14 |  | 2016-03-24 | 2016-03-29 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24261 | C1280 | BRU | WK | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3889259065 | 2016-03-29 | 2016-04-30 |  | 2016-03-30 | 2016-03-30 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24261 | C1280 | BRU | WK | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-26 10:04 | kit is at packing | 5 | DONE | MORSC3889259065 | 2016-03-29 | 2016-05-14 |  | 2016-03-30 | 2016-03-30 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24266 | C1275 | BRU | WN | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC6318995789 | 2016-03-29 | 2016-04-30 |  | 2016-03-30 | 2016-03-30 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24266 | C1275 | BRU | WN | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-26 10:13 |  | 5 | DONE | MORSC6318995789 | 2016-03-29 | 2016-05-14 |  | 2016-03-30 | 2016-03-30 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24267 | C1274 | BRU | WA | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC1195554925 | 2016-03-30 | 2016-04-30 |  | 2016-03-31 | 2016-03-31 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24267 | C1274 | BRU | WA | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 4 | 1 | MIM-Shipped | DEMAND_PLANNING | demand for NCS rack dropped in short 16000899-01 to kit | DEMAND_PLANNING//demand for NCS rack dropped in short 16000899-01 to kit | DC_DEPLOY | Y | 2016-03-16 08:06 | MOR for 16000899-01 is at shipped | 5 | DONE | MORSC1195554925 | 2016-03-30 | 2016-05-14 |  | 2016-03-31 | 2016-03-31 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24295 | C1273 | LPP | LF | 86009690 | 3 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 9 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 9 | DONE | MORSC3889040765 | 2016-03-01 | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24295 | C1273 | LPP | LF | 86009690 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 3 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-26 10:29 | All kits at NEW | 3 | DONE | MORSC3889040765 | 2016-03-01 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24296 | C1272 | LPP | LK | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3889137800 | 2016-04-06 | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_24296 | C1272 | LPP | LK | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-03-09 13:52 |  | 5 | DONE | MORSC3889137800 | 2016-04-06 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_25898 | C1273 | LPP | LG | 86009690 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 6 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 6 | DONE | MORSC3889040765 | 2016-04-06 | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_25898 | C1273 | LPP | LG | 86009690 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-03-09 12:34 |  | 2 | DONE | MORSC3889040765 | 2016-04-06 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_26067 | C1282 | LPP | LI | 86009690 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 12 | DONE | MORSC3889246611 | 2016-03-23 | 2016-04-30 |  | 2016-03-24 | 2016-03-29 | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4697_26067 | C1282 | LPP | LI | 86009690 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-03-21 07:47 |  | 4 | DONE | MORSC3889246611 | 2016-03-23 | 2016-05-14 |  | 2016-03-24 | 2016-03-29 | 2016-04-25 | 0
FABRIC | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4698_24274 | C1304 | SIN | SA | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3889196911 | 2016-04-08 | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4698_24274 | C1304 | SIN | SA | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped | NPI | Short of accessories 72002171-03 due to site balance | NPI//Short of accessories 72002171-03 due to site balance | DC_DEPLOY | Y | 2016-04-06 05:23 | 3 shipped, 72002171-03 just receieved - last 2 in WIP | 5 | DONE | MORSC3889067930 | 2016-04-08 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4698_24281 | C1299 | CHG | TJ | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3889196911 | 2016-04-11 | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4698_24281 | C1299 | CHG | TJ | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped | NPI | testing issue | NPI//testing issue | DC_DEPLOY | Y | 2016-02-25 05:44 | all in WIP | 5 | DONE | MORSC3889067930 | 2016-04-08 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4698_24288 | C1292 | CHG | TG | 86009690 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-04-30 |  | 15 | DONE | MORSC3889334071 | 2016-04-08 | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4698_24288 | C1292 | CHG | TG | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped | NPI | testing issue | NPI//testing issue | DC_DEPLOY | Y | 2016-02-25 05:44 | all 5 racks in WIP | 5 | DONE | MORSC3889067592 | 2016-04-08 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4706_24348 | 4706_24348 | CBF | JK | 86009688 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 16 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-04-30 |  | 16 | DONE | MORSC3883453191 | 2016-03-01 | 2016-04-30 | 2015-12-07 |  | 2015-12-09 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4706_24348 | 4706_24348 | CBF | JK | 86009688 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009243 | 2 | 2 | 0 | MIM-Shipped | NPI | Temporary Hold on racks calling out 160012XX-01; FA required | NPI//Temporary Hold on racks calling out 160012XX-01; FA required | DVT | Y | 2016-02-03 19:04 | FA rack just completed XNRKIT415600- NEw | 2 | DONE | MORSC3884523689, MORSC3884705510 | 2016-02-08 | 2016-05-14 | 2016-02-08 |  | 2016-02-10 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4706_24348 | 4706_24348 | CBF | JK | 86009688 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009323 | 2 | 2 | 0 | MIM-Shipped | NPI | Temporary Hold on racks calling out 160012XX-01; FA required | NPI//Temporary Hold on racks calling out 160012XX-01; FA required | DVT | Y | 2016-02-03 19:07 | FA rack just completed XNRKIT415633- New | 2 | DONE | MORSC3884523689, MORSC3884705510 | 2016-02-08 | 2016-05-14 | 2016-02-08 |  | 2016-02-10 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24954 | 4840_24954 | CBF | JW | 86010958 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24954 | 4840_24954 | CBF | JW | 86010958 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010927 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-03 06:32 |  | 2 | DONE | MORSC3884525537, MORSC3884706586 | 2016-02-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24954 | 4840_24954 | CBF | JW | 86010958 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010929 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-04 04:54 |  | 2 | DONE | MORSC3884525340, MORSC3884706586 | 2016-02-09 | 2016-05-14 |  |  | 2016-02-10 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24968 | 4840_24968 | CBF | JW | 86011147 | 6 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24968 | 4840_24968 | CBF | JW | 86011147 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010991 | 6 | 6 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-03 16:01 |  | 6 | DONE | MORSC3884514121, MORSC3884525550, MORSC3884706137 | 2016-02-08 | 2016-05-14 | 2016-02-08 |  | 2016-02-10 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24968 | 4840_24968 | CBF | JW | 86011147 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010992 | 6 | 6 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-04 22:30 |  | 6 | DONE | MORSC3884514121, MORSC3884525550, MORSC3884706137, MORSC3884714746 | 2016-02-10 | 2016-05-14 | 2016-02-10 |  | 2016-02-12 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24969 | 4840_24969 | CBF | JW | 86010958 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24969 | 4840_24969 | CBF | JW | 86010958 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010927 | 1 | 1 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-01 21:12 |  | 1 | done | MORSC3884726847 | 2016-02-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4840_24969 | 4840_24969 | CBF | JW | 86010958 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010929 | 1 | 1 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-02 04:20 |  | 1 | DONE | MORSC3884726847 | 2016-02-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4862_25070 | C1397 | CBF | JN | 86011012 | 16 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4862_25070 | C1397 | CBF | JN | 86011012 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA3S | 86010988 | 16 | 16 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-04 06:02 |  | 16 | DONE | MORSC6415141984, MORSC6525752360 | 2016-04-05 | 2016-05-14 | 2016-04-05 |  | 2016-04-06 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4873_25110 | C1417 | CBF | JL | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-08 10:20 |  | 4 | DONE | MORSC3884710267,MORSC3371011174 | 2016-02-10 | 2016-05-14 | 2016-02-10 |  | 2016-02-12 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4873_25110 | C1417 | CBF | JL | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-08 10:21 |  | 4 | DONE | MORSC3884710267, MORSC3371011174 | 2016-02-10 | 2016-05-14 | 2016-02-10 |  | 2015-02-12 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4874_25112 | C1418 | CHS | VJ | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-09 10:48 |  | 4 | DONE | MORSC3884710269, MORSC3884714807 | 2016-02-10 | 2016-05-14 | 2016-02-10 |  | 2016-02-11 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4874_25112 | C1418 | CHS | VJ | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-11 20:55 |  | 4 | DONE | MORSC3884711512, MORSC3884714807, MORSC3423751394 | 2016-02-15 | 2016-05-14 | 2016-02-15 |  | 2016-02-16 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4875_25115 | C1419 | MRN | QN | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 3 | 1 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-09 18:08 |  | 4 | DONE | MORSC3884714636, MORSC3884717635, MORSC3423751168 | 2016-03-01 | 2016-05-14 | 2016-02-12 |  | 2016-02-17 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4875_25115 | C1419 | MRN | QN | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 1 | 4 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-04-04 04:53 |  | 4 | DONE | MORSC3884714948, MORSC3884727209, MORSC3884726347 | 2016-03-01 | 2016-05-14 | 2016-02-12 |  | 2016-02-16 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4876_25117 | C1420 | TUL | OO | 86003857 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-05 05:28 |  | 2 | DONE | MORSC3884708305 | 2016-02-08 | 2016-05-14 | 2016-02-08 |  | 2016-02-11 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4876_25117 | C1420 | TUL | OO | 86003857 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-02-05 05:30 |  | 2 | DONE | MORSC3884708305 | 2016-02-08 | 2016-05-14 | 2016-02-08 |  | 2016-02-11 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4883_25356 | GCDPVT0002 | ATL | GD | 86010210 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 8 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4883_25356 | GCDPVT0002 | ATL | GD | 86010210 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA3S | 86009609 | 2 | 2 | 0 | MIM-Shipped |  |  |  | DVT | Y | 2016-02-15 22:05 | another 2 pcs will go away | 2 | DONE | MORSC3884755433, MORSC3884756300 | 2016-04-12 | 2016-05-14 | 2016-02-18 |  | 2016-02-23 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4883_25494 | 4883_25494 | CBF | JK | 86011479 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86011470 | 2 | 2 | 0 | MIM-Shipped | NPI | FA required | NPI//FA required | OTHER | Y | 2016-04-01 21:46 | Fa required from 4883_25493 just completed 1 shipped, last 1 kit is at New | 2 | DONE | MORSC3889368921 | 2016-04-05 | 2016-05-14 | 2016-04-04 |  | 2016-04-07 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4883_25494 | 4883_25494 | CBF | JK | 86011479 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86011471 | 2 | 2 | 0 | MIM-Shipped | NPI | FA required | NPI//FA required | OTHER | Y | 2016-04-02 10:36 | Fa required from 4883_25493 just completed 1 kit is at picking, 1 kit is at NEW | 2 | DONE | MORSC6525752356 | 2016-04-05 | 2016-05-14 | 2016-04-05 |  | 2016-04-07 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4883_25858 | NPI0235 | ATL | QP | 86011707 | 15 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEAS | 86011707 | 15 | 5 | 0 | Pending Kit | NPI | Fa required / BOM Issues pending | NPI//Fa required / BOM Issues pending | OTHER | Y | 2016-05-14 | 1 Fa rack just shipped, 4 in WIP XNRKIT459940- NEW XNRKIT459920- NEW XNRKIT459981- NEW XNRKIT459832- NEW XNRKIT459927- NEW | 0 |  |  | 2016-04-26 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4893_25208 | 4893_25208 | DLS | PF | 86012108 | 8 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 32 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4893_25208 | 4893_25208 | DLS | PF | 86012108 | 8 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 928 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4893_25208 | 4893_25208 | DLS | PF | 86012108 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 16 | 16 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-06 20:07 |  | 16 | DONE | MORSC3889397280, MORSC6587866545 | 2016-04-12 | 2016-05-14 | 2016-04-08 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4893_25209 | 4893_25209 | DLS | PF | 86011072 | 8 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4893_25209 | 4893_25209 | DLS | PF | 86011072 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-06 21:50 |  | 8 | DONE | MORSC3889397341 | 2016-04-08 | 2016-05-14 | 2016-04-08 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4893_25209 | 4893_25209 | DLS | PF | 86011072 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-07 00:53 |  | 8 | DONE | MORSC3889397582 | 2016-04-08 | 2016-05-14 | 2016-04-08 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4894_25210 | 4894_25210 | DLS | PF | 86004188 | 6 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 84 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4894_25210 | 4894_25210 | DLS | PF | 86004188 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004098 | 6 | 6 | 0 | MIM-Shipped | EXE | Kit delivery | EXE//Kit delivery |  | N | 2016-04-08 12:35 | kit is at packing XBRKIT444247 | 6 | DONE | MORSC3889397773, MORSC3889398119, MORSC6666769879 | 2016-04-11 | 2016-05-14 | 2016-04-11 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4894_25210 | 4894_25210 | DLS | PF | 86004188 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004099 | 6 | 6 | 0 | MIM-Shipped | EXE | MIM Shipment | EXE//MIM Shipment |  | N | 2016-04-11 21:27 | last 2 in WIP to ship ASAP | 6 | DONE | MORSC3889397773, MORSC3889398119, MORSC6666770555 | 2016-04-12 | 2016-05-14 | 2016-04-12 |  | 2016-04-19 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4894_25212 | 4894_25212 | DLS | PF | 86007621 | 10 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 140 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4894_25212 | 4894_25212 | DLS | PF | 86007621 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006116 | 10 | 10 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 05:43 |  | 10 | DONE | MORSC3889415573 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4894_25212 | 4894_25212 | DLS | PF | 86007621 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006117 | 10 | 10 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 04:44 |  | 10 | DONE | MORSC3889415537 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4903_25252 | 4903_25252 | CHS | VO | 86012099 | 14 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 168 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4903_25252 | 4903_25252 | CHS | VO | 86012099 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 14 | 14 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-15 08:55 |  | 14 | DONE | MORSC3889421819, MORSC6769434925 | 2016-04-15 | 2016-05-14 | 2016-04-15 |  | 2016-04-19 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4903_25252 | 4903_25252 | CHS | VO | 86012099 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 14 | 15 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-27 14:10 |  | 14 | DONE | MORSC3889421432, MORSC6769434925, MORSC3889537068 | 2016-04-27 | 2016-05-14 | 2016-04-27 |  | 2016-04-28 | 2016-04-25 | 3
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4917_25293 | 4917_25293 | TUL | OH | 86012174 | 10 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 160 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4917_25293 | 4917_25293 | TUL | OH | 86012174 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009246 | 10 | 10 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-18 16:36 |  | 10 | DONE | MORSC3889463265, MORSC6842557032, MORSC3889479484 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4917_25293 | 4917_25293 | TUL | OH | 86012174 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009254 | 10 | 10 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 10:19 |  | 10 | DONE | MORSC6842557032, MORSC3889479484 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4917_25294 | 4917_25294 | TUL | OH | 86012174 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 80 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4917_25294 | 4917_25294 | TUL | OH | 86012174 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009246 | 5 | 5 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-18 17:39 |  | 5 | DONE | MORSC3889465213, MORSC3889479606 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4917_25294 | 4917_25294 | TUL | OH | 86012174 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009254 | 5 | 5 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 10:17 |  | 5 | DONE | MORSC3889465213, MORSC3889479606 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4927_25350 | 4927_25350 | CBF | IY | 86011070 | 6 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 72 | DONE | MORSC6497741918 | 2016-04-06 | 2016-04-30 | 2016-04-04 |  | 2016-04-06 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4927_25350 | 4927_25350 | CBF | IY | 86011070 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-07 19:13 | Kits are at New | 6 | DONE | MORSC3889396423, MORSC3889399071 | 2016-04-08 | 2016-05-14 | 2016-04-08 |  | 2016-04-13 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4927_25350 | 4927_25350 | CBF | IY | 86011070 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-07 22:33 | last 2 in WIP | 6 | DONE | MORSC3889399071, MORSC3889467120 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4931_25845 | 4931_25845 | CHG | TK | 86012088 | 16 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 192 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4931_25845 | 4931_25845 | CHG | TK | 86012088 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 16 | 16 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-16 07:06 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | SG | 2016-05-12 | 2016-05-09 | 2016W19 | 4931_25845 | 4931_25845 | CHG | TK | 86012088 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 16 | 16 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-23 03:06 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4938_25630 | 4938_25630 | TUL | OT | 86005342 | 3 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4938_25630 | 4938_25630 | TUL | OT | 86005342 | 3 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4938_25630 | 4938_25630 | TUL | OT | 86005342 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 17:10 |  | 6 | DONE | MORSC3889409527, MORSC6742044694 | 2016-04-14 | 2016-05-14 |  |  | 2016-04-18 | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4939_25629 | 4939_25629 | LPP | LO | 86008000 | 1 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 4 | DONE | MORSC3889463004 | 2016-04-18 | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4939_25629 | 4939_25629 | LPP | LO | 86008000 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 116 | DONE | MORSC3889463004 | 2016-04-18 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4939_25629 | 4939_25629 | LPP | LO | 86008000 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-29 08:50 |  | 2 | DONE | MORSC3889463004 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4940_25628 | 4940_25628 | LPP | LM | 86008000 | 1 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 4 | DONE | MORSC3889485400 | 2016-04-21 | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4940_25628 | 4940_25628 | LPP | LM | 86008000 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 116 | DONE | MORSC3889485400 | 2016-04-21 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4940_25628 | 4940_25628 | LPP | LM | 86008000 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 17:06 |  | 2 | DONE | MORSC3889485400 | 2016-04-21 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4941_25619 | 4941_25619 | CHS | VO | 86012767 | 1 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4941_25619 | 4941_25619 | CHS | VO | 86012767 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4941_25619 | 4941_25619 | CHS | VO | 86012767 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-15 00:58 |  | 2 | DONE | MORSC3889464444 | 2016-04-18 | 2016-05-14 | 2016-04-18 |  | 2016-04-19 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4941_25620 | 4941_25620 | CHS | VO | 86012109 | 3 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4941_25620 | 4941_25620 | CHS | VO | 86012109 | 3 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4941_25620 | 4941_25620 | CHS | VO | 86012109 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-14 11:30 |  | 6 | DONE | MORSC3889422056, MORSC3889422654 | 2016-04-14 | 2016-05-14 |  |  | 2016-04-19 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4942_25398 | 4942_25398 | CBF | JA | 86010549 | 14 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 168 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4942_25398 | 4942_25398 | CBF | JA | 86010549 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 14 | 14 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-16 13:32 |  | 14 | DONE | MORSC3889419911, MORSC3889421871, MORSC3889424490, MORSC3889463870 | 2016-04-18 | 2016-05-14 | 2016-04-18 |  | 2016-04-20 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4942_25398 | 4942_25398 | CBF | JA | 86010549 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 14 | 14 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-15 18:42 |  | 14 | DONE | MORSC3889419911, MORSC3889421871, MORSC3889421478, MORSC3889424490, MORSC3889463870 | 2016-04-18 | 2016-05-14 | 2016-04-18 |  | 2016-04-20 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4942_25399 | 4942_25399 | CBF | JA | 86010612 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4942_25399 | 4942_25399 | CBF | JA | 86010612 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-09 04:44 |  | 2 | DONE | MORSC3889404000 | 2016-04-11 | 2016-05-14 | 2016-04-11 |  | 2016-04-14 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4942_25399 | 4942_25399 | CBF | JA | 86010612 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-09 04:47 |  | 2 | DONE | MORSC3889404000, MORSC1238947721 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-15 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4965_25534 | C1445 | TUL | OH | 86005444 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 28 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4965_25534 | C1445 | TUL | OH | 86005444 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86005420 | 4 | 4 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-04 04:54 |  | 4 | DONE | MORSC6387008225, MORSC6497741855, MORSC3889373699 | 2016-04-05 | 2016-05-14 | 2016-04-05 |  | 2016-04-07 | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4965_25534 | C1445 | TUL | OH | 86009487 | 16 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 64 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4965_25534 | C1445 | TUL | OH | 86009487 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009488 | 16 | 15 | 1 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-04 04:52 |  | 16 | DONE | MORSC3889239266, MORSC6497741855, MORSC6506753848, MORSC3889370725 | 2016-04-05 | 2016-05-14 | 2016-04-05 |  | 2016-04-07 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4971_25578 | 4971_25578 | TUL | OO | 86005342 | 14 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 56 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4971_25578 | 4971_25578 | TUL | OO | 86005342 | 14 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 1624 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4971_25578 | 4971_25578 | TUL | OO | 86005342 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 28 | 28 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 12:55 | last 4 in WIP | 28 | DONE | MORSC3889409696, MORSC3889410034, MORSC3889409950, MORSC6696357894, MORSC3889415238 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-20 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_25579 | 4972_25579 | CBF | JG | 86011080 | 1 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_25579 | 4972_25579 | CBF | JG | 86011080 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_25579 | 4972_25579 | CBF | JG | 86011080 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 10:24 | last 2 in WIP | 2 | DONE | MORSC3889415249 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-20 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_25581 | 4972_25581 | CBF | JG | 86012771 | 3 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 0 |  |  |  | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_25581 | 4972_25581 | CBF | JG | 86012771 | 3 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_25581 | 4972_25581 | CBF | JG | 86012771 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 12:54 | in WIP | 6 | DONE | MORSC3889415553 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-18 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_26388 | 4972_26388 | CBF | JG | 86012073 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_26388 | 4972_26388 | CBF | JG | 86012073 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 08:26 | in WIP | 1 | DONE | MORSC6722923888 | 2016-04-13 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_26388 | 4972_26388 | CBF | JG | 86012073 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 05:45 | in WIP | 1 | DONE | MORSC6722923888 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-18 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_26389 | 4972_26389 | CBF | JG | 86012173 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_26389 | 4972_26389 | CBF | JG | 86012173 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-12 15:04 |  | 2 | DONE | MORSC6696355298 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4972_26389 | 4972_26389 | CBF | JG | 86012173 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-12 13:57 |  | 2 | DONE | MORSC6696355298 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-15 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4977_25601 | 4977_25601 | DLS | PC | 86012029 | 12 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 108 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4977_25601 | 4977_25601 | DLS | PC | 86012029 | 12 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86012031 | 12 | 12 | 0 | MIM-Shipped | NPI | FA rack short NPI consigned parts to kit / Kit delivery | NPI//FA rack short NPI consigned parts to kit / Kit delivery |  | N | 2016-04-19 19:42 | all remanining kits just receieved, 11 in WIP, 1 shipped | 12 | DONE | MORSC3889406342, MORSC3889482812 | 2016-04-20 | 2016-05-14 | 2016-04-20 |  | 2016-04-29 | 2016-04-25 | 4
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4988_25772 | 4988_25772 | CBF | JN | 86012209 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 20 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4988_25772 | 4988_25772 | CBF | JN | 86012209 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012210 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa required | NPI//Fa required | OTHER | Y | 2016-04-20 16:21 | in WIP | 1 | DONE | MORSC3889485952 | 2016-04-21 | 2016-05-14 | 2016-04-21 |  | 2016-04-25 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4988_25772 | 4988_25772 | CBF | JN | 86012209 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012211 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa required | NPI//Fa required | OTHER | Y | 2016-04-15 04:29 | in WIP | 1 | DONE | MORSC3889424037 | 2016-04-20 | 2016-05-14 | 2016-04-15 |  | 2016-04-19 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4989_25672 | 4989_25672 | MRN | QJ | 86011069 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4989_25672 | 4989_25672 | MRN | QJ | 86011069 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-18 17:40 |  | 4 | DONE | MORSC3889428646, MORSC1246945636 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 4989_25672 | 4989_25672 | MRN | QJ | 86011069 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 03:37 |  | 4 | DONE | MORSC3889428646 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4991_25754 | 4991_25754 | LPP | LI | 86009744 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 12 | DONE | MORSC3889430182 | 2016-04-18 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4991_25754 | 4991_25754 | LPP | LI | 86009744 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-23 14:04 |  | 1 | DONE | MORSC3889430182 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4991_25754 | 4991_25754 | LPP | LI | 86009744 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-24 11:05 |  | 1 | DONE | MORSC3889430182 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4991_25755 | 4991_25755 | LPP | LI | 86009745 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4991_25755 | 4991_25755 | LPP | LI | 86009745 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-23 13:57 |  | 1 | DONE | MORSC3889430193 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 4991_25755 | 4991_25755 | LPP | LI | 86009745 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-24 12:34 |  | 1 | DONE | MORSC3889430193 | 2016-04-18 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 5027_26120 | 5027_26120 | LPP | LO | 86012109 | 35 | 2016-04-18 | 2016-04-18 | BATTERY-BOX | PACK | 07017435 | 140 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-23 |  | 140 | DONE | MORSC3889466441 | 2016-04-19 | 2016-04-23 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 5027_26120 | 5027_26120 | LPP | LO | 86012109 | 35 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07000733 | 4060 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 4060 | DONE | MORSC3889466910 MORSC3889466441 | 2016-04-19 | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | 5027_26120 | 5027_26120 | LPP | LO | 86012109 | 35 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 70 | 70 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 12:58 | in WIP | 70 | DONE | MORSC3889466973 MORSC3889466910 MORSC3889485501 MORSC6892502372 | 2016-04-21 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 5049_25965 | 5049_25965 | CBF | JW | 86011147 | 4 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 64 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 5049_25965 | 5049_25965 | CBF | JW | 86011147 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010991 | 4 | 4 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-21 15:05 | in WIP | 4 | DONE | MORSC3889490384 | 2016-04-22 | 2016-05-14 |  |  | 2016-04-26 | 2016-04-25 | 1
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 5049_25965 | 5049_25965 | CBF | JW | 86011147 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010992 | 4 | 5 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-05-03 16:33 | in WIP | 4 | DONE | MORSC3889482732, MORSC3889490384, MORSC3889500084 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-04-28 | 2016-04-25 | 3
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 5049_25966 | 5049_25966 | CBF | JW | 86012223 | 14 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 168 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 5049_25966 | 5049_25966 | CBF | JW | 86012223 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010927 | 14 | 14 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-20 03:45 | in WIP | 14 | DONE | MORSC1248146928 | 2016-04-20 | 2016-05-14 | 2016-04-20 |  | 2016-04-22 | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | 5049_25966 | 5049_25966 | CBF | JW | 86012223 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010929 | 14 | 15 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-28 19:37 | in WIP | 14 | DONE | MORSC3889480658, MORSC3889468165, MORSC6919600455, MORSC3889500244, MORSC3889556104 | 2016-04-29 | 2016-05-14 | 2016-04-29 |  | 2016-05-02 | 2016-04-25 | 7
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86003208_01_A_16W19 | BURSTBUFFER | ATL | QP | 86003208 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86004098_01_A_16W18 | BURSTBUFFER | ATL | QP | 86004098 | 7 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004098 | 7 | 2 | 0 | Pending Kit |  |  |  |  | Y | 2016-05-14 | XNRKIT460189- NEW XNRKIT460007- NEW XNRKIT460340- NEW XNRKIT460346- NEW | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86004099_01_A_16W18 | BURSTBUFFER | ATL | QP | 86004099 | 7 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004099 | 7 | 3 | 0 | Pending Kit |  |  |  |  | Y | 2016-05-14 | XNRKIT460220- NEW XNRKIT460063- NEW XNRKIT460076-NEW XNRKIT460100- NEW | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86006051_01_A_16W19 | BURSTBUFFER | ATL | QP | 86006051 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 2 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008383_01_A_16W19 | BURSTBUFFER | ATL | QP | 86008383 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008383_01_E_16W19 | BURSTBUFFER | AMS | QP | 86008383 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | Y | 2016-05-11 08:15 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008385_01_A_16W19 | BURSTBUFFER | ATL | QP | 86008385 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008385_01_E_16W19 | BURSTBUFFER | AMS | QP | 86008385 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | Y | 2016-05-11 14:24 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008943_01_A_16W19 | BURSTBUFFER | ATL | QP | 86008943 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008943_01_E_16W19 | BURSTBUFFER | AMS | QP | 86008943 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | Y | 2016-05-12 10:27 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008944_01_A_16W19 | BURSTBUFFER | ATL | QP | 86008944 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86008944_01_E_16W19 | BURSTBUFFER | AMS | QP | 86008944 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | Y | 2016-05-12 20:27 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86009511_02_A_16W19 | GCDBUFFER | ATL | QP | 86009511 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009511 | 10 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
FABRIC | NL | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86009511_02_E_16W19 | GCDBUFFER | AMS | EP | 86009511 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009511 | 5 | 2 | 0 | At-risk | MS | short RMU | MS//short RMU |  | Y | 2016-05-14 | RMU is on the way to complete build | 0 |  |  | 2016-05-11 | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | AT | 2016-05-12 | 2016-05-09 | 2016W19 | BTS_86011588_01_A_16W19 | BURSTBUFFER | ATL | QP | 86011588 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86011588 | 10 | 0 | 0 | [5 empty] | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-04-25 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4018_21725 | 4018_21725 | GRQ | EF | 86008863 | 6 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4018_21725 | 4018_21725 | GRQ | EF | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007203 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 15:34 |  | 0 |  |  | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4018_21725 | 4018_21725 | GRQ | EF | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007204 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 19:45 | 2 in WIP, 4 peding kit delivery | 0 |  |  | 2016-04-28 | 2016-05-14 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4020_20052 | C1226 | GRQ | EH | 86009512 | 4 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 16 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4020_20052 | C1226 | GRQ | EH | 86009512 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009511 | 4 | 4 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-05-03 08:46 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4021_20054 | C1227 | GRQ | EH | 86009512 | 4 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 16 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4021_20054 | C1227 | GRQ | EH | 86009512 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009511 | 4 | 4 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-05-03 17:52 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4567_23752 | 4567_23752 | LPP | LF | 86006781 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4567_23752 | 4567_23752 | LPP | LF | 86006781 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86006659 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-11 18:55 |  | 1 | DONE | MORSC3889569004 | 2016-05-02 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4567_23752 | 4567_23752 | LPP | LF | 86006781 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86006660 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-12 09:36 |  | 1 | DONE | MORSC3889569004 | 2016-05-02 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4568_23753 | 4568_23753 | MRN | QB | 86009489 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4568_23753 | 4568_23753 | MRN | QB | 86009489 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009168 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 18:40 |  | 1 | DONE | MORSC3889524233 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4568_23753 | 4568_23753 | MRN | QB | 86009489 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009169 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 14:07 |  | 1 | DONE | MORSC3889524233 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4571_23756 | 4571_23756 | CBF | JB | 86009489 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4571_23756 | 4571_23756 | CBF | JB | 86009489 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009168 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 15:02 |  | 1 | DONE | MORSC3889500243 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4571_23756 | 4571_23756 | CBF | JB | 86009489 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009169 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 19:26 |  | 1 | DONE | MORSC3889500243 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4582_23767 | 4582_23767 | DLS | PF | 86012608 | 3 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4582_23767 | 4582_23767 | DLS | PF | 86012608 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009168 | 3 | 3 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-06 23:24 |  | 3 | done | MORSC3889397669 | 2016-04-08 | 2016-05-14 | 2016-04-08 |  | 2016-04-15 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4582_23767 | 4582_23767 | DLS | PF | 86012608 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009169 | 3 | 3 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-06 19:42 |  | 3 | done | MORSC3889397669 | 2016-04-08 | 2016-05-14 | 2016-04-08 |  | 2016-04-15 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4589_23783 | 4589_23783 | MRN | QK | 86009489 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4589_23783 | 4589_23783 | MRN | QK | 86009489 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009168 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 14:35 |  | 1 | DONE | MORSC3889504373 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4589_23783 | 4589_23783 | MRN | QK | 86009489 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009169 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 03:21 |  | 1 | DONE | MORSC3889550242 | 2016-04-28 | 2016-05-14 | 2016-04-28 |  | 2016-04-29 | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4594_23789 | 4594_23789 | LPP | LE | 86006781 | 4 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 96 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 96 | DONE | MORSC3889915283 | 2016-05-11 | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4594_23789 | 4594_23789 | LPP | LE | 86006781 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86006659 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-12 16:54 |  | 4 | DONE | MORSC3889568541 | 2016-05-02 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4594_23789 | 4594_23789 | LPP | LE | 86006781 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86006660 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 08:10 |  | 4 | DONE | MORSC3889568541 | 2016-05-02 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4675_24096 | 4675_24096 | SIN | SB | 86006781 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86006659 | 1 | 1 | 0 | MIM-Shipped | DEMAND_PLANNING | Pull in within LT | DEMAND_PLANNING//Pull in within LT |  | N | 2016-03-16 18:31 | kit is at packing | 0 |  |  | 2016-03-14 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4675_24096 | 4675_24096 | SIN | SB | 86006781 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2 | 86006660 | 1 | 1 | 0 | MIM-Shipped | DEMAND_PLANNING | Pull in within LT | DEMAND_PLANNING//Pull in within LT |  | N | 2016-03-17 17:29 | kit is at NEw | 0 |  |  | 2016-03-14 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | SG | 2016-05-12 | 2016-05-16 | 2016W20 | 4675_24096 | 4675_24096 | SIN | SB | 86006781 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4685_24163 | C1265 | LPP | LQ | 86009690 | 5 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-07 |  | 5 | DONE | MORSC3884512801 | 2016-04-08 | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4685_24163 | C1265 | LPP | LQ | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped | EXE | Testing issue | EXE//Testing issue | DC_DEPLOY | Y | 2016-01-29 08:31 | in WIP | 5 | DONE | MEL001 | 2016-02-09 | 2016-05-14 |  |  |  | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4698_24292 | C1289 | CBF | IR | 86009690 | 5 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4698_24292 | C1289 | CBF | IR | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 5 | MIM-Shipped |  |  |  | DC_DEPLOY | Y |  |  | 5 | DONE | MORSC3889415449 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-20 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07001792 | 16 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07004272 | 16 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07004276 | 16 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07004328 | 256 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07007365 | 16 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07014320 | 256 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07018006 | 32 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07048407 | 16 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 901223 | 256 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 901225 | 256 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 901289 | 256 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4722_24438 | 4722_24438 | ATL | BA | 86011987 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEAS-B | 86006500 | 16 | 4 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4723_24442 | 4723_24442 | ATL | AC | 86011773 | 26 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEAS-S | 86004295 | 26 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07001792 | 10 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07004272 | 10 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07004276 | 10 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07004328 | 160 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07007365 | 10 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07014320 | 160 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07018006 | 20 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 07048407 | 10 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 901223 | 160 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 901225 | 160 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-02 | 2016-05-02 | RACK-ASM | HWKIT | 901289 | 160 | 0 | 0 | [5 empty] | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4724_24445 | 4724_24445 | AMS | BA | 86011987 | 10 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEAS-B | 86006500 | 10 | 10 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-09 20:28 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 4725_24449 | 4725_24449 | AMS | AC | 86011773 | 12 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEAS-S | 86004295 | 12 | 12 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-12 18:51 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_24666 | 4767_24666 | DLS | PL | 86012228 | 45 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 810 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_24666 | 4767_24666 | DLS | PL | 86012228 | 45 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011505 | 45 | 45 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-06 04:51 | 45 completed, 44 shipped | 45 | DONE | MORSC3889630307, MORSC3889631809, MORSC3889640126, MORSC3889641287, MORSC3889886011, MORSC3889887008, MORSC3889898891, MORSC3889900425 | 2016-05-10 | 2016-05-14 | 2016-05-06 |  | 2016-05-13 | 2016-05-02 | 11
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_24666 | 4767_24666 | DLS | PL | 86012228 | 45 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011506 | 45 | 45 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-06 04:52 | 45 completed, 44 shipped | 45 | DONE | MORSC3889630240, MORSC3889630458, MORSC3889631809, MORSC3889640126, MORSC7265717284, MORSC3889631809, MORSC3889889763, MORSC3889898891 | 2016-05-10 | 2016-05-14 | 2016-05-06 |  | 2016-05-13 | 2016-05-02 | 11
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_24667 | 4767_24667 | DLS | PL | 86012308 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 18 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_24667 | 4767_24667 | DLS | PL | 86012308 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011505 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-02 20:23 | Fa just completed, Kits is still at packing | 1 | DONE | MORSC1266156938 | 2016-05-10 | 2016-05-14 | 2016-05-03 |  | 2016-05-09 | 2016-05-02 | 7
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_24667 | 4767_24667 | DLS | PL | 86012308 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011506 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-02 15:59 | Fa just completed, rack is in WIP | 1 | DONE | MORSC1266156938 | 2016-05-10 | 2016-05-14 | 2016-05-03 |  | 2016-05-09 | 2016-05-02 | 7
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_25622 | 4767_25622 | DLS | PL | 86012307 | 6 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 108 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_25622 | 4767_25622 | DLS | PL | 86012307 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011505 | 6 | 6 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-03 19:18 | Fa rack was completed, last rack will be shipped | 6 | DONE | MORSC3889498080, MORSC3889629441, MORSC3889640560 | 2016-05-10 | 2016-05-14 | 2016-05-04 |  | 2016-05-09 | 2016-05-02 | 7
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4767_25622 | 4767_25622 | DLS | PL | 86012307 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011506 | 6 | 6 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-03 08:34 | Fa rack was completed, remaning kits are at packing | 6 | DONE | MORSC3889487468, MORSC3889629441, MORSC3889631152, MORSC3889640560 | 2016-05-10 | 2016-05-14 | 2016-05-04 |  | 2016-05-09 | 2016-05-02 | 7
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4932_25379 | C1426 | CHS | VY | 86005444 | 4 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 28 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4932_25379 | C1426 | CHS | VY | 86005444 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86005420 | 4 | 2 | 2 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-15 03:24 |  | 4 | DONE | MORSC3884756097, MORSC3889404517, MORSC6774470824 | 2016-04-18 | 2016-05-14 | 2016-04-18 |  | 2016-04-19 | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4932_25379 | C1426 | CHS | VY | 86009487 | 24 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 96 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 4932_25379 | C1426 | CHS | VY | 86009487 | 24 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009488 | 24 | 24 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-26 10:14 |  | 24 | DONE | MORSC3889370371, MORSC6740528647, MORSC3889467634, MORSC3889504416 | 2016-05-03 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5001_25864 | 5001_25864 | TUL | NA | 86012109 | 14 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07017435 | 56 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5001_25864 | 5001_25864 | TUL | NA | 86012109 | 14 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | PACK | 07000733 | 1624 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5001_25864 | 5001_25864 | TUL | NA | 86012109 | 14 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 28 | 29 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-04 18:39 |  | 16 |  | MORSC6892196216, MORSC3889483509 | 2016-04-20 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5004_25766 | 5004_25766 | TUL | OQ | 86012111 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5004_25766 | 5004_25766 | TUL | OQ | 86012111 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5004_25766 | 5004_25766 | TUL | OQ | 86012111 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 10:48 |  | 2 | DONE | MORSC6919600087 | 2016-04-22 | 2016-05-14 | 2016-04-22 |  | 2016-04-26 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5019_25841 | 5019_25841 | TUL | OY | 86008405 | 2 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5019_25841 | 5019_25841 | TUL | OY | 86008405 | 2 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5019_25841 | 5019_25841 | TUL | OY | 86008405 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 07:37 |  | 4 | DONE | MORSC6919600461 | 2016-04-22 | 2016-05-14 | 2016-04-22 |  | 2016-04-26 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5019_25842 | 5019_25842 | TUL | OY | 86012370 | 3 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5019_25842 | 5019_25842 | TUL | OY | 86012370 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004100 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 01:10 |  | 3 | DONE | MORSC3889550342 | 2016-04-28 | 2016-05-14 | 2016-04-28 |  | 2016-05-02 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5019_25842 | 5019_25842 | TUL | OY | 86012370 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 13:39 |  | 3 | DONE | MORSC3889504217, MORSC3889550342 | 2016-04-28 | 2016-05-14 | 2016-04-28 |  | 2016-05-02 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5026_25885 | 5026_25885 | DLS | PC | 86012220 | 2 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 36 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5026_25885 | 5026_25885 | DLS | PC | 86012220 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86003383 | 2 | 2 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-07 13:47 | last one in WIP | 2 | DONE | MORSC3889554006 | 2016-05-10 | 2016-05-14 |  |  | 2016-05-06 | 2016-05-02 | 4
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5026_25885 | 5026_25885 | DLS | PC | 86012220 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86003384 | 2 | 2 | 0 | MIM-Shipped | NPI | Fa rack Required | NPI//Fa rack Required |  | N | 2016-05-05 21:54 | Fa rack just completed, XBRKIT457355- NEW | 2 | DONE | MORSC3889554006, MORSC3889909598 | 2016-05-10 | 2016-05-14 | 2016-05-09 |  | 2016-05-13 | 2016-05-02 | 11
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5062_26045 | 5062_26045 | TUL | ON | 86010549 | 12 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5062_26045 | 5062_26045 | TUL | ON | 86010549 | 12 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 12 | 12 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-22 16:33 |  | 12 | DONE | MORSC3889490607, MORSC3889499700, MORSC3889503542 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5062_26045 | 5062_26045 | TUL | ON | 86010549 | 12 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 12 | 12 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 10:34 |  | 12 | DONE | MORSC3889490607, MORSC3889503542, MORSC3889504221 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5080_26121 | 5080_26121 | BRU | WM | 86012068 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 12 | DONE | MORSC3889503407 | 2016-04-26 | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5080_26121 | 5080_26121 | BRU | WM | 86012068 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 06:54 |  | 1 | DONE | MORSC3889503407 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5080_26121 | 5080_26121 | BRU | WM | 86012068 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 06:43 |  | 1 | DONE | MORSC3889503407 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5080_26209 | 5080_26209 | BRU | WM | 86012109 | 5 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 20 | DONE | MORSC3889501859 | 2016-04-26 | 2016-04-30 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5080_26209 | 5080_26209 | BRU | WM | 86012109 | 5 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 580 | DONE | MORSC3889501859 | 2016-04-26 | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5080_26209 | 5080_26209 | BRU | WM | 86012109 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 10 | 10 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-22 11:40 |  | 10 | DONE | MORSC3889501859 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5081_26124 | 5081_26124 | BRU | WQ | 86012071 | 2 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 24 | DONE | MORSC3889503436 | 2016-04-26 | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5081_26124 | 5081_26124 | BRU | WQ | 86012071 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 09:10 |  | 2 | DONE | MORSC3889503436 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5081_26124 | 5081_26124 | BRU | WQ | 86012071 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 11:06 |  | 2 | DONE | MORSC3889503436 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5081_26125 | 5081_26125 | BRU | WQ | 86012173 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 18 | DONE | MORSC3889549854 | 2016-04-28 | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5081_26125 | 5081_26125 | BRU | WQ | 86012173 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 17:44 |  | 1 | DONE | MORSC3889549854 | 2016-04-28 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5081_26125 | 5081_26125 | BRU | WQ | 86012173 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 20:11 |  | 1 | DONE | MORSC3889549854 | 2016-04-28 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26127 | 5082_26127 | CHS | VL | 86012068 | 2 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26127 | 5082_26127 | CHS | VL | 86012068 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 10:21 |  | 2 | DONE | MORSC3889504398, MORSC3889522077 | 2016-04-27 | 2016-05-14 | 2016-04-27 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26127 | 5082_26127 | CHS | VL | 86012068 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-23 11:43 |  | 2 | DONE | MORSC3889504398 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26210 | 5082_26210 | CHS | VL | 86012081 | 1 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26210 | 5082_26210 | CHS | VL | 86012081 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 16:29 |  | 1 | DONE | MORSC3889530145 | 2016-04-28 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26210 | 5082_26210 | CHS | VL | 86012081 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 21:11 |  | 1 | DONE | MORSC1246945307 | 2016-04-20 | 2016-05-14 | 2016-04-20 |  | 2016-04-21 | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26213 | 5082_26213 | CHS | VL | 86012111 | 3 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26213 | 5082_26213 | CHS | VL | 86012111 | 3 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | 5082_26213 | 5082_26213 | CHS | VL | 86012111 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 01:08 | last 2 kit is at packing XBRKIT453565 | 6 | DONE | MORSC3889530164, MORSC3889550476 | 2016-04-28 | 2016-05-14 | 2016-04-28 |  | 2016-04-29 | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5171_26445 | 5171_26445 | LPP | LK | 86012887 | 4 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5171_26445 | 5171_26445 | LPP | LK | 86012887 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010229 | 4 | 4 | 0 | MIM-Shipped |  |  |  | PVT | Y | 2016-04-29 11:23 |  | 4 | DONE | MORSC3889569142 | 2016-05-02 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | 5171_26445 | 5171_26445 | LPP | LK | 86012887 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86010230 | 4 | 4 | 0 | MIM-Shipped |  |  |  | PVT | Y | 2016-04-29 13:08 |  | 4 | DONE | MORSC3889569142 | 2016-05-02 | 2016-05-14 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86003208_01_A_16W20 | BURSTBUFFER | ATL | QP | 86003208 | 5 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 5 | 0 | 0 | [5 empty] | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86008383_01_A_16W20 | BURSTBUFFER | ATL | QP | 86008383 | 0 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86008383 | 0 | 0 | 0 | MIM-Shipped |  |  |  |  | N |  |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86008385_01_A_16W20 | BURSTBUFFER | ATL | QP | 86008385 | 0 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86008385 | 0 | 0 | 0 | MIM-Shipped |  |  |  |  | N |  |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86009511_02_A_16W20 | GCDBUFFER | ATL | QP | 86009511 | 10 | 2016-05-16 | 2016-05-16 | RACK-ASM | NRACK.IKEAS | 86009511 | 10 | 0 | 0 | [5 empty] | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
FABRIC | NL | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86009511_02_E_16W20 | GCDBUFFER | AMS | EP | 86009511 | 5 | 2016-05-16 | 2016-05-16 | RACK-ASM | NRACK.IKEAS | 86009511 | 5 | 0 | 0 | [5 empty] | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86011587_01_A_16W20 | BURSTBUFFER | ATL | QP | 86011587 | 5 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86011587 | 5 | 0 | 0 | [5 empty] | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
SERVER | AT | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86011588_01_A_16W20 | BURSTBUFFER | ATL | QP | 86011588 | 10 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86011588 | 10 | 0 | 0 | [5 empty] | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-02 | 0
SERVER | NL | 2016-05-12 | 2016-05-16 | 2016W20 | BTS_86011588_01_E_16W18 | BURSTBUFFER | AMS | QP | 86011588 | 4 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86011588 | 4 | 3 | 0 | At-risk | MS | short cable 16000821-01 to kit / build Dropped in within LT | MS//short cable 16000821-01 to kit / build Dropped in within LT |  | Y | 2016-05-14 | Will kit ASAP once Cables are recieved | 0 |  |  | 2016-05-09 | 2016-05-21 |  |  |  | 2016-05-02 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 3846_18931 | C1162 | TUL | ND | 86009418 | 8 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 56 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 3846_18931 | C1162 | TUL | ND | 86009418 | 8 | 2016-05-16 | 2016-05-16 | RACK-ASM | NRACK.IKEAS | 86009419 | 8 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 3846_18931 | C1162 | TUL | ND | 86010778 | 12 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 3846_18931 | C1162 | TUL | ND | 86010778 | 12 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA3S | 86010993 | 12 | 11 | 0 | At-risk | MS | short NPI -consigned 86008205-02 | MS//short NPI -consigned 86008205-02 |  | N | 2016-05-14 | 10 shipped, 1 in WIP , last one short Switches to kit | 11 |  | MORSC3889464345, MORSC3889479781, MORSC3889480649, MORSC3889482369, MORSC3889492755, MORSC3889640654, MORSC3889909851, MORSC3889957861 | 2016-05-13 | 2016-05-14 |  |  | 2016-05-16 | 2016-05-09 | 7
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24262 | C1279 | CHS | VJ | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24262 | C1279 | CHS | VJ | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-10 20:59 | last 1 in WIP | 5 | DONE | MORSC7265717072, MORSC3889636454, MORSC3889886998, MORSC3889929457 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-12 | 2016-05-09 | 3
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24264 | C1277 | ATL | YK | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24264 | C1277 | ATL | YK | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-07 13:53 | last 3 in WIP | 5 | DONE |  | 2016-05-09 | 2016-05-14 | 2016-05-09 |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24265 | C1276 | MRN | QF | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24265 | C1276 | MRN | QF | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 3 | 0 | On-track |  |  |  | DC_DEPLOY | Y | 2016-05-14 | all in WIP | 3 |  | MORSC3889918944, MORSC3889929494 | 2016-05-11 | 2016-05-14 |  |  | 2016-05-12 | 2016-05-09 | 3
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24297 | C1271 | ATL | YV | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24297 | C1271 | ATL | YV | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-12 13:05 | last 3 in WIP | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24299 | C1269 | CHS | VN | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24299 | C1269 | CHS | VN | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-12 01:43 | all in WIP | 4 |  | MORSC3889929413 | 2016-05-11 | 2016-05-14 |  |  | 2016-05-12 | 2016-05-09 | 3
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24300 | C1268 | CHS | UA | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4697_24300 | C1268 | CHS | UA | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-02 07:35 |  | 5 | DONE | MORSC3889522074, MORSC3889631045 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-04 | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4698_24269 | C1309 | TUL | OI | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4698_24269 | C1309 | TUL | OI | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-02 07:38 |  | 5 | DONE | MORSC3889624822, MORSC7264521007 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-05 | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4698_24272 | C1306 | CBF | IL | 86009690 | 5 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4698_24272 | C1306 | CBF | IL | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-02 03:29 |  | 5 | DONE | MORSC3889624842 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4707_24349 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 25 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4707_24349 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012105 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa rack | NPI//Fa rack | DVT | Y | 2016-05-12 14:04 | FA rack still in WIP | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4707_24349 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012106 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa rack | NPI//Fa rack | DVT | Y | 2016-05-12 14:15 | FA rack still in WIP | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4707_24349 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012107 | 1 | 1 | 0 | MIM-Shipped | NPI | Fa rack | NPI//Fa rack | DVT | Y | 2016-05-11 20:28 | FA rack still in WIP | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4767_25515 | 4767_25515 | DLS | PL | 86012227 | 41 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 738 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4767_25515 | 4767_25515 | DLS | PL | 86012227 | 41 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011498 | 41 | 37 | 0 | At-risk | NPI | Fa rack / Bom issues on 72000790-02 | NPI//Fa rack / Bom issues on 72000790-02 |  | N | 2016-05-14 | XBRKIT460299- Void XBRKIT460786- void shipped 37 | 37 |  | MORSC3889886855, MORSC3889899007, MORSC3889898398, MORSC3889900476, MORSC3889905467, , MORSC7439817340, MORSC3889912388, MORSC3889929770 | 2016-05-11 | 2016-05-14 |  |  | 2016-05-16 | 2016-05-09 | 7
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4767_25515 | 4767_25515 | DLS | PL | 86012227 | 41 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011499 | 41 | 41 | 0 | MIM-Shipped | NPI | Fa rack / Material shoratges 72000790-02 | NPI//Fa rack / Material shoratges 72000790-02 |  | N | 2016-05-11 15:52 | last 1 in WIP | 40 |  | MORSC1294156120,MORSC3889909984, MORSC3889911891, MORSC7439817340, MORSC3889912388, MORSC3889929770, MORSC3889941533 | 2016-05-12 | 2016-05-14 |  |  | 2016-05-17 | 2016-05-09 | 8
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4767_25621 | 4767_25621 | DLS | PL | 86012227 | 7 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 126 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4767_25621 | 4767_25621 | DLS | PL | 86012227 | 7 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA2D | 86011498 | 7 | 1 | 0 | At-risk | NPI | Fa rack / BOM issues on PDU / short switches | NPI//Fa rack / BOM issues on PDU / short switches |  | N | 2016-05-14 | 1 shipped, 6 awaiting kit delivery XBRKIT460313- Void XBRKIT461032- void XBRKIT461036- Void | 1 |  | MORSC7074390085 | 2016-05-09 | 2016-05-21 |  |  | 2016-05-06 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4767_25621 | 4767_25621 | DLS | PL | 86012227 | 7 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA2D | 86011499 | 7 | 7 | 0 | MIM-Shipped | MS | Fa rack / bom issues on 72000790-02 | MS//Fa rack / bom issues on 72000790-02 |  | N | 2016-05-10 03:55 | remanining 6 in WIP | 7 | DONE | MORSC3889629940, MORSC3889912547, MORSC3889931248 | 2016-05-11 | 2016-05-21 | 2016-05-11 |  | 2016-05-13 | 2016-05-09 | 4
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4841_24958 | 4841_24958 | SCL | CE | 86009284 | 1 | 2016-04-25 | 2016-04-25 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-04-30 |  | 0 |  |  |  | 2016-04-30 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4841_24958 | 4841_24958 | SCL | CE | 86009284 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 1 | MIM-Shipped |  |  |  |  | N |  |  | 1 | DONE | MORSC3889031009 | 2016-04-19 | 2016-05-14 | 2016-02-29 |  | 2016-05-09 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4841_24958 | 4841_24958 | SCL | CE | 86009284 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 1 | MIM-Shipped |  |  |  |  | N |  |  | 1 | DONE | MORSC3889031009 | 2016-04-19 | 2016-05-14 | 2016-02-29 |  | 2016-05-09 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4904_26033 | 4904_26033 | TUL | OX | 86012224 | 26 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 312 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4904_26033 | 4904_26033 | TUL | OX | 86012224 | 26 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 26 | 26 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-16 13:30 |  | 26 | DONE | MORSC3889421876, MORSC3889424651, MORSC6765573265, MORSC3889463510 | 2016-04-18 | 2016-05-14 |  |  | 2016-04-20 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4904_26033 | 4904_26033 | TUL | OX | 86012224 | 26 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 26 | 26 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 10:16 |  | 26 | DONE | MORSC3889421981, MORSC6765573265, MORSC6842228502, MORSC3889479609 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-04-21 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4944_25404 | 4944_25404 | ATL | YI | 86009745 | 3 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4944_25404 | 4944_25404 | ATL | YI | 86009745 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 3 | 0 | 3 | MIM-Shipped |  |  |  |  | N |  |  | 3 | DONE | MORSC3884759846 | 2016-02-18 | 2016-05-14 | 2016-02-18 |  | 2016-02-18 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4944_25404 | 4944_25404 | ATL | YI | 86009745 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 3 | 0 | 3 | MIM-Shipped |  |  |  |  | N |  |  | 3 | DONE | MORSC3884759846 | 2016-02-18 | 2016-05-14 | 2016-02-18 |  | 2016-02-18 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4944_25405 | 4944_25405 | ATL | YI | 86012217 | 4 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 56 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4944_25405 | 4944_25405 | ATL | YI | 86012217 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86011472 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-19 13:40 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07001792 | 3 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07004272 | 3 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07004276 | 3 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07004328 | 48 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07007365 | 3 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07014320 | 48 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07018006 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 07048407 | 3 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 901223 | 48 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 901225 | 48 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | HWKIT | 901289 | 48 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4954_25517 | 4954_25517 | ATL | AC | 86012689 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86008579 | 3 | 3 | 0 | MIM-Shipped |  |  |  | PVT | Y | 2016-03-09 20:02 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4991_25756 | 4991_25756 | TUL | OK | 86009745 | 4 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4991_25756 | 4991_25756 | TUL | OK | 86009745 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 23:11 |  | 4 | DONE | MORSC3889499535 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-04-28 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 4991_25756 | 4991_25756 | TUL | OK | 86009745 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-22 14:11 |  | 4 | DONE | MORSC3889499535 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-04-28 | 2016-05-09 | 0
SERVER | NL | 2016-05-12 | 2016-05-23 | 2016W21 | 5005_25767 | 5005_25767 | LPP | LH | 86012087 | 1 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 12 | DONE | MORSC3889896339 | 2016-05-06 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | NL | 2016-05-12 | 2016-05-23 | 2016W21 | 5005_25767 | 5005_25767 | LPP | LH | 86012087 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 12:37 |  | 1 | DONE | MORSC3889896339 | 2016-05-06 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | NL | 2016-05-12 | 2016-05-23 | 2016W21 | 5005_25767 | 5005_25767 | LPP | LH | 86012087 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 13:07 |  | 1 | DONE | MORSC3889896339 | 2016-05-06 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | NL | 2016-05-12 | 2016-05-23 | 2016W21 | 5081_26126 | 5081_26126 | BRU | WQ | 86012073 | 1 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 18 | DONE | MORSC3889639674 | 2016-05-04 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | NL | 2016-05-12 | 2016-05-23 | 2016W21 | 5081_26126 | 5081_26126 | BRU | WQ | 86012073 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 14:32 |  | 1 | DONE | MORSC3889639674 | 2016-05-04 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | NL | 2016-05-12 | 2016-05-23 | 2016W21 | 5081_26126 | 5081_26126 | BRU | WQ | 86012073 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 14:33 |  | 1 | DONE | MORSC3889639674 | 2016-05-04 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5083_26131 | 5083_26131 | TUL | OM | 86012082 | 2 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5083_26131 | 5083_26131 | TUL | OM | 86012082 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-29 09:47 |  | 2 | DONE | MORSC1252358808 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5083_26131 | 5083_26131 | TUL | OM | 86012082 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 03:11 |  | 2 | DONE | MORSC1252358808 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5099_26185 | 5099_26185 | TUL | OZ | 86012071 | 3 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 36 | DONE | MORSC1252358915 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-04 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5099_26185 | 5099_26185 | TUL | OZ | 86012071 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-29 21:51 |  | 3 | DONE | MORSC3889626180 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5099_26185 | 5099_26185 | TUL | OZ | 86012071 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-29 21:55 |  | 3 | DONE | MORSC3889626180 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5099_26187 | 5099_26187 | TUL | OZ | 86012209 | 3 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 60 | DONE | MORSC3889624325 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-04 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5099_26187 | 5099_26187 | TUL | OZ | 86012209 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012210 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 10:18 |  | 3 | DONE | MORSC3889625210, MORSC3889630275 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-09 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5099_26187 | 5099_26187 | TUL | OZ | 86012209 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012211 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-06 16:43 | last 2 in WIP | 3 | DONE | MORSC3889625210, MORSC3889909824, MORSC3889912164 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-09 | 3
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26219 | 5109_26219 | MRN | QM | 86012109 | 4 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-07 |  | 0 |  |  |  | 2016-05-07 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26219 | 5109_26219 | MRN | QM | 86012109 | 4 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26219 | 5109_26219 | MRN | QM | 86012109 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 14:27 |  | 8 | DONE | MORSC3889631230 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-04 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26406 | 5109_26406 | MRN | QM | 86012068 | 3 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26406 | 5109_26406 | MRN | QM | 86012068 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 04:43 |  | 3 | DONE | MORSC3889631179, MORSC7297742259 | 2016-05-05 | 2016-05-14 | 2016-05-05 |  | 2016-05-06 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26406 | 5109_26406 | MRN | QM | 86012068 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-29 21:49 |  | 3 | DONE | MORSC3889631179 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-04 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26407 | 5109_26407 | MRN | QM | 86012067 | 2 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26407 | 5109_26407 | MRN | QM | 86012067 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-02 04:44 |  | 2 | DONE | MORSC7263420687, MORSC7265720899 | 2016-05-05 | 2016-05-14 | 2016-05-05 |  | 2016-05-06 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26407 | 5109_26407 | MRN | QM | 86012067 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-29 14:18 |  | 2 | DONE | MORSC7263420687 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-04 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26642 | 5109_26642 | MRN | QM | 86012082 | 2 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26642 | 5109_26642 | MRN | QM | 86012082 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | Pending Kit | MS | short 901249 | MS//short 901249 |  | N | 2016-05-14 | XBRKIT460304- NEW | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5109_26642 | 5109_26642 | MRN | QM | 86012082 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | Pending Kit | MS | short 901249 | MS//short 901249 |  | N | 2016-05-14 | XBRKIT460324- NEW | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5224_26588 | C1523 | CHS | VY | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 4 | 0 | MIM-Shipped | NPI | FA | NPI//FA | DC_DEPLOY | Y | 2016-05-11 01:19 | last 1 in WIP | 4 | DONE | MORSC3889631509, MORSC7395777011, MORSC3889924480, MORSC3889929622 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-12 | 2016-05-09 | 3
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5224_26588 | C1523 | CHS | VY | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 4 | 0 | MIM-Shipped | NPI | FA | NPI//FA | DC_DEPLOY | Y | 2016-05-11 01:26 | last 2 in WIP | 4 | DONE | MORSC3889631509, MORSC7395777011, MORSC3889929622 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-12 | 2016-05-09 | 3
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5225_26590 | C1524 | TUL | OO | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-10 21:20 | in WIP | 4 | DONE | MORSC3889909707, MORSC3889910831, MORSC3889930440 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-13 | 2016-05-09 | 4
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5225_26590 | C1524 | TUL | OO | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 4 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-11 01:23 | XNFKIT455858- packing | 4 | DONE | MORSC3889909707, MORSC3889930440 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-13 | 2016-05-09 | 4
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5231_26599 | 5231_26599 | CBF | IS | 86010448 | 6 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 84 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 84 | DONE | MORSC3889625992 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-04 | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5231_26599 | 5231_26599 | CBF | IS | 86010448 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009168 | 6 | 0 | 0 | Pending Kit |  |  |  |  | N | 2016-05-14 | XBRKIT460265- NEW XBRKIT460254- NEW XBRKIT460278- NEW | 2 |  | MORSC3889959097 | 2016-05-13 | 2016-05-14 |  |  | 2016-05-16 | 2016-05-09 | 7
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | 5231_26599 | 5231_26599 | CBF | IS | 86010448 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009169 | 6 | 0 | 0 | Pending Kit |  |  |  |  | N | 2016-05-14 | XBRKIT460267- NEW XBRKIT460260- NEW XBRKIT460289- NEW | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | BTS_86008383_01_A_16W21 | BURSTBUFFER | ATL | QP | 86008383 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008383 | 5 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | BTS_86008385_01_A_16W21 | BURSTBUFFER | ATL | QP | 86008385 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008385 | 5 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | BTS_86009419_02_A_16W21 | GCDBUFFER | ATL | QP | 86009419 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | NRACK.IKEAS | 86009419 | 2 | 0 | 0 | [5 empty] | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-23 | 2016W21 | BTS_86009511_02_A_16W21 | GCDBUFFER | ATL | QP | 86009511 | 4 | 2016-05-23 | 2016-05-23 | RACK-ASM | NRACK.IKEAS | 86009511 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-09 | 0
FABRIC | NL | 2016-05-12 | 2016-05-23 | 2016W21 | BTS_86009511_02_E_16W21 | GCDBUFFER | AMS | EP | 86009511 | 5 | 2016-05-16 | 2016-05-23 | RACK-ASM | NRACK.IKEAS | 86009511 | 5 | 0 | 0 | [5 empty] | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-09 | 0
SERVER | AT | 2016-05-12 | 2016-05-23 | 2016W21 | BTS_86011587_01_A_16W21 | BURSTBUFFER | ATL | QP | 86011587 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86011587 | 5 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-09 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4015_23979 | C1165 | GRQ | EC | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003678 | 4 | 4 | 0 | MIM-Shipped | MS | Material Shortage | MS//Material Shortage | DC_DEPLOY | Y | 2015-11-04 06:27 | 16000622-01 | 4 | DONE | MORSC3889166314 | 2016-03-14 | 2016-05-14 | 2015-11-06 |  | 2015-11-23 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4015_23979 | C1165 | GRQ | EC | 86003857 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86003679 | 4 | 4 | 0 | MIM-Shipped | MS | Material Shortage | MS//Material Shortage | DC_DEPLOY | Y | 2015-11-04 02:03 | 16000622-01 | 4 | DONE | MORSC3889166314 | 2016-03-14 | 2016-05-14 | 2015-11-06 |  | 2015-11-23 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24255 | C1286 | MRN | QB | 86009690 | 5 | 2016-05-09 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24255 | C1286 | MRN | QB | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24257 | C1284 | CHS | VR | 86009690 | 5 | 2016-05-09 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24257 | C1284 | CHS | VR | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24258 | C1283 | CHS | VU | 86009690 | 5 | 2016-05-09 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24258 | C1283 | CHS | VU | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24263 | C1278 | DLS | PC | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-04-26 02:41 |  | 5 | DONE | MORSC6952247241, MORSC7171107710 | 2016-04-29 | 2016-05-14 | 2016-04-29 |  | 2016-05-06 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24263 | C1278 | DLS | PC | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24298 | C1270 | SCL | CB | 86009690 | 5 | 2016-05-02 | 2016-05-02 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-07 |  | 15 | DONE | MORSC445888339 | 2016-03-01 | 2016-05-07 | 2015-11-17 |  | 2015-11-17 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24298 | C1270 | SCL | CB | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-04-16 10:58 |  | 5 | DONE | MORSC3889424143, MORSC6842228493, MORSC3889466580 | 2016-04-19 | 2016-05-14 | 2016-04-19 |  | 2016-05-16 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24301 | C1262 | DLS | PF | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-04-28 04:54 |  | 5 | DONE | MORSC3889557622 | 2016-04-29 | 2016-05-14 | 2016-04-29 |  | 2016-05-06 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4697_24301 | C1262 | DLS | PF | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_24268 | C1310 | TUL | OL | 86009690 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 1 | 1 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-05-11 21:18 |  | 1 | DONE | MORSC3889942611 | 2016-05-12 | 2016-05-14 | 2016-05-12 |  | 2016-05-16 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_24268 | C1310 | TUL | OL | 86009690 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 3 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 15 | DONE | MORSC3884912493 | 2016-03-01 | 2016-05-21 | 2016-02-22 |  | 2016-02-24 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_24271 | C1307 | CBF | IN | 86009690 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 5 | 0 | MIM-Shipped |  |  |  | DC_DEPLOY | Y | 2016-04-28 17:17 |  | 5 | DONE | MORSC1252359260 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_24271 | C1307 | CBF | IN | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 15 | DONE | MORSC3884912477 | 2016-03-01 | 2016-05-21 | 2016-02-22 |  | 2016-02-24 | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_24273 | C1305 | TUL | OT | 86009690 | 5 | 2016-05-09 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_24273 | C1305 | TUL | OT | 86009690 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_26640 | C1310 | TUL | OM | 86009690 | 4 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3S | 86009207 | 4 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-14 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4698_26640 | C1310 | TUL | OM | 86009690 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 4753_24610 | 4753_24610 | LPP | LI | 86010612 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-06 14:55 |  | 1 | DONE | MORSC3889955790 | 2016-05-13 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 4753_24610 | 4753_24610 | LPP | LI | 86010612 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-06 14:45 |  | 1 | DONE | MORSC3889955790 | 2016-05-13 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 4753_24610 | 4753_24610 | LPP | LI | 86010612 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 12 | DONE | MORSC3889955790 | 2016-05-13 | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 4753_24614 | 4753_24614 | LPP | LI | 86008828 | 1 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-14 |  | 4 | DONE | MORSC3889956023 | 2016-05-13 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 4753_24614 | 4753_24614 | LPP | LI | 86008828 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-04 18:45 |  | 2 | DONE | MORSC3889956023 | 2016-05-13 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 4753_24614 | 4753_24614 | LPP | LI | 86008828 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 116 | DONE | MORSC3889956023 | 2016-05-13 | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4767_25779 | 4767_25779 | DLS | PL | 86012369 | 15 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86011506 | 15 | 15 | 0 | MIM-Shipped | MS | short 72000790-01 | MS//short 72000790-01 |  | N | 2016-05-10 17:39 | 12 completed. 3 in WIP | 15 | DONE | MORSC7395777345, MORSC3889912099, MORSC3889919300, MORSC3889929481 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-13 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4767_25779 | 4767_25779 | DLS | PL | 86012369 | 15 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA2D | 86011505 | 15 | 15 | 0 | MIM-Shipped | MS | short 72000790-02 / BOM pending to flip to IKEA 3 DLS | MS//short 72000790-02 / BOM pending to flip to IKEA 3 DLS |  | N | 2016-05-12 12:40 | 11 completed, 2 in WIP , last 2 awating kit deliveryXBRKIT458037- packing | 13 |  | MORSC3889903350, MORSC7395777345, MORSC3889909883, MORSC3889912099, MORSC3889929481, MORSC7479331003, MORSC3889957782 | 2016-05-13 | 2016-05-21 |  |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4767_25779 | 4767_25779 | DLS | PL | 86012369 | 15 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 270 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4926_26401 | 4926_26401 | CBF | JK | 86012827 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012829 | 1 | 1 | 0 | MIM-Shipped | NPI | FA required | NPI//FA required | DVT | Y | 2016-05-07 17:37 | In WIP | 1 | DONE | MORSC7395777528 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-11 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4926_26401 | 4926_26401 | CBF | JK | 86012827 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 10 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-05-21 |  | 10 | DONE | MORSC3889625932 | 2016-05-02 | 2016-05-21 | 2016-05-02 |  | 2016-05-04 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_25647 | 4982_25647 | TUL | OY | 86012213 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 8 | 8 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-29 09:54 |  | 8 | DONE | MORSC3889624064 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_25647 | 4982_25647 | TUL | OY | 86012213 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006052 | 8 | 8 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-29 21:54 |  | 8 | DONE | MORSC3889624064 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_25647 | 4982_25647 | TUL | OY | 86012213 | 8 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_25648 | 4982_25648 | CBF | JB | 86012213 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 5 | 8 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-26 10:29 |  | 6 |  | MORSC3889503604 | 2016-04-26 | 2016-05-14 |  |  | 2016-04-28 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_25648 | 4982_25648 | CBF | JB | 86012213 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006052 | 5 | 8 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-26 10:47 |  | 6 |  | MORSC3889500167, MORSC3889503604 | 2016-04-26 | 2016-05-14 |  |  | 2016-04-28 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_25648 | 4982_25648 | CBF | JB | 86012213 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_26317 | 4982_26317 | TUL | OY | 86012213 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 2 | 2 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-29 09:49 |  | 2 | DONE | MORSC1252358814 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_26317 | 4982_26317 | TUL | OY | 86012213 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006052 | 2 | 2 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-04-28 23:22 |  | 2 | DONE | MORSC1252358814 | 2016-05-02 | 2016-05-14 | 2016-05-02 |  | 2016-05-05 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_26317 | 4982_26317 | TUL | OY | 86012213 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-21 |  | 24 | DONE | MORSC1252358918 | 2016-05-02 | 2016-05-21 | 2016-05-02 |  | 2016-05-04 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_26755 | 4982_26755 | CBF | JB | 86011090 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006051 | 5 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 5 | DONE | MORSC3889910476 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_26755 | 4982_26755 | CBF | JB | 86011090 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86006052 | 5 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 5 | DONE | MORSC7395777367, MORSC3889910476 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 4982_26755 | 4982_26755 | CBF | JB | 86011090 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5026_25883 | 5026_25883 | DLS | PC | 86012216 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86010907 | 4 | 2 | 0 | At-risk | NPI | Fa rack Required / BOM issues on 72000790-01 | NPI//Fa rack Required / BOM issues on 72000790-01 |  | N | 2016-05-14 | FA rack just completed 1 in WIP , last 2 awaiting for kit delivery XBRKIT460330- Void | 2 |  | MORSC3889898415, MORSC3889958871 | 2016-05-13 | 2016-05-14 |  |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5026_25883 | 5026_25883 | DLS | PC | 86012216 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA2D | 86010908 | 4 | 1 | 0 | At-risk | MS | Fa rack Required / BOM issues on 72000790-01 / short switches | MS//Fa rack Required / BOM issues on 72000790-01 / short switches |  | N | 2016-05-14 | FA rack just completed last 3 might short part to kit | 1 |  | MORSC3889929479 | 2016-05-11 | 2016-05-14 |  |  | 2016-05-13 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5026_25883 | 5026_25883 | DLS | PC | 86012216 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 88 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 5038_25912 | 5038_25912 | LPP | LE | 86010548 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009147 | 5 | 5 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-04 13:00 |  | 5 | DONE | MORSC3889939506 | 2016-05-12 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 5038_25912 | 5038_25912 | LPP | LE | 86010548 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009148 | 5 | 5 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-04 17:33 |  | 5 | DONE | MORSC3889939506 | 2016-05-12 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | NL | 2016-05-12 | 2016-05-30 | 2016W22 | 5038_25912 | 5038_25912 | LPP | LE | 86010548 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 70 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 70 | DONE | MORSC3889939506 | 2016-05-12 | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5039_25913 | C1469 | TUL | NB | 86010778 | 8 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5039_25913 | C1469 | TUL | NB | 86010778 | 8 | 2016-05-16 | 2016-05-23 | RACK-ASM | NRACK.IKEA3S | 86010993 | 8 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5039_25913 | C1469 | TUL | NB | 86012428 | 4 | 2016-05-16 | 2016-05-23 | RACK-ASM | NRACK.IKEA3S | 86012428 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5042_25917 | C1468 | TUL | ND | 86010778 | 12 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5042_25917 | C1468 | TUL | ND | 86010778 | 12 | 2016-05-16 | 2016-05-23 | RACK-ASM | NRACK.IKEA3S | 86010993 | 12 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25929 | 5047_25929 | CBF | IO | 86009745 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC3889957864 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25929 | 5047_25929 | CBF | IO | 86009745 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC3889957864 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25929 | 5047_25929 | CBF | IO | 86009745 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25930 | 5047_25930 | CBF | IO | 86012173 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC3889958063 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25930 | 5047_25930 | CBF | IO | 86012173 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC3889958063 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25930 | 5047_25930 | CBF | IO | 86012173 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25932 | 5047_25932 | CBF | JG | 86009868 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 3 | DONE | MORSC3889903737, MORSC3889910864, MORSC3889918459 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25932 | 5047_25932 | CBF | JG | 86009868 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 |  | MORSC3889919060 | 2016-05-10 | 2016-05-14 |  |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25932 | 5047_25932 | CBF | JG | 86009868 | 3 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25933 | 5047_25933 | CBF | JG | 86012090 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 5 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 5 | DONE | MORSC7381549859, MORSC7439817420 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25933 | 5047_25933 | CBF | JG | 86012090 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 5 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 5 | DONE | MORSC3889910479, MORSC7439817420, MORSC3889957799 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25933 | 5047_25933 | CBF | JG | 86012090 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25934 | 5047_25934 | CBF | JG | 86010549 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 | DONE | MORSC3889903890 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25934 | 5047_25934 | CBF | JG | 86010549 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 | DONE | MORSC3889910335 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25934 | 5047_25934 | CBF | JG | 86010549 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25942 | 5047_25942 | TUL | OI | 86009747 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 3 | DONE | MORSC3889911894, MORSC3889919043, MORSC7518723866 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25942 | 5047_25942 | TUL | OI | 86009747 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 3 | DONE | MORSC3889911894, MORSC3889919043, MORSC7518723866 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25942 | 5047_25942 | TUL | OI | 86009747 | 3 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25944 | 5047_25944 | TUL | OI | 86009106 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008703 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC3889957930 | 2016-05-13 | 2016-05-14 | 2016-05-13 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25944 | 5047_25944 | TUL | OI | 86009106 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008704 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC7515162187 | 2016-05-12 | 2016-05-14 | 2016-05-12 |  | 2016-05-16 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25944 | 5047_25944 | TUL | OI | 86009106 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25945 | 5047_25945 | TUL | OL | 86010549 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 |  | MORSC3889909851 | 2016-05-09 | 2016-05-14 |  |  | 2016-05-11 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25945 | 5047_25945 | TUL | OL | 86010549 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 |  | MORSC3889909851, MORSC3889929816 | 2016-05-11 | 2016-05-14 |  |  | 2016-05-13 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25945 | 5047_25945 | TUL | OL | 86010549 | 3 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25946 | 5047_25946 | TUL | OL | 86009868 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 | DONE | MORSC3889903844 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-11 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25946 | 5047_25946 | TUL | OL | 86009868 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 |  | MORSC3889912727 | 2016-05-10 | 2016-05-14 |  |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25946 | 5047_25946 | TUL | OL | 86009868 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25947 | 5047_25947 | DLS | PG | 86012090 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 5 | 5 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-05 13:37 |  | 5 | DONE | MORSC3889569276, MORSC3889886570, MORSC3889899369 | 2016-05-06 | 2016-05-14 | 2016-05-06 |  | 2016-05-13 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25947 | 5047_25947 | DLS | PG | 86012090 | 5 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 5 | 5 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-06 18:25 | 3 completed, 2 in WIP | 5 | DONE | MORSC3889886570, MORSC3889899369, MORSC3889903259 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-13 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25947 | 5047_25947 | DLS | PG | 86012090 | 5 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25950 | 5047_25950 | MRN | QH | 86010549 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 | DONE | MORSC7439817830 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25950 | 5047_25950 | MRN | QH | 86010549 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-25 23:01 |  | 2 | DONE | MORSC3889524221 | 2016-04-26 | 2016-05-14 | 2016-04-26 |  | 2016-04-28 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25950 | 5047_25950 | MRN | QH | 86010549 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25951 | 5047_25951 | MRN | QH | 86009868 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC7464932385 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25951 | 5047_25951 | MRN | QH | 86009868 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 1 | DONE | MORSC3889909699 | 2016-05-09 | 2016-05-14 | 2016-05-09 |  | 2016-05-10 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25951 | 5047_25951 | MRN | QH | 86009868 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25952 | 5047_25952 | MRN | QL | 86010549 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 2 |  | MORSC3889909573, MORSC3783773865 | 2016-05-10 | 2016-05-14 |  |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25952 | 5047_25952 | MRN | QL | 86010549 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 3 | DONE | MORSC3783773865 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25952 | 5047_25952 | MRN | QL | 86010549 | 3 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25955 | 5047_25955 | CHS | VQ | 86009868 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 6 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 6 | DONE | MORSC1294156127, MORSC3889921965 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25955 | 5047_25955 | CHS | VQ | 86009868 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 6 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 6 | DONE | MORSC1294156127, MORSC3889921965, MORSC7468446113 | 2016-05-11 | 2016-05-14 | 2016-05-11 |  | 2016-05-12 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25955 | 5047_25955 | CHS | VQ | 86009868 | 6 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25957 | 5047_25957 | CHS | VQ | 86010549 | 7 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 7 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 5 |  | MORSC7395777514 | 2016-05-09 | 2016-05-14 |  |  | 2016-05-10 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25957 | 5047_25957 | CHS | VQ | 86010549 | 7 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 7 | 7 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-05 20:47 |  | 6 |  | MORSC7395777514 | 2016-05-09 | 2016-05-14 |  |  | 2016-05-10 | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5047_25957 | 5047_25957 | CHS | VQ | 86010549 | 7 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 84 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5153_26359 | C1518 | CHS | VH | 86007920 | 4 | 2016-05-09 | 2016-05-16 | RACK-ASM | NRACK.IKEASC | 86007921 | 4 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5153_26359 | C1518 | CHS | VH | 86007920 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5167_26431 | 5167_26431 | ATL | YK | 86012673 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012668 | 2 | 0 | 0 | At-risk | NPI | Fa rack | NPI//Fa rack |  | N | 2016-05-14 | pending FA rack from other build 5167_26432 | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5167_26431 | 5167_26431 | ATL | YK | 86012673 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012669 | 2 | 0 | 0 | At-risk | NPI | Fa rack | NPI//Fa rack |  | N | 2016-05-14 | pending FA rack from other build 5167_26432 | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5167_26431 | 5167_26431 | ATL | YK | 86012673 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5167_26432 | 5167_26432 | ATL | YK | 86012630 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012668 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5167_26432 | 5167_26432 | ATL | YK | 86012630 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012669 | 1 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5167_26432 | 5167_26432 | ATL | YK | 86012630 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5213_26714 | GCDPVT0002 | ATL | QP | 86012388 | 40 | 2016-05-30 | 2016-05-30 | RACK-ASM | NRACK.IKEA3S | 86012388 | 40 | 0 | 0 |  |  |  |  | DVT | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5213_26753 | NPI0250 | ATL | QP | 86006425 | 1 | 2016-05-23 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86006425 | 1 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-16 | 0
SERVER | AT | 2016-05-12 | 2016-05-30 | 2016W22 | 5372_26976 | 5372_26976 | ATL | AC | 86012567 | 1 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 1 | 0 | 0 |  |  |  |  | DVT | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-16 | 0
FABRIC | NL | 2016-05-12 | 2016-05-30 | 2016W22 | BTS_86009419_02_E_16W22 | GCDBUFFER | AMS | EP | 86009419 | 4 | 2016-05-23 | 2016-05-30 | RACK-ASM | NRACK.IKEAS | 86009419 | 4 | 0 | 0 | [5 empty] | Y | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-16 | 0
FABRIC | NL | 2016-05-12 | 2016-05-30 | 2016W22 | BTS_86009511_02_E_16W22 | GCDBUFFER | AMS | EP | 86009511 | 1 | 2016-05-23 | 2016-05-30 | RACK-ASM | NRACK.IKEAS | 86009511 | 1 | 0 | 0 | [5 empty] | Y | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-16 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86007920 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEASC | 86007921 | 4 | 4 | 0 | MIM-Shipped |  |  |  | OTHER | Y | 2016-03-16 18:29 | last 2 in WIP | 4 | DONE | MORSC3889197350, MORSC3889217050 | 2016-03-21 | 2016-05-14 | 2016-03-17 |  | 2016-03-22 | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86007920 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86009418 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEAS | 86009419 | 8 | 8 | 0 | MIM-Shipped | NPI | FA Required | NPI//FA Required | OTHER | Y | 2016-04-02 05:51 | last 3 racks in WIP | 8 | DONE | MORSC6169526245, MORSC3889305359, MORSC3889332696, MORSC6492973951, MORSC3889374702 | 2016-04-05 | 2016-05-14 | 2016-04-05 |  | 2016-04-07 | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86009418 | 8 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 56 | 0 | 0 | Built-to-Stock |  |  |  | OTHER | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86009478 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 3 | 5 | 0 | MIM-Shipped | NPI | short 86006582 | NPI// short 86006582 | OTHER | Y | 2016-03-21 13:11 |  | 2 | DONE | MORSC6169526245, MORSC3889305359 | 2016-03-29 | 2016-05-14 | 2016-03-29 |  | 2016-03-31 | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86009478 | 3 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86009479 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3S | 86009207 | 2 | 5 | 0 | MIM-Shipped | NPI | short 86006582 | NPI// short 86006582 | OTHER | Y | 2016-03-21 13:11 |  | 2 | DONE | MORSC6169526245, MORSC3889305359 | 2016-03-29 | 2016-05-14 | 2016-03-29 |  | 2016-03-31 | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86010778 | 12 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
FABRIC | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 3844_18929 | C1161 | TUL | NB | 86010778 | 12 | 2016-05-30 | 2016-05-30 | RACK-ASM | NRACK.IKEA3S | 86010993 | 12 | 12 | 0 | MIM-Shipped | NPI | short switches 86008205-01, BOM pending for change , Fa required | NPI//short switches 86008205-01, BOM pending for change , Fa required | OTHER | Y | 2016-04-13 10:35 | last 1 in WIP | 12 | DONE | MORSC3889389505, MORSC3889404363, MORSC3889410057, MORSC3889412862, MORSC3889415294 | 2016-04-13 | 2016-06-04 |  |  | 2016-04-15 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4631_24173 | 4631_24173 | NRT | XA | 86011669 | 18 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA3S | 86009609 | 18 | 7 | 0 | At-risk | OTHER | testing gating kit | OTHER//testing gating kit |  | N | 2016-05-14 | 7 out of 18 were kitted XBFKIT456780- packing 4 racks in WIP | 4 |  | MORSC3889911416 | 2016-05-09 | 2016-05-14 |  |  | 2016-05-17 | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4631_24173 | 4631_24173 | NRT | XA | 86011669 | 18 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4631_24176 | 4631_24176 | NRT | XB | 86011669 | 18 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA3S | 86009609 | 18 | 3 | 0 | At-risk | MS | testing gating kit | MS//testing gating kit |  | N | 2016-05-14 | 7 out of 18 were kitted All kits are at NEW 2 in WIP XBFKIT459369- picking XBFKIT459383- NEW XBFKIT459548- NEW | 3 |  | MORSC3889943068 MORSC3889957941 | 2016-05-13 | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4631_24176 | 4631_24176 | NRT | XB | 86011669 | 18 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4631_24179 | 4631_24179 | NRT | XC | 86011669 | 18 | 2016-05-09 | 2016-05-09 | RACK-ASM | NRACK.IKEA3S | 86009609 | 18 | 0 | 0 | At-risk | MS | testing gating kit | MS//testing gating kit |  | N | 2016-05-14 | 7 out of 18 were kitted XBFKIT459393- NEW XBFKIT459405- NEW XBFKIT460169- NEW XBFKIT460270- NEW | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4631_24179 | 4631_24179 | NRT | XC | 86011669 | 18 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4682_24136 | 4682_24136 | CHS | VL | 86012069 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008383 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-29 17:32 |  | 4 | DONE | MORSC3889640251 | 2016-05-04 | 2016-05-14 | 2016-05-04 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4682_24136 | 4682_24136 | CHS | VL | 86012069 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008385 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-29 19:46 |  | 4 | DONE | MORSC3889640251 | 2016-05-04 | 2016-05-14 | 2016-05-04 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4682_24136 | 4682_24136 | CHS | VL | 86012069 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4683_24140 | 4683_24140 | DLS | PF | 86008825 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 3 | 3 | 0 | MIM-Shipped | EXE | XPO to ship on schedule | EXE//XPO to ship on schedule |  | N | 2015-11-25 17:06 |  | 3 | DONE | MORSC3889625956 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4683_24140 | 4683_24140 | DLS | PF | 86008825 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 3 | 3 | 0 | MIM-Shipped | EXE | XPO to ship on schedule | EXE//XPO to ship on schedule |  | N | 2015-11-25 19:57 |  | 3 | DONE | MORSC3889625956 | 2016-05-03 | 2016-05-14 | 2016-05-03 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4683_24140 | 4683_24140 | DLS | PF | 86008825 | 3 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-06 | 2016W23 | 4683_24143 | 4683_24143 | LPP | LG | 86008828 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 8 | 8 | 0 | MIM-Shipped | EXE | XPO to ship on schedule | EXE//XPO to ship on schedule |  | N | 2015-11-20 09:28 |  | 0 |  |  | 2016-02-02 | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-06 | 2016W23 | 4683_24143 | 4683_24143 | LPP | LG | 86008828 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-06 | 2016W23 | 4683_24143 | 4683_24143 | LPP | LG | 86008828 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4769_24673 | 4769_24673 | CHG | TG | 86007599 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007600 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 05:44 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4769_24673 | 4769_24673 | CHG | TG | 86007599 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007619 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 05:45 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4769_24673 | 4769_24673 | CHG | TG | 86007599 | 1 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4769_25780 | 4769_25780 | CHG | TG | 86012327 | 15 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007600 | 15 | 15 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-29 08:09 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4769_25780 | 4769_25780 | CHG | TG | 86012327 | 15 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007619 | 15 | 15 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-05 06:28 |  | 0 |  |  | 2016-05-03 | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | SG | 2016-05-12 | 2016-06-06 | 2016W23 | 4769_25780 | 4769_25780 | CHG | TG | 86012327 | 15 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 180 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4966_25549 | 4966_25549 | MRN | QB | 86006453 | 4 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86008703 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4966_25549 | 4966_25549 | MRN | QB | 86006453 | 4 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86008704 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4966_25549 | 4966_25549 | MRN | QB | 86006453 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 56 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4974_25595 | 4974_25595 | MRN | QB | 86011070 | 10 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86004101 | 10 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4974_25595 | 4974_25595 | MRN | QB | 86011070 | 10 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86004102 | 10 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4974_25595 | 4974_25595 | MRN | QB | 86011070 | 10 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4974_25668 | 4974_25668 | MRN | QB | 86012007 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4974_25668 | 4974_25668 | MRN | QB | 86012007 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4974_25668 | 4974_25668 | MRN | QB | 86012007 | 2 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4980_25696 | 4980_25696 | SCL | CE | 86006458 | 4 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 56 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4980_25696 | 4980_25696 | SCL | CE | 86006458 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008703 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 23:24 |  | 4 | DONE | MORSC6952247263 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4980_25696 | 4980_25696 | SCL | CE | 86006458 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008704 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-22 04:53 |  | 4 | DONE | MORSC3889485765, MORSC6952247263 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4980_25744 | 4980_25744 | SCL | CE | 86012091 | 1 | 2016-05-09 | 2016-05-09 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4980_25744 | 4980_25744 | SCL | CE | 86012091 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86003986 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 03:46 |  | 1 | DONE | MORSC3889487184 | 2016-04-21 | 2016-05-14 | 2016-04-21 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4980_25744 | 4980_25744 | SCL | CE | 86012091 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86003988 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-21 15:57 |  | 1 | DONE | MORSC3889498207 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-05-23 | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4988_25671 | 4988_25671 | CBF | JN | 86013007 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012268 | 4 | 0 | 0 | Pending Kit | NPI | FA required | NPI//FA required | OTHER | Y | 2016-05-14 | FA rack kti XBRKIT459870- NEW Can;'t kit more until FA rack kit is delivered | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4988_25671 | 4988_25671 | CBF | JN | 86013007 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012269 | 4 | 0 | 0 | Pending Kit | NPI | FA required | NPI//FA required | OTHER | Y | 2016-05-14 | FA rack kti XBRKIT459870- NEW Can;'t kit more until FA rack kit is delivered | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 4988_25671 | 4988_25671 | CBF | JN | 86013007 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-05-28 |  | 48 | DONE | MORSC3889625111 | 2016-05-02 | 2016-05-28 | 2016-05-02 |  | 2016-05-04 | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-06 | 2016W23 | 5047_25935 | 5047_25935 | LPP | LH | 86009868 | 1 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-06 | 2016W23 | 5047_25935 | 5047_25935 | LPP | LH | 86009868 | 1 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-06 | 2016W23 | 5047_25935 | 5047_25935 | LPP | LH | 86009868 | 1 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5167_26433 | 5167_26433 | ATL | YK | 86012629 | 4 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86012647 | 4 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5167_26433 | 5167_26433 | ATL | YK | 86012629 | 4 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86012648 | 4 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5167_26433 | 5167_26433 | ATL | YK | 86012629 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 56 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5167_26434 | 5167_26434 | ATL | YK | 86012674 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012647 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 01:09 |  | 1 | DONE |  | 2016-05-02 | 2016-05-14 | 2016-05-02 |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5167_26434 | 5167_26434 | ATL | YK | 86012674 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012648 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 18:36 |  | 1 | DONE |  | 2016-05-02 | 2016-05-14 | 2016-05-02 |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5167_26434 | 5167_26434 | ATL | YK | 86012674 | 1 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5168_26436 | 5168_26436 | TUL | OQ | 86012109 | 26 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 104 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5168_26436 | 5168_26436 | TUL | OQ | 86012109 | 26 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 52 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5168_26436 | 5168_26436 | TUL | OQ | 86012109 | 26 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 3016 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5168_26437 | 5168_26437 | TUL | OQ | 86012111 | 9 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 36 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5168_26437 | 5168_26437 | TUL | OQ | 86012111 | 9 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 18 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5168_26437 | 5168_26437 | TUL | OQ | 86012111 | 9 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 1044 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5175_26451 | 5175_26451 | TUL | OQ | 86012497 | 4 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86012086 | 4 | 0 | 0 |  |  |  |  | PVT | Y | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5175_26451 | 5175_26451 | TUL | OQ | 86012497 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5284_26741 | 5284_26741 | CHS | VO | 86010448 | 6 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86009168 | 6 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5284_26741 | 5284_26741 | CHS | VO | 86010448 | 6 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86009169 | 6 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5284_26741 | 5284_26741 | CHS | VO | 86010448 | 6 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 84 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26748 | 5286_26748 | CBF | IX | 86012067 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26748 | 5286_26748 | CBF | IX | 86012067 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26748 | 5286_26748 | CBF | IX | 86012067 | 2 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26749 | 5286_26749 | CBF | IX | 86012109 | 18 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 72 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26749 | 5286_26749 | CBF | IX | 86012109 | 18 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 36 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26749 | 5286_26749 | CBF | IX | 86012109 | 18 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 2088 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26750 | 5286_26750 | CBF | IX | 86012108 | 1 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26750 | 5286_26750 | CBF | IX | 86012108 | 1 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5286_26750 | 5286_26750 | CBF | IX | 86012108 | 1 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5303_26791 | 5303_26791 | TUL | OV | 86012109 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5303_26791 | 5303_26791 | TUL | OV | 86012109 | 4 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 8 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5303_26791 | 5303_26791 | TUL | OV | 86012109 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5304_26792 | 5304_26792 | TUL | OJ | 86012109 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5304_26792 | 5304_26792 | TUL | OJ | 86012109 | 4 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 8 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5304_26792 | 5304_26792 | TUL | OJ | 86012109 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5305_26793 | 5305_26793 | TUL | OW | 86012109 | 4 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5305_26793 | 5305_26793 | TUL | OW | 86012109 | 4 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 8 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5305_26793 | 5305_26793 | TUL | OW | 86012109 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5308_26795 | 5308_26795 | TUL | OJ | 86012109 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5308_26795 | 5308_26795 | TUL | OJ | 86012109 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-23 | 0
SERVER | AT | 2016-05-12 | 2016-06-06 | 2016W23 | 5308_26795 | 5308_26795 | TUL | OJ | 86012109 | 2 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-23 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4362_22768 | 4362_22768 | GRQ | EC | 86010548 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009147 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-31 13:42 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4362_22768 | 4362_22768 | GRQ | EC | 86010548 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009148 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-31 18:29 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4362_22768 | 4362_22768 | GRQ | EC | 86010548 | 4 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 56 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4580_23765 | 4580_23765 | BRU | WS | 86009489 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009168 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-11 19:40 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4580_23765 | 4580_23765 | BRU | WS | 86009489 | 3 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009169 | 3 | 3 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-11 19:52 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4580_23765 | 4580_23765 | BRU | WS | 86009489 | 3 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4631_24180 | 4631_24180 | NRT | XA | 86010320 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | NRACK.IKEA3S | 86009609 | 2 | 0 | 0 | At-risk | MS | NPI-Cosigned 72005205-01 | MS//NPI-Cosigned 72005205-01 |  | N | 2016-05-21 | Will kit more once more kits are delivered | 0 |  |  | 2016-05-09 | 2016-05-21 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 4631_24180 | 4631_24180 | NRT | XA | 86010320 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 8 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4697_24260 | C1281 | MRN | QG | 86009690 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4697_24260 | C1281 | MRN | QG | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24275 | C1303 | TUL | OF | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24275 | C1303 | TUL | OF | 86009690 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24276 | C1302 | CBF | IU | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24276 | C1302 | CBF | IU | 86009690 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24278 | C1301 | CBF | JA | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24278 | C1301 | CBF | JA | 86009690 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24280 | C1300 | TUL | OZ | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24280 | C1300 | TUL | OZ | 86009690 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24282 | C1298 | CBF | IX | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24282 | C1298 | CBF | IX | 86009690 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24283 | C1297 | CBF | JD | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24283 | C1297 | CBF | JD | 86009690 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24284 | C1296 | CBF | JK | 86009690 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24284 | C1296 | CBF | JK | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24285 | C1295 | TUL | OW | 86009690 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24285 | C1295 | TUL | OW | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24286 | C1294 | CBF | IJ | 86009690 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24286 | C1294 | CBF | IJ | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24289 | C1291 | CBF | JL | 86009690 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24289 | C1291 | CBF | JL | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24291 | C1290 | TUL | OQ | 86009690 | 5 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 |  |  |  |  | DC_DEPLOY | Y | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4698_24291 | C1290 | TUL | OQ | 86009690 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 15 | 0 | 0 | Pull-from-Stock |  |  |  | DC_DEPLOY | Y | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4760_24641 | 4760_24641 | GRQ | EC | 86010548 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-30 13:38 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4760_24641 | 4760_24641 | GRQ | EC | 86010548 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-03-30 13:53 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4760_24641 | 4760_24641 | GRQ | EC | 86010548 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4841_24957 | 4841_24957 | SCL | CB | 86009284 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 1 | 1 | MIM-Shipped |  |  |  |  | N | 2016-03-02 18:16 |  | 2 | DONE | MORSC3884989261, MORSC3889075515 | 2016-03-07 | 2016-05-14 | 2016-03-07 |  | 2016-06-06 | 2016-05-30 | 7
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4841_24957 | 4841_24957 | SCL | CB | 86009284 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 1 | 1 | MIM-Shipped |  |  |  |  | N | 2016-04-07 08:47 |  | 2 | DONE | MORSC3884989261, MORSC3889424376 | 2016-04-15 | 2016-05-14 | 2016-04-15 |  | 2016-05-30 | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4841_24957 | 4841_24957 | SCL | CB | 86009284 | 2 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4975_25596 | 4975_25596 | BRU | WS | 86012219 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 11:32 | in WIP | 2 | DONE | MORSC3889489079 | 2016-04-22 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4975_25596 | 4975_25596 | BRU | WS | 86012219 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 11:43 | in WIP | 2 | DONE | MORSC3889485364 | 2016-04-21 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4975_25596 | 4975_25596 | BRU | WS | 86012219 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 24 | DONE | MORSC3889485364 | 2016-04-21 | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4975_25597 | 4975_25597 | BRU | WS | 86005342 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 20:22 | in WIP | 0 |  |  | 2016-04-19 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4975_25597 | 4975_25597 | BRU | WS | 86005342 | 2 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4975_25597 | 4975_25597 | BRU | WS | 86005342 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4976_25650 | 4976_25650 | BRU | WS | 86009284 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 18:03 |  | 4 | DONE | MORSC3889503369 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4976_25650 | 4976_25650 | BRU | WS | 86009284 | 4 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 4 | 4 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-20 20:16 |  | 4 | DONE | MORSC3889503369 | 2016-04-26 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4976_25650 | 4976_25650 | BRU | WS | 86009284 | 4 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 72 | DONE | MORSC3889503369 | 2016-04-26 | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4976_25651 | 4976_25651 | BRU | WS | 86009264 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008943 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-03 18:37 |  | 8 | DONE | MORSC3889639671 | 2016-05-04 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4976_25651 | 4976_25651 | BRU | WS | 86009264 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008944 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-03 20:11 | In WIP | 7 |  | MORSC3889639671 | 2016-05-04 | 2016-05-14 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 4976_25651 | 4976_25651 | BRU | WS | 86009264 | 8 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 144 | DONE | MORSC3889639671 | 2016-05-04 | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4980_26410 | 4980_26410 | SCL | CE | 86012607 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-22 10:40 |  | 6 | DONE | MORSC3889486430, MORSC3889498422 | 2016-04-25 | 2016-05-14 | 2016-04-25 |  | 2016-05-30 | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4980_26410 | 4980_26410 | SCL | CE | 86012607 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-25 18:00 |  | 6 | DONE | MORSC3889498422, MORSC3889524546 | 2016-04-27 | 2016-05-14 | 2016-04-27 |  | 2016-05-30 | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 4980_26410 | 4980_26410 | SCL | CE | 86012607 | 6 | 2016-05-16 | 2016-05-16 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5022_25873 | 5022_25873 | ATL | YB | 86012074 | 3 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86011349 | 3 | 3 | 0 | MIM-Shipped | MS | 07097737 & 901249 | MS//07097737 & 901249 |  | N | 2016-05-05 20:45 | short 07097737, 901249 to kit in FB | 0 |  |  | 2016-05-03 | 2016-05-21 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5022_25873 | 5022_25873 | ATL | YB | 86012074 | 3 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86011356 | 3 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  | 2016-05-03 | 2016-05-21 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5022_25873 | 5022_25873 | ATL | YB | 86012074 | 3 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5022_25874 | 5022_25874 | ATL | YB | 86012079 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86011349 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-28 17:29 |  | 1 | DONE |  | 2016-05-02 | 2016-05-14 | 2016-05-02 |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5022_25874 | 5022_25874 | ATL | YB | 86012079 | 1 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86011356 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-04 04:18 |  | 0 |  |  | 2016-05-03 | 2016-05-21 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5022_25874 | 5022_25874 | ATL | YB | 86012079 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5026_25884 | 5026_25884 | DLS | PC | 86012214 | 6 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA2D | 86003383 | 6 | 6 | 0 | MIM-Shipped | NPI | Fa rack / Material shoratges 72000790-02 | NPI//Fa rack / Material shoratges 72000790-02 |  | N | 2016-05-06 20:23 | last 2 in WIP | 6 | DONE | MORSC7351216741, MORSC3889911893 | 2016-05-10 | 2016-05-21 | 2016-05-10 |  | 2016-05-16 | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5026_25884 | 5026_25884 | DLS | PC | 86012214 | 6 | 2016-05-09 | 2016-05-16 | RACK-ASM | MRACK.IKEA2D | 86003384 | 6 | 6 | 0 | MIM-Shipped | NPI | Fa rack / Material shoratges 72000790-02 | NPI//Fa rack / Material shoratges 72000790-02 |  | N | 2016-05-06 22:03 | in WIP | 6 | DONE | MORSC3889903220, MORSC3889911893 | 2016-05-10 | 2016-05-21 | 2016-05-10 |  | 2016-05-16 | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5026_25884 | 5026_25884 | DLS | PC | 86012214 | 6 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 108 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25926 | 5047_25926 | GRQ | EC | 86012090 | 6 | 2016-05-09 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004101 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-06 19:28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25926 | 5047_25926 | GRQ | EC | 86012090 | 6 | 2016-05-09 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004102 | 6 | 6 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-10 16:21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25926 | 5047_25926 | GRQ | EC | 86012090 | 6 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25927 | 5047_25927 | GRQ | EC | 86012087 | 4 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004101 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25927 | 5047_25927 | GRQ | EC | 86012087 | 4 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004102 | 4 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25927 | 5047_25927 | GRQ | EC | 86012087 | 4 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25928 | 5047_25928 | GRQ | EC | 86009868 | 1 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25928 | 5047_25928 | GRQ | EC | 86009868 | 1 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25928 | 5047_25928 | GRQ | EC | 86009868 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25936 | 5047_25936 | LPP | LH | 86010549 | 2 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25936 | 5047_25936 | LPP | LH | 86010549 | 2 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5047_25936 | 5047_25936 | LPP | LH | 86010549 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5109_26218 | 5109_26218 | MRN | QM | 86012111 | 3 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5109_26218 | 5109_26218 | MRN | QM | 86012111 | 3 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5109_26218 | 5109_26218 | MRN | QM | 86012111 | 3 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5132_26291 | C1489 | CBF | JN | 86005444 | 8 | 2016-05-23 | 2016-05-23 | RACK-ASM | NRACK.IKEAS | 86005420 | 8 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5132_26291 | C1489 | CBF | JN | 86005444 | 8 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 56 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5132_26291 | C1489 | CBF | JN | 86011012 | 32 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5132_26291 | C1489 | CBF | JN | 86011012 | 32 | 2016-06-06 | 2016-06-06 | RACK-ASM | NRACK.IKEA3S | 86010988 | 32 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5168_26435 | 5168_26435 | TUL | OQ | 86012100 | 26 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004101 | 26 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5168_26435 | 5168_26435 | TUL | OQ | 86012100 | 26 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86004102 | 26 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5168_26435 | 5168_26435 | TUL | OQ | 86012100 | 26 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 312 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5252_26652 | C1548 | MRN | QN | 86005444 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 7 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5252_26652 | C1548 | MRN | QN | 86005444 | 1 | 2016-06-06 | 2016-06-06 | RACK-ASM | NRACK.IKEAS | 86005420 | 1 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5252_26652 | C1548 | MRN | QN | 86009636 | 4 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5252_26652 | C1548 | MRN | QN | 86009636 | 4 | 2016-06-06 | 2016-06-06 | RACK-ASM | NRACK.IKEASC | 86009637 | 4 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5309_26796 | 5309_26796 | TUL | OW | 86012109 | 3 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5309_26796 | 5309_26796 | TUL | OW | 86012109 | 3 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5309_26796 | 5309_26796 | TUL | OW | 86012109 | 3 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5310_26797 | 5310_26797 | TUL | OV | 86012109 | 2 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5310_26797 | 5310_26797 | TUL | OV | 86012109 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5310_26797 | 5310_26797 | TUL | OV | 86012109 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5317_26815 | C1545 | DLS | PL | 86009512 | 8 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
FABRIC | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5317_26815 | C1545 | DLS | PL | 86009512 | 8 | 2016-05-30 | 2016-05-30 | RACK-ASM | NRACK.IKEAS | 86009511 | 8 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5352_26911 | 5352_26911 | SIN | SC | 86012072 | 1 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5352_26911 | 5352_26911 | SIN | SC | 86012072 | 1 | 2016-05-16 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5352_26911 | 5352_26911 | SIN | SC | 86012072 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5411_27093 | 5411_27093 | TUL | OM | 86012073 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5411_27093 | 5411_27093 | TUL | OM | 86012073 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5411_27093 | 5411_27093 | TUL | OM | 86012073 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5411_27094 | 5411_27094 | TUL | OM | 86012173 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5411_27094 | 5411_27094 | TUL | OM | 86012173 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5411_27094 | 5411_27094 | TUL | OM | 86012173 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5420_27122 | 5420_27122 | BRU | WQ | 86012073 | 3 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 3 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5420_27122 | 5420_27122 | BRU | WQ | 86012073 | 3 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 3 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5420_27122 | 5420_27122 | BRU | WQ | 86012073 | 3 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5420_27123 | 5420_27123 | BRU | WQ | 86012173 | 4 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 4 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5420_27123 | 5420_27123 | BRU | WQ | 86012173 | 4 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 4 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | NL | 2016-05-12 | 2016-06-13 | 2016W24 | 5420_27123 | 5420_27123 | BRU | WQ | 86012173 | 4 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5421_27124 | 5421_27124 | SIN | SC | 86012073 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5421_27124 | 5421_27124 | SIN | SC | 86012073 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5421_27124 | 5421_27124 | SIN | SC | 86012073 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5421_27125 | 5421_27125 | SIN | SC | 86012173 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5421_27125 | 5421_27125 | SIN | SC | 86012173 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5421_27125 | 5421_27125 | SIN | SC | 86012173 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5422_27126 | 5422_27126 | CHG | TI | 86012073 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5422_27126 | 5422_27126 | CHG | TI | 86012073 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5422_27126 | 5422_27126 | CHG | TI | 86012073 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5422_27127 | 5422_27127 | CHG | TI | 86012173 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5422_27127 | 5422_27127 | CHG | TI | 86012173 | 2 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | SG | 2016-05-12 | 2016-06-13 | 2016W24 | 5422_27127 | 5422_27127 | CHG | TI | 86012173 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5423_27129 | 5423_27129 | CBF | IU | 86012173 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5423_27129 | 5423_27129 | CBF | IU | 86012173 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-13 | 2016W24 | 5423_27129 | 5423_27129 | CBF | IU | 86012173 | 1 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-05-30 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 3733_21739 | 3733_21739 | DLS | PJ | 86008540 | 6 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA2 | 86008483 | 6 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 3733_21739 | 3733_21739 | DLS | PJ | 86008540 | 6 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA2 | 86008484 | 6 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 3733_21739 | 3733_21739 | DLS | PJ | 86008540 | 6 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 120 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | SG | 2016-05-12 | 2016-06-20 | 2016W25 | 5112_26227 | 5112_26227 | CHG | TI | 86012088 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004101 | 16 | 16 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-10 07:54 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-06-06 | 0
SERVER | SG | 2016-05-12 | 2016-06-20 | 2016W25 | 5112_26227 | 5112_26227 | CHG | TI | 86012088 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86004102 | 16 | 16 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-12 06:14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-06-06 | 0
SERVER | SG | 2016-05-12 | 2016-06-20 | 2016W25 | 5112_26227 | 5112_26227 | CHG | TI | 86012088 | 16 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 192 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | SG | 2016-05-12 | 2016-06-20 | 2016W25 | 5112_26228 | 5112_26228 | CHG | TI | 86012093 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008703 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-12 07:46 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-06-06 | 0
SERVER | SG | 2016-05-12 | 2016-06-20 | 2016W25 | 5112_26228 | 5112_26228 | CHG | TI | 86012093 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008704 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-05-12 07:45 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-06-06 | 0
SERVER | SG | 2016-05-12 | 2016-06-20 | 2016W25 | 5112_26228 | 5112_26228 | CHG | TI | 86012093 | 1 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5150_26375 | 5150_26375 | GRQ | ED | 86007280 | 2 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5150_26375 | 5150_26375 | GRQ | ED | 86007280 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5150_26375 | 5150_26375 | GRQ | ED | 86007280 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5156_26362 | 5156_26362 | CBF | JA | 86012097 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86004101 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5156_26362 | 5156_26362 | CBF | JA | 86012097 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86004102 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5156_26362 | 5156_26362 | CBF | JA | 86012097 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5157_26378 | 5157_26378 | ATL | YW | 86012080 | 3 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86011472 | 6 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5157_26378 | 5157_26378 | ATL | YW | 86012080 | 3 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5159_26383 | 5159_26383 | CBF | IY | 86012110 | 10 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07017435 | 40 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5159_26383 | 5159_26383 | CBF | IY | 86012110 | 10 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 20 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5159_26383 | 5159_26383 | CBF | IY | 86012110 | 10 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07000733 | 1160 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5159_26384 | 5159_26384 | CBF | IY | 86012110 | 7 | 2016-05-23 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 14 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5159_26384 | 5159_26384 | CBF | IY | 86012110 | 7 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07017435 | 28 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5159_26384 | 5159_26384 | CBF | IY | 86012110 | 7 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07000733 | 812 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5227_26593 | 5227_26593 | CBF | IM | 86012110 | 6 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07017435 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5227_26593 | 5227_26593 | CBF | IM | 86012110 | 6 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 12 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5227_26593 | 5227_26593 | CBF | IM | 86012110 | 6 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07000733 | 696 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26620 | 5237_26620 | GRQ | ED | 86012067 | 7 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008383 | 7 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26620 | 5237_26620 | GRQ | ED | 86012067 | 7 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008385 | 7 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26620 | 5237_26620 | GRQ | ED | 86012067 | 7 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 84 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26621 | 5237_26621 | GRQ | ED | 86012068 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26621 | 5237_26621 | GRQ | ED | 86012068 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26621 | 5237_26621 | GRQ | ED | 86012068 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26622 | 5237_26622 | GRQ | ED | 86012108 | 5 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26622 | 5237_26622 | GRQ | ED | 86012108 | 5 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 10 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26622 | 5237_26622 | GRQ | ED | 86012108 | 5 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26623 | 5237_26623 | GRQ | ED | 86012192 | 10 | 2016-05-30 | 2016-05-30 | BATTERY-BOX | PACK | 07017435 | 40 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26623 | 5237_26623 | GRQ | ED | 86012192 | 10 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 20 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | NL | 2016-05-12 | 2016-06-20 | 2016W25 | 5237_26623 | 5237_26623 | GRQ | ED | 86012192 | 10 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07000733 | 1160 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5351_26910 | 5351_26910 | DLS | PF | 86012067 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5351_26910 | 5351_26910 | DLS | PF | 86012067 | 1 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5351_26910 | 5351_26910 | DLS | PF | 86012067 | 1 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5418_27118 | 5418_27118 | CHS | VL | 86012073 | 1 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5418_27118 | 5418_27118 | CHS | VL | 86012073 | 1 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5418_27118 | 5418_27118 | CHS | VL | 86012073 | 1 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5418_27119 | 5418_27119 | CHS | VL | 86012173 | 4 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008943 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5418_27119 | 5418_27119 | CHS | VL | 86012173 | 4 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008944 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5418_27119 | 5418_27119 | CHS | VL | 86012173 | 4 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5419_27120 | 5419_27120 | MRN | QM | 86012073 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5419_27120 | 5419_27120 | MRN | QM | 86012073 | 2 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5419_27120 | 5419_27120 | MRN | QM | 86012073 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5419_27121 | 5419_27121 | MRN | QM | 86012173 | 6 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008943 | 6 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5419_27121 | 5419_27121 | MRN | QM | 86012173 | 6 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA3 | 86008944 | 6 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-06 | 0
SERVER | AT | 2016-05-12 | 2016-06-20 | 2016W25 | 5419_27121 | 5419_27121 | MRN | QM | 86012173 | 6 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | ANTARES | 45000039-05 | 108 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-06 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86005444 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 28 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86005444 | 4 | 2016-05-23 | 2016-05-30 | RACK-ASM | NRACK.IKEAS | 86005420 | 4 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86007920 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 32 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86007920 | 4 | 2016-05-23 | 2016-05-30 | RACK-ASM | NRACK.IKEASC | 86007921 | 4 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86009478 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3S | 86009207 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86009478 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 20 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86009512 | 4 | 2016-05-23 | 2016-05-23 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-13 | 0
FABRIC | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 3836_18921 | C1170 | CHG | TM | 86009512 | 4 | 2016-05-30 | 2016-05-30 | RACK-ASM | NRACK.IKEAS | 86009511 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4019_21734 | 4019_21734 | GRQ | EG | 86011028 | 3 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86010807 | 6 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4019_21734 | 4019_21734 | GRQ | EG | 86011028 | 3 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4022_21736 | 4022_21736 | GRQ | EI | 86011028 | 6 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86010807 | 12 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4022_21736 | 4022_21736 | GRQ | EI | 86011028 | 6 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 108 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4753_24611 | 4753_24611 | LPP | LI | 86010612 | 1 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4753_24611 | 4753_24611 | LPP | LI | 86010612 | 1 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4753_24611 | 4753_24611 | LPP | LI | 86010612 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4753_24615 | 4753_24615 | LPP | LI | 86008828 | 1 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4753_24615 | 4753_24615 | LPP | LI | 86008828 | 1 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4753_24615 | 4753_24615 | LPP | LI | 86008828 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4757_24631 | 4757_24631 | TUL | OH | 86012367 | 3 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012387 | 3 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4757_24631 | 4757_24631 | TUL | OH | 86012367 | 3 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 21 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4767_26251 | 4767_26251 | DLS | PL | 86012227 | 40 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA2D | 86011498 | 40 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4767_26251 | 4767_26251 | DLS | PL | 86012227 | 40 | 2016-05-30 | 2016-05-30 | RACK-ASM | MRACK.IKEA2D | 86011499 | 40 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4767_26251 | 4767_26251 | DLS | PL | 86012227 | 40 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 720 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4792_24771 | 4792_24771 | CHS | VA | 86012367 | 7 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012387 | 7 | 7 | 0 | MIM-Shipped | NPI | FA required | NPI//FA required |  | N | 2016-05-07 02:48 | last 4 in WIP | 7 | DONE | MORSC3783773868 | 2016-05-10 | 2016-05-14 | 2016-05-10 |  | 2016-05-12 | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4792_24771 | 4792_24771 | CHS | VA | 86012367 | 7 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 49 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4938_25390 | 4938_25390 | TUL | OT | 86012212 | 4 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 4 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4938_25390 | 4938_25390 | TUL | OT | 86012212 | 4 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 4 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4938_25390 | 4938_25390 | TUL | OT | 86012212 | 4 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 40 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4939_25391 | 4939_25391 | LPP | LO | 86012212 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4939_25391 | 4939_25391 | LPP | LO | 86012212 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4939_25391 | 4939_25391 | LPP | LO | 86012212 | 9 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 90 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4940_25392 | 4940_25392 | LPP | LM | 86012212 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4940_25392 | 4940_25392 | LPP | LM | 86012212 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 4940_25392 | 4940_25392 | LPP | LM | 86012212 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 50 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4941_25393 | 4941_25393 | CHS | VO | 86012212 | 6 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 6 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4941_25393 | 4941_25393 | CHS | VO | 86012212 | 6 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 6 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4941_25393 | 4941_25393 | CHS | VO | 86012212 | 6 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25655 | 4985_25655 | TUL | OH | 86012174 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25655 | 4985_25655 | TUL | OH | 86012174 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25655 | 4985_25655 | TUL | OH | 86012174 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 80 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25657 | 4985_25657 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25657 | 4985_25657 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25657 | 4985_25657 | TUL | OH | 86012174 | 8 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 128 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25687 | 4985_25687 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25687 | 4985_25687 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25687 | 4985_25687 | TUL | OH | 86012174 | 8 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 128 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25688 | 4985_25688 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25688 | 4985_25688 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25688 | 4985_25688 | TUL | OH | 86012174 | 8 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 128 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25689 | 4985_25689 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25689 | 4985_25689 | TUL | OH | 86012174 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25689 | 4985_25689 | TUL | OH | 86012174 | 8 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 128 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25690 | 4985_25690 | TUL | OH | 86012174 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009246 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 08:34 | in WIP | 8 | DONE | MORSC6696355296, MORSC3889412931 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-15 | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25690 | 4985_25690 | TUL | OH | 86012174 | 8 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86009254 | 8 | 8 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-13 08:31 | 1 shipped, 1 in completed not shipped, the rest are in WIP | 8 | DONE | MORSC6696355296, MORSC3889412931 | 2016-04-13 | 2016-05-14 | 2016-04-13 |  | 2016-04-15 | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25690 | 4985_25690 | TUL | OH | 86012174 | 8 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 128 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25691 | 4985_25691 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25691 | 4985_25691 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25691 | 4985_25691 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25692 | 4985_25692 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25692 | 4985_25692 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25692 | 4985_25692 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25693 | 4985_25693 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25693 | 4985_25693 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25693 | 4985_25693 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25694 | 4985_25694 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009246 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 8 |  | MORSC3889909869, MORSC7464932595 | 2016-05-11 | 2016-06-11 |  |  | 2016-05-12 | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25694 | 4985_25694 | CHS | VY | 86012174 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86009254 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 8 |  | MORSC3889909869, MORSC3783773901, MORSC7464932595 | 2016-05-11 | 2016-06-11 |  |  | 2016-05-12 | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 4985_25694 | 4985_25694 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5003_25764 | 5003_25764 | ATL | YI | 86012212 | 11 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 11 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5003_25764 | 5003_25764 | ATL | YI | 86012212 | 11 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 11 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5003_25764 | 5003_25764 | ATL | YI | 86012212 | 11 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 110 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5004_25765 | 5004_25765 | TUL | OQ | 86012212 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5004_25765 | 5004_25765 | TUL | OQ | 86012212 | 9 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 9 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5004_25765 | 5004_25765 | TUL | OQ | 86012212 | 9 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 90 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 5027_25889 | 5027_25889 | LPP | LO | 86012212 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 5027_25889 | 5027_25889 | LPP | LO | 86012212 | 8 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 8 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 5027_25889 | 5027_25889 | LPP | LO | 86012212 | 8 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 80 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5113_26229 | 5113_26229 | CHG | TH | 86012212 | 16 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012208 | 16 | 0 | 0 | [5 empty] | N | 2016-05-14 |  | 0 |  |  |  | 2016-05-14 |  |  |  | 2016-06-13 | 0
SERVER | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 5113_26229 | 5113_26229 | CHG | TH | 86012212 | 16 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86012207 | 16 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-06-13 | 0
SERVER | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 5113_26229 | 5113_26229 | CHG | TH | 86012212 | 16 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 160 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 5150_26374 | 5150_26374 | GRQ | ED | 86012109 | 19 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 76 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 5150_26374 | 5150_26374 | GRQ | ED | 86012109 | 19 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 38 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | NL | 2016-05-12 | 2016-06-27 | 2016W26 | 5150_26374 | 5150_26374 | GRQ | ED | 86012109 | 19 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 2204 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5151_26355 | 5151_26355 | MRN | QB | 86012109 | 10 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 40 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5151_26355 | 5151_26355 | MRN | QB | 86012109 | 10 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 20 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5151_26355 | 5151_26355 | MRN | QB | 86012109 | 10 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 1160 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5151_26557 | 5151_26557 | MRN | QB | 86012109 | 5 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5151_26557 | 5151_26557 | MRN | QB | 86012109 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 10 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5151_26557 | 5151_26557 | MRN | QB | 86012109 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26381 | 5159_26381 | CBF | IY | 86012070 | 10 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008383 | 10 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26381 | 5159_26381 | CBF | IY | 86012070 | 10 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008385 | 10 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26381 | 5159_26381 | CBF | IY | 86012070 | 10 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26677 | 5159_26677 | CBF | IY | 86012070 | 10 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008383 | 10 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26677 | 5159_26677 | CBF | IY | 86012070 | 10 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008385 | 10 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26677 | 5159_26677 | CBF | IY | 86012070 | 10 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26678 | 5159_26678 | CBF | IY | 86012070 | 6 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008383 | 6 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26678 | 5159_26678 | CBF | IY | 86012070 | 6 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008385 | 6 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5159_26678 | 5159_26678 | CBF | IY | 86012070 | 6 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 5162_26408 | 5162_26408 | CHG | TI | 86010548 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86009147 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-06-13 | 0
SERVER | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 5162_26408 | 5162_26408 | CHG | TI | 86010548 | 2 | 2016-05-16 | 2016-05-16 | RACK-ASM | MRACK.IKEA3 | 86009148 | 2 | 0 | 0 | [5 empty] | N | 2016-05-21 |  | 0 |  |  |  | 2016-05-21 |  |  |  | 2016-06-13 | 0
SERVER | SG | 2016-05-12 | 2016-06-27 | 2016W26 | 5162_26408 | 5162_26408 | CHG | TI | 86010548 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 28 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5179_26455 | 5179_26455 | CHS | VK | 86012076 | 2 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5179_26455 | 5179_26455 | CHS | VK | 86012076 | 2 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5179_26455 | 5179_26455 | CHS | VK | 86012076 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5179_26456 | 5179_26456 | CHS | VK | 86012082 | 4 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008943 | 4 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5179_26456 | 5179_26456 | CHS | VK | 86012082 | 4 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008944 | 4 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5179_26456 | 5179_26456 | CHS | VK | 86012082 | 4 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5180_26457 | 5180_26457 | TUL | OT | 86012109 | 2 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5180_26457 | 5180_26457 | TUL | OT | 86012109 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5180_26457 | 5180_26457 | TUL | OT | 86012109 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5180_26458 | 5180_26458 | TUL | OT | 86012108 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5180_26458 | 5180_26458 | TUL | OT | 86012108 | 1 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5180_26458 | 5180_26458 | TUL | OT | 86012108 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5181_26459 | 5181_26459 | CHS | UA | 86012109 | 5 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5181_26459 | 5181_26459 | CHS | UA | 86012109 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 10 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5181_26459 | 5181_26459 | CHS | UA | 86012109 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5181_26460 | 5181_26460 | CHS | UA | 86012108 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5181_26460 | 5181_26460 | CHS | UA | 86012108 | 2 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5181_26460 | 5181_26460 | CHS | UA | 86012108 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5184_26464 | 5184_26464 | ATL | YB | 86012079 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86011349 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5184_26464 | 5184_26464 | ATL | YB | 86012079 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86011356 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5184_26464 | 5184_26464 | ATL | YB | 86012079 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5184_26631 | 5184_26631 | ATL | YB | 86012074 | 2 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86011349 | 2 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5184_26631 | 5184_26631 | ATL | YB | 86012074 | 2 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86011356 | 2 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5184_26631 | 5184_26631 | ATL | YB | 86012074 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 28 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5185_26465 | 5185_26465 | MRN | QT | 86012110 | 3 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5185_26465 | 5185_26465 | MRN | QT | 86012110 | 3 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5185_26465 | 5185_26465 | MRN | QT | 86012110 | 3 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5186_26467 | 5186_26467 | CBF | IV | 86012109 | 2 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5186_26467 | 5186_26467 | CBF | IV | 86012109 | 2 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 8 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5186_26467 | 5186_26467 | CBF | IV | 86012109 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 232 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26488 | 5197_26488 | CHS | VS | 86012108 | 7 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 14 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26488 | 5197_26488 | CHS | VS | 86012108 | 7 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 28 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26488 | 5197_26488 | CHS | VS | 86012108 | 7 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 812 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26489 | 5197_26489 | CHS | VS | 86012767 | 3 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 6 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26489 | 5197_26489 | CHS | VS | 86012767 | 3 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 12 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26489 | 5197_26489 | CHS | VS | 86012767 | 3 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 348 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26679 | 5197_26679 | CHS | VS | 86012069 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26679 | 5197_26679 | CHS | VS | 86012069 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5197_26679 | 5197_26679 | CHS | VS | 86012069 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
FABRIC | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5199_26512 | C1530 | CBF | IR | 86005444 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 14 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
FABRIC | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5199_26512 | C1530 | CBF | IR | 86005444 | 2 | 2016-06-20 | 2016-06-20 | RACK-ASM | NRACK.IKEAS | 86005420 | 2 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-13 | 0
FABRIC | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5200_26513 | C1532 | TUL | OL | 86005444 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 14 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
FABRIC | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5200_26513 | C1532 | TUL | OL | 86005444 | 2 | 2016-06-20 | 2016-06-20 | RACK-ASM | NRACK.IKEAS | 86005420 | 2 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5204_26559 | 5204_26559 | DLS | PH | 86012109 | 6 | 2016-05-23 | 2016-05-30 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 12 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-06-04 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5204_26559 | 5204_26559 | DLS | PH | 86012109 | 6 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5204_26559 | 5204_26559 | DLS | PH | 86012109 | 6 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 696 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26644 | 5249_26644 | MRN | QN | 86012082 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008943 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26644 | 5249_26644 | MRN | QN | 86012082 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008944 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26644 | 5249_26644 | MRN | QN | 86012082 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 90 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26645 | 5249_26645 | MRN | QN | 86009264 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008943 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26645 | 5249_26645 | MRN | QN | 86009264 | 5 | 2016-06-06 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008944 | 5 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26645 | 5249_26645 | MRN | QN | 86009264 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 90 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26671 | 5249_26671 | MRN | QN | 86012069 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26671 | 5249_26671 | MRN | QN | 86012069 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26671 | 5249_26671 | MRN | QN | 86012069 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26672 | 5249_26672 | MRN | QN | 86012767 | 5 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 10 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26672 | 5249_26672 | MRN | QN | 86012767 | 5 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26672 | 5249_26672 | MRN | QN | 86012767 | 5 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26673 | 5249_26673 | MRN | QN | 86012109 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26673 | 5249_26673 | MRN | QN | 86012109 | 1 | 2016-06-06 | 2016-06-06 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5249_26673 | 5249_26673 | MRN | QN | 86012109 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
FABRIC | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5330_26879 | C1531 | CBF | IS | 86009512 | 4 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-13 | 0
FABRIC | AT | 2016-05-12 | 2016-06-27 | 2016W26 | 5330_26879 | C1531 | CBF | IS | 86009512 | 4 | 2016-06-20 | 2016-06-20 | RACK-ASM | NRACK.IKEAS | 86009511 | 4 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-13 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24946 | 4838_24946 | CBF | JH | 86008828 | 6 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24946 | 4838_24946 | CBF | JH | 86008828 | 6 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 12 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24946 | 4838_24946 | CBF | JH | 86008828 | 6 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 696 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24947 | 4838_24947 | CBF | JH | 86012771 | 15 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 60 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24947 | 4838_24947 | CBF | JH | 86012771 | 15 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 30 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24947 | 4838_24947 | CBF | JH | 86012771 | 15 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 1740 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24948 | 4838_24948 | CBF | JH | 86010549 | 7 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86004101 | 7 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24948 | 4838_24948 | CBF | JH | 86010549 | 7 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86004102 | 7 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4838_24948 | 4838_24948 | CBF | JH | 86010549 | 7 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 84 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4985_25656 | 4985_25656 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86009246 | 9 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4985_25656 | 4985_25656 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86009254 | 9 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4985_25656 | 4985_25656 | CHS | VY | 86012174 | 9 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4985_25658 | 4985_25658 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86009246 | 9 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4985_25658 | 4985_25658 | CHS | VY | 86012174 | 9 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86009254 | 9 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 4985_25658 | 4985_25658 | CHS | VY | 86012174 | 9 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 144 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5002_25763 | 5002_25763 | LPP | LO | 86012212 | 34 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86012207 | 34 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5002_25763 | 5002_25763 | LPP | LO | 86012212 | 34 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86012208 | 34 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5002_25763 | 5002_25763 | LPP | LO | 86012212 | 34 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 340 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5103_26194 | 5103_26194 | CBF | JG | 86006782 | 55 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86006859 | 55 | 0 | 0 |  |  |  |  | PVT | Y | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5103_26194 | 5103_26194 | CBF | JG | 86006782 | 55 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008326 | 55 | 0 | 0 |  |  |  |  | PVT | Y | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5103_26194 | 5103_26194 | CBF | JG | 86006782 | 55 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 770 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5114_26230 | 5114_26230 | CHG | TK | 86012212 | 12 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86012208 | 12 | 1 | 0 | At-risk | NPI | FA required | NPI//FA required |  | N | 2016-05-14 | Fa rack just completed Can't kit more until Fa passes test | 0 |  |  | 2016-05-09 | 2016-05-14 |  |  |  | 2016-06-20 | 0
SERVER | SG | 2016-05-12 | 2016-07-04 | 2016W27 | 5114_26230 | 5114_26230 | CHG | TK | 86012212 | 12 | 2016-05-23 | 2016-05-23 | RACK-ASM | MRACK.IKEA3 | 86012207 | 12 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-05-28 |  |  |  | 2016-06-20 | 0
SERVER | SG | 2016-05-12 | 2016-07-04 | 2016W27 | 5114_26230 | 5114_26230 | CHG | TK | 86012212 | 12 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26364 | 5123_26364 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26364 | 5123_26364 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26364 | 5123_26364 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26365 | 5123_26365 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26365 | 5123_26365 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26365 | 5123_26365 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26366 | 5123_26366 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26366 | 5123_26366 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26366 | 5123_26366 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26367 | 5123_26367 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26367 | 5123_26367 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26367 | 5123_26367 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26368 | 5123_26368 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26368 | 5123_26368 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26368 | 5123_26368 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26369 | 5123_26369 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26369 | 5123_26369 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26369 | 5123_26369 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26370 | 5123_26370 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26370 | 5123_26370 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26370 | 5123_26370 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26371 | 5123_26371 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26371 | 5123_26371 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26371 | 5123_26371 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26372 | 5123_26372 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26372 | 5123_26372 | DUB | DG | 86009264 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5123_26372 | 5123_26372 | DUB | DG | 86009264 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5150_26373 | 5150_26373 | GRQ | ED | 86012081 | 19 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 19 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5150_26373 | 5150_26373 | GRQ | ED | 86012081 | 19 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 19 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5150_26373 | 5150_26373 | GRQ | ED | 86012081 | 19 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 228 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26674 | 5151_26674 | MRN | QB | 86012067 | 5 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 5 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26674 | 5151_26674 | MRN | QB | 86012067 | 5 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 5 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26674 | 5151_26674 | MRN | QB | 86012067 | 5 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 60 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26675 | 5151_26675 | MRN | QB | 86012070 | 10 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 10 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26675 | 5151_26675 | MRN | QB | 86012070 | 10 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 10 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26675 | 5151_26675 | MRN | QB | 86012070 | 10 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26676 | 5151_26676 | MRN | QB | 86012069 | 4 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 4 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26676 | 5151_26676 | MRN | QB | 86012069 | 4 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 4 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5151_26676 | 5151_26676 | MRN | QB | 86012069 | 4 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26558 | 5204_26558 | DLS | PH | 86012212 | 4 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012207 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26558 | 5204_26558 | DLS | PH | 86012212 | 4 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.IKEA3 | 86012208 | 4 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26558 | 5204_26558 | DLS | PH | 86012212 | 4 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 40 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26560 | 5204_26560 | DLS | PH | 86012110 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26560 | 5204_26560 | DLS | PH | 86012110 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26560 | 5204_26560 | DLS | PH | 86012110 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26561 | 5204_26561 | DLS | PH | 86012108 | 1 | 2016-05-30 | 2016-06-06 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-06-04 |  | 0 |  |  |  | 2016-06-11 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26561 | 5204_26561 | DLS | PH | 86012108 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5204_26561 | 5204_26561 | DLS | PH | 86012108 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5226_26591 | 5226_26591 | TUL | OM | 86012076 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5226_26591 | 5226_26591 | TUL | OM | 86012076 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5226_26591 | 5226_26591 | TUL | OM | 86012076 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5226_26592 | 5226_26592 | TUL | OM | 86012082 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5226_26592 | 5226_26592 | TUL | OM | 86012082 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5226_26592 | 5226_26592 | TUL | OM | 86012082 | 2 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5228_26594 | 5228_26594 | TUL | OU | 86012212 | 4 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86012207 | 4 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5228_26594 | 5228_26594 | TUL | OU | 86012212 | 4 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86012208 | 4 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5228_26594 | 5228_26594 | TUL | OU | 86012212 | 4 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 40 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5230_26598 | 5230_26598 | LPP | LE | 86012110 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5230_26598 | 5230_26598 | LPP | LE | 86012110 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5230_26598 | 5230_26598 | LPP | LE | 86012110 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5241_26628 | 5241_26628 | CBF | IQ | 86012077 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5241_26628 | 5241_26628 | CBF | IQ | 86012077 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5241_26628 | 5241_26628 | CBF | IQ | 86012077 | 2 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5249_26648 | 5249_26648 | MRN | QN | 86010447 | 3 | 2016-06-06 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86009168 | 3 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5249_26648 | 5249_26648 | MRN | QN | 86010447 | 3 | 2016-06-06 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86009169 | 3 | 0 | 0 | [5 empty] | N | 2016-06-11 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5249_26648 | 5249_26648 | MRN | QN | 86010447 | 3 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5263_26680 | 5263_26680 | ATL | YB | 86012080 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86011472 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5263_26680 | 5263_26680 | ATL | YB | 86012080 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5263_26681 | 5263_26681 | ATL | YB | 86012068 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5263_26681 | 5263_26681 | ATL | YB | 86012068 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5263_26681 | 5263_26681 | ATL | YB | 86012068 | 2 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5264_26682 | 5264_26682 | CHS | VW | 86012071 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5264_26682 | 5264_26682 | CHS | VW | 86012071 | 1 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5264_26682 | 5264_26682 | CHS | VW | 86012071 | 1 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5264_26683 | 5264_26683 | CHS | VW | 86012109 | 6 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5264_26683 | 5264_26683 | CHS | VW | 86012109 | 6 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 12 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5264_26683 | 5264_26683 | CHS | VW | 86012109 | 6 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 696 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5266_26686 | 5266_26686 | CHS | VO | 86009746 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5266_26686 | 5266_26686 | CHS | VO | 86009746 | 2 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5266_26686 | 5266_26686 | CHS | VO | 86009746 | 2 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5288_26764 | 5288_26764 | MRN | QV | 86012081 | 19 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008383 | 19 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5288_26764 | 5288_26764 | MRN | QV | 86012081 | 19 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.IKEA3 | 86008385 | 19 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | AT | 2016-05-12 | 2016-07-04 | 2016W27 | 5288_26764 | 5288_26764 | MRN | QV | 86012081 | 19 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | ANTARES | 45000039-05 | 228 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5425_27131 | 5425_27131 | LPP | LG | 86012111 | 10 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | PACK | 07017435 | 40 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5425_27131 | 5425_27131 | LPP | LG | 86012111 | 10 | 2016-06-13 | 2016-06-13 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 20 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-20 | 0
SERVER | NL | 2016-05-12 | 2016-07-04 | 2016W27 | 5425_27131 | 5425_27131 | LPP | LG | 86012111 | 10 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07000733 | 1160 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-20 | 0
FABRIC | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 3992_19908 | C1180 | TUL | NF | 86009418 | 4 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 28 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 3992_19908 | C1180 | TUL | NF | 86009418 | 4 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEAS | 86009419 | 4 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-06-27 | 0
FABRIC | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 3992_19908 | C1180 | TUL | NF | 86011012 | 24 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 3992_19908 | C1180 | TUL | NF | 86011012 | 24 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEA3S | 86010988 | 24 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4020_23698 | 4020_23698 | GRQ | EH | 86011028 | 3 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86010807 | 6 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4020_23698 | 4020_23698 | GRQ | EH | 86011028 | 3 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4863_25071 | C1488 | LPP | LU | 86005444 | 5 | 2016-06-13 | 2016-06-13 | RACK-ASM | NRACK.IKEAS | 86005420 | 5 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-27 | 0
FABRIC | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4863_25071 | C1488 | LPP | LU | 86005444 | 5 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 35 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4863_25071 | C1488 | LPP | LU | 86010778 | 8 | 2016-06-20 | 2016-06-27 | RACK-ASM | NRACK.IKEA3S | 86010993 | 8 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4863_25071 | C1488 | LPP | LU | 86010778 | 8 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4863_25071 | C1488 | LPP | LU | 86011012 | 40 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
FABRIC | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 4863_25071 | C1488 | LPP | LU | 86011012 | 40 | 2016-06-27 | 2016-07-04 | RACK-ASM | NRACK.IKEA3S | 86010988 | 40 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5013_25817 | 5013_25817 | GRQ | ED | 86012108 | 5 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5013_25817 | 5013_25817 | GRQ | ED | 86012108 | 5 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 10 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5013_25817 | 5013_25817 | GRQ | ED | 86012108 | 5 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5013_25818 | 5013_25818 | GRQ | ED | 86012212 | 4 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012207 | 4 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5013_25818 | 5013_25818 | GRQ | ED | 86012212 | 4 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012208 | 4 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5013_25818 | 5013_25818 | GRQ | ED | 86012212 | 4 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 40 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5099_26186 | 5099_26186 | TUL | OZ | 86012209 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012210 | 1 | 0 | 0 |  |  |  |  | PVT | Y | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5099_26186 | 5099_26186 | TUL | OZ | 86012209 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012211 | 1 | 0 | 0 |  |  |  |  | PVT | Y | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5099_26186 | 5099_26186 | TUL | OZ | 86012209 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 20 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5099_26188 | 5099_26188 | TUL | OZ | 86013007 | 6 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012268 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5099_26188 | 5099_26188 | TUL | OZ | 86013007 | 6 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012269 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5099_26188 | 5099_26188 | TUL | OZ | 86013007 | 6 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5100_26189 | 5100_26189 | GRQ | EF | 86012109 | 5 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 20 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5100_26189 | 5100_26189 | GRQ | EF | 86012109 | 5 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 10 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5100_26189 | 5100_26189 | GRQ | EF | 86012109 | 5 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 580 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5100_26190 | 5100_26190 | GRQ | EF | 86012212 | 5 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012207 | 5 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5100_26190 | 5100_26190 | GRQ | EF | 86012212 | 5 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012208 | 5 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5100_26190 | 5100_26190 | GRQ | EF | 86012212 | 5 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 50 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5116_26238 | 5116_26238 | SCL | CB | 86012092 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008703 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 15:36 |  | 1 | DONE | MORSC3889524587 | 2016-04-27 | 2016-05-14 | 2016-04-27 |  | 2016-06-28 | 2016-06-27 | 1
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5116_26238 | 5116_26238 | SCL | CB | 86012092 | 1 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008704 | 1 | 1 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 14:27 |  | 1 | DONE | MORSC3889524587 | 2016-04-27 | 2016-05-14 | 2016-04-27 |  | 2016-06-28 | 2016-06-27 | 1
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5116_26238 | 5116_26238 | SCL | CB | 86012092 | 1 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5116_26239 | 5116_26239 | SCL | CB | 86012096 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008703 | 2 | 1 | 1 | MIM-Shipped |  |  |  |  | N | 2016-04-27 11:00 |  | 1 |  | MORSC3889631046 | 2016-05-03 | 2016-05-14 |  |  | 2016-06-28 | 2016-06-27 | 1
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5116_26239 | 5116_26239 | SCL | CB | 86012096 | 2 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86008704 | 2 | 2 | 0 | MIM-Shipped |  |  |  |  | N | 2016-04-26 10:42 |  | 2 | DONE | MORSC3889536996 | 2016-04-27 | 2016-05-14 | 2016-04-27 |  | 2016-06-28 | 2016-06-27 | 1
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5116_26239 | 5116_26239 | SCL | CB | 86012096 | 2 | 2016-06-13 | 2016-06-13 | BATTERY-BOX | ANTARES | 45000039-05 | 28 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-18 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5163_26409 | 5163_26409 | GRQ | ED | 86010548 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5163_26409 | 5163_26409 | GRQ | ED | 86010548 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5163_26409 | 5163_26409 | GRQ | ED | 86010548 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5183_26462 | 5183_26462 | BRU | WM | 86012082 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5183_26462 | 5183_26462 | BRU | WM | 86012082 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5183_26462 | 5183_26462 | BRU | WM | 86012082 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5183_26463 | 5183_26463 | BRU | WM | 86012075 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5183_26463 | 5183_26463 | BRU | WM | 86012075 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5183_26463 | 5183_26463 | BRU | WM | 86012075 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26604 | 5233_26604 | GRQ | ED | 86012109 | 4 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26604 | 5233_26604 | GRQ | ED | 86012109 | 4 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 8 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26604 | 5233_26604 | GRQ | ED | 86012109 | 4 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26605 | 5233_26605 | GRQ | ED | 86012108 | 4 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 16 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26605 | 5233_26605 | GRQ | ED | 86012108 | 4 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 8 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26605 | 5233_26605 | GRQ | ED | 86012108 | 4 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 464 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26606 | 5233_26606 | GRQ | ED | 86012111 | 9 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 36 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26606 | 5233_26606 | GRQ | ED | 86012111 | 9 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 18 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26606 | 5233_26606 | GRQ | ED | 86012111 | 9 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 1044 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26639 | 5233_26639 | GRQ | ED | 86012068 | 2 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26639 | 5233_26639 | GRQ | ED | 86012068 | 2 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | NL | 2016-05-12 | 2016-07-11 | 2016W28 | 5233_26639 | 5233_26639 | GRQ | ED | 86012068 | 2 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5263_26694 | 5263_26694 | ATL | YB | 86012074 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86011349 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5263_26694 | 5263_26694 | ATL | YB | 86012074 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86011356 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5263_26694 | 5263_26694 | ATL | YB | 86012074 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5263_26695 | 5263_26695 | ATL | YB | 86012079 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86011349 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5263_26695 | 5263_26695 | ATL | YB | 86012079 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86011356 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5263_26695 | 5263_26695 | ATL | YB | 86012079 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5266_26685 | 5266_26685 | CHS | VO | 86012109 | 12 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 48 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5266_26685 | 5266_26685 | CHS | VO | 86012109 | 12 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 24 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5266_26685 | 5266_26685 | CHS | VO | 86012109 | 12 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 1392 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5279_26712 | 5279_26712 | CBF | IT | 86012082 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5279_26712 | 5279_26712 | CBF | IT | 86012082 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5279_26712 | 5279_26712 | CBF | IT | 86012082 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5279_26713 | 5279_26713 | CBF | IT | 86012076 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5279_26713 | 5279_26713 | CBF | IT | 86012076 | 1 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5279_26713 | 5279_26713 | CBF | IT | 86012076 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5283_26738 | 5283_26738 | CHS | VO | 86012082 | 1 | 2016-06-13 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5283_26738 | 5283_26738 | CHS | VO | 86012082 | 1 | 2016-06-13 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5283_26738 | 5283_26738 | CHS | VO | 86012082 | 1 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5283_26739 | 5283_26739 | CHS | VO | 86012212 | 2 | 2016-06-13 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012207 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5283_26739 | 5283_26739 | CHS | VO | 86012212 | 2 | 2016-06-13 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86012208 | 2 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5283_26739 | 5283_26739 | CHS | VO | 86012212 | 2 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 20 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5288_26765 | 5288_26765 | MRN | QV | 86012068 | 2 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008383 | 2 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5288_26765 | 5288_26765 | MRN | QV | 86012068 | 2 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86008385 | 2 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5288_26765 | 5288_26765 | MRN | QV | 86012068 | 2 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5288_26766 | 5288_26766 | MRN | QV | 86012109 | 20 | 2016-06-13 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 40 | 0 | 0 | [5 empty] | N | 2016-06-18 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5288_26766 | 5288_26766 | MRN | QV | 86012109 | 20 | 2016-06-20 | 2016-06-20 | BATTERY-BOX | PACK | 07017435 | 80 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5288_26766 | 5288_26766 | MRN | QV | 86012109 | 20 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07000733 | 2320 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5332_26882 | 5332_26882 | TUL | OZ | 86010448 | 5 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86009168 | 5 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5332_26882 | 5332_26882 | TUL | OZ | 86010448 | 5 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86009169 | 5 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-11 | 2016W28 | 5332_26882 | 5332_26882 | TUL | OZ | 86010448 | 5 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | ANTARES | 45000039-05 | 70 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-06-27 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3674_18450 | 3674_18450 | CBF | JO | 86011028 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86010807 | 12 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3674_18450 | 3674_18450 | CBF | JO | 86011028 | 6 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 108 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3676_18451 | 3676_18451 | CBF | JP | 86011028 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86010807 | 12 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3676_18451 | 3676_18451 | CBF | JP | 86011028 | 6 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 108 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3844_22248 | 3844_22248 | TUL | NB | 86013027 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86013029 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3844_22248 | 3844_22248 | TUL | NB | 86013027 | 6 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3846_22247 | 3846_22247 | TUL | ND | 86013027 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86013029 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3846_22247 | 3846_22247 | TUL | ND | 86013027 | 6 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 120 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3992_22256 | 3992_22256 | TUL | NF | 86010392 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86010332 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3992_22256 | 3992_22256 | TUL | NF | 86010392 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86010333 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3992_22256 | 3992_22256 | TUL | NF | 86010392 | 6 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
FABRIC | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_19909 | C1179 | TUL | NG | 86009418 | 8 | 2016-06-27 | 2016-07-11 | RACK-ASM | NRACK.IKEAS | 86009419 | 8 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-04 | 0
FABRIC | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_19909 | C1179 | TUL | NG | 86009418 | 8 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 56 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
FABRIC | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_19909 | C1179 | TUL | NG | 86010778 | 24 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
FABRIC | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_19909 | C1179 | TUL | NG | 86010778 | 24 | 2016-07-11 | 2016-07-11 | RACK-ASM | NRACK.IKEA3S | 86010993 | 24 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_22257 | 3993_22257 | TUL | NG | 86010392 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86010332 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_22257 | 3993_22257 | TUL | NG | 86010392 | 6 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86010333 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 3993_22257 | 3993_22257 | TUL | NG | 86010392 | 6 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 4579_24388 | 4579_24388 | DUB | DG | 86009489 | 3 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86009168 | 3 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 4579_24388 | 4579_24388 | DUB | DG | 86009489 | 3 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86009169 | 3 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 4579_24388 | 4579_24388 | DUB | DG | 86009489 | 3 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 4707_24350 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012105 | 1 | 0 | 0 |  |  |  |  | DVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 4707_24350 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012106 | 1 | 0 | 0 |  |  |  |  | DVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 4707_24350 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012107 | 1 | 0 | 0 |  |  |  |  | DVT | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 4707_24350 | NPI0232 | CBF | JK | 86012104 | 1 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 25 | 0 | 0 | Pull-from-Stock |  |  |  | DVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5015_25830 | 5015_25830 | CBF | JN | 86012407 | 4 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012447 | 4 | 0 | 0 |  |  |  |  | OTHER | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5015_25830 | 5015_25830 | CBF | JN | 86012407 | 4 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012528 | 4 | 0 | 0 |  |  |  |  | OTHER | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5015_25830 | 5015_25830 | CBF | JN | 86012407 | 4 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 80 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5015_25833 | 5015_25833 | CBF | JN | 86012907 | 8 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012250 | 8 | 0 | 0 |  |  |  |  | OTHER | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5015_25833 | 5015_25833 | CBF | JN | 86012907 | 8 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012251 | 8 | 0 | 0 |  |  |  |  | OTHER | Y | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5015_25833 | 5015_25833 | CBF | JN | 86012907 | 8 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  | OTHER | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5131_26290 | 5131_26290 | TUL | OX | 86012212 | 26 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012207 | 26 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5131_26290 | 5131_26290 | TUL | OX | 86012212 | 26 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86012208 | 26 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5131_26290 | 5131_26290 | TUL | OX | 86012212 | 26 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 260 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5291_26774 | 5291_26774 | ATL | YV | 86012074 | 4 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86011349 | 4 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5291_26774 | 5291_26774 | ATL | YV | 86012074 | 4 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86011356 | 4 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5291_26774 | 5291_26774 | ATL | YV | 86012074 | 4 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 56 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07001792 | 2 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07004272 | 2 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07004276 | 2 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07004328 | 32 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07007365 | 2 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07014320 | 32 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07018006 | 4 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07048407 | 2 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 901223 | 32 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 901225 | 32 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 901289 | 32 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26780 | 5294_26780 | ATL | AC | 86012689 | 2 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3S | 86008579 | 2 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07001792 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07004272 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07004276 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07004328 | 192 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07007365 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07014320 | 192 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07018006 | 24 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 07048407 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 901223 | 192 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 901225 | 192 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-04 | 2016-07-04 | RACK-ASM | HWKIT | 901289 | 192 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5294_26783 | 5294_26783 | ATL | AC | 86012689 | 12 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3S | 86008579 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5331_26881 | 5331_26881 | LPP | LU | 86010448 | 5 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86009168 | 5 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5331_26881 | 5331_26881 | LPP | LU | 86010448 | 5 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86009169 | 5 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5331_26881 | 5331_26881 | LPP | LU | 86010448 | 5 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 70 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5333_26883 | 5333_26883 | CBF | JN | 86010448 | 5 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86009168 | 5 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5333_26883 | 5333_26883 | CBF | JN | 86010448 | 5 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86009169 | 5 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5333_26883 | 5333_26883 | CBF | JN | 86010448 | 5 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 70 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26904 | 5349_26904 | ATL | YB | 86012080 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86011472 | 2 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26904 | 5349_26904 | ATL | YB | 86012080 | 1 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26905 | 5349_26905 | ATL | YB | 86012069 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86008383 | 1 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26905 | 5349_26905 | ATL | YB | 86012069 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86008385 | 1 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26905 | 5349_26905 | ATL | YB | 86012069 | 1 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26906 | 5349_26906 | ATL | YB | 86012080 | 1 | 2016-06-27 | 2016-06-27 | RACK-ASM | MRACK.IKEA3 | 86011472 | 2 | 0 | 0 | [5 empty] | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5349_26906 | 5349_26906 | ATL | YB | 86012080 | 1 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5424_27130 | 5424_27130 | DLS | PF | 86012111 | 13 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 26 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5424_27130 | 5424_27130 | DLS | PF | 86012111 | 13 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07017435 | 52 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | AT | 2016-05-12 | 2016-07-18 | 2016W29 | 5424_27130 | 5424_27130 | DLS | PF | 86012111 | 13 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | PACK | 07000733 | 1508 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5426_27132 | 5426_27132 | LPP | LE | 86012111 | 10 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 20 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5426_27132 | 5426_27132 | LPP | LE | 86012111 | 10 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07017435 | 40 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5426_27132 | 5426_27132 | LPP | LE | 86012111 | 10 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | PACK | 07000733 | 1160 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5427_27133 | 5427_27133 | LPP | LO | 86012111 | 16 | 2016-06-20 | 2016-06-20 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 32 | 0 | 0 | [5 empty] | N | 2016-06-25 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5427_27133 | 5427_27133 | LPP | LO | 86012111 | 16 | 2016-06-27 | 2016-06-27 | BATTERY-BOX | PACK | 07017435 | 64 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-02 |  | 0 |  |  |  | 2016-07-02 |  |  |  | 2016-07-04 | 0
SERVER | NL | 2016-05-12 | 2016-07-18 | 2016W29 | 5427_27133 | 5427_27133 | LPP | LO | 86012111 | 16 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | PACK | 07000733 | 1856 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-04 | 0
FABRIC | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5127_26471 | 5127_26471 | IAD | XG | 86010317 | 1 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEA3S | 86010148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
FABRIC | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5127_26472 | 5127_26472 | IAD | XG | 86010007 | 4 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEAS | 86010008 | 4 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
FABRIC | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5128_26474 | 5128_26474 | IAD | XH | 86010317 | 1 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEA3S | 86010148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
FABRIC | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5128_26475 | 5128_26475 | IAD | XH | 86010007 | 4 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEAS | 86010008 | 4 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
FABRIC | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5129_26484 | 5129_26484 | IAD | XI | 86010317 | 1 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEA3S | 86010148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
FABRIC | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5129_26485 | 5129_26485 | IAD | XI | 86010007 | 4 | 2016-07-04 | 2016-07-04 | RACK-ASM | NRACK.IKEAS | 86010008 | 4 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5350_26907 | 5350_26907 | ATL | YB | 86012080 | 1 | 2016-07-04 | 2016-07-04 | RACK-ASM | MRACK.IKEA3 | 86011472 | 2 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5350_26907 | 5350_26907 | ATL | YB | 86012080 | 1 | 2016-07-11 | 2016-07-11 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5350_27035 | 5350_27035 | ATL | YB | 86012080 | 1 | 2016-07-04 | 2016-07-04 | RACK-ASM | MRACK.IKEA3 | 86011472 | 2 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5350_27035 | 5350_27035 | ATL | YB | 86012080 | 1 | 2016-07-11 | 2016-07-11 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5357_26920 | 5357_26920 | CHS | VU | 86012110 | 1 | 2016-07-04 | 2016-07-04 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5357_26920 | 5357_26920 | CHS | VU | 86012110 | 1 | 2016-07-04 | 2016-07-04 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-07-11 | 0
SERVER | AT | 2016-05-12 | 2016-07-25 | 2016W30 | 5357_26920 | 5357_26920 | CHS | VU | 86012110 | 1 | 2016-07-11 | 2016-07-11 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-11 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 4753_24612 | 4753_24612 | LPP | LI | 86010612 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 4753_24612 | 4753_24612 | LPP | LI | 86010612 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 4753_24612 | 4753_24612 | LPP | LI | 86010612 | 1 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 4753_24616 | 4753_24616 | LPP | LI | 86008828 | 1 | 2016-07-11 | 2016-07-11 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 4753_24616 | 4753_24616 | LPP | LI | 86008828 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 4753_24616 | 4753_24616 | LPP | LI | 86008828 | 1 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | SG | 2016-05-12 | 2016-08-01 | 2016W31 | 4769_24672 | 4769_24672 | CHG | TG | 86012188 | 45 | 2016-05-23 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86007600 | 45 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-07-18 | 0
SERVER | SG | 2016-05-12 | 2016-08-01 | 2016W31 | 4769_24672 | 4769_24672 | CHG | TG | 86012188 | 45 | 2016-05-23 | 2016-06-20 | RACK-ASM | MRACK.IKEA3 | 86007619 | 45 | 0 | 0 | [5 empty] | N | 2016-05-28 |  | 0 |  |  |  | 2016-06-25 |  |  |  | 2016-07-18 | 0
SERVER | SG | 2016-05-12 | 2016-08-01 | 2016W31 | 4769_24672 | 4769_24672 | CHG | TG | 86012188 | 45 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 540 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 4990_25676 | 4990_25676 | MRN | QM | 86010548 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 4990_25676 | 4990_25676 | MRN | QM | 86010548 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 4990_25676 | 4990_25676 | MRN | QM | 86010548 | 1 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5127_26473 | 5127_26473 | IAD | XG | 86011669 | 6 | 2016-07-11 | 2016-07-11 | RACK-ASM | NRACK.IKEA3S | 86009609 | 6 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5127_26473 | 5127_26473 | IAD | XG | 86011669 | 6 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5128_26476 | 5128_26476 | IAD | XH | 86011669 | 6 | 2016-07-11 | 2016-07-11 | RACK-ASM | NRACK.IKEA3S | 86009609 | 6 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5128_26476 | 5128_26476 | IAD | XH | 86011669 | 6 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5129_26487 | 5129_26487 | IAD | XI | 86011669 | 6 | 2016-07-11 | 2016-07-11 | RACK-ASM | NRACK.IKEA3S | 86009609 | 6 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5129_26487 | 5129_26487 | IAD | XI | 86011669 | 6 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 5164_26417 | 5164_26417 | LPP | LE | 86010548 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 5164_26417 | 5164_26417 | LPP | LE | 86010548 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | NL | 2016-05-12 | 2016-08-01 | 2016W31 | 5164_26417 | 5164_26417 | LPP | LE | 86010548 | 1 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5165_26420 | 5165_26420 | TUL | OO | 86010548 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5165_26420 | 5165_26420 | TUL | OO | 86010548 | 1 | 2016-07-11 | 2016-07-11 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-16 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-01 | 2016W31 | 5165_26420 | 5165_26420 | TUL | OO | 86010548 | 1 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-18 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 3630_21744 | 3630_21744 | ATL | YR | 86008540 | 6 | 2016-07-11 | 2016-07-18 | RACK-ASM | MRACK.IKEA2 | 86008483 | 6 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 3630_21744 | 3630_21744 | ATL | YR | 86008540 | 6 | 2016-07-11 | 2016-07-18 | RACK-ASM | MRACK.IKEA2 | 86008484 | 6 | 0 | 0 | [5 empty] | N | 2016-07-16 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 3630_21744 | 3630_21744 | ATL | YR | 86008540 | 6 | 2016-07-25 | 2016-07-25 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 120 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07001792 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004272 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004276 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004328 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004980 | 210 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07007365 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07014320 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07018006 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07036764 | 120 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048077 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048132 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048407 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07052887 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07054109 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086015 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086018 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07090295 | 210 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07091558 | 180 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07108530 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07114616 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07120200 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07124653 | 300 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07126550 | 1080 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 12000325-01 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000189-01 | 270 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000592-01 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000616-01 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000808-02 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000173-01 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000307-05 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000495-13 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000497-03 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000535-02 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000548-05 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42001369-01 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901223 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901225 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901289 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_24439 | 4722_24439 | ATL | BA | 86012328 | 30 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-B | 86006500 | 30 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07001792 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004272 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004276 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004328 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004980 | 210 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07007365 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07014320 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07018006 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07036764 | 120 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048077 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048132 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048407 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07052887 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07054109 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086015 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086018 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07090295 | 210 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07091558 | 180 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07108530 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07114616 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07120200 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07124653 | 300 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07126550 | 1080 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 12000325-01 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000189-01 | 270 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000592-01 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000616-01 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000808-02 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000173-01 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000307-05 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000495-13 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000497-03 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000535-02 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000548-05 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42001369-01 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901223 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901225 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901289 | 480 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4722_26873 | 4722_26873 | ATL | BA | 86012328 | 30 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-B | 86006500 | 30 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4723_24443 | 4723_24443 | ATL | AC | 86012567 | 12 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 12 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 4723_26877 | 4723_26877 | ATL | AC | 86012567 | 28 | 2016-08-01 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 28 | 0 | 0 | [5 empty] | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07001792 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004272 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004276 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004328 | 160 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004980 | 70 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07007365 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07014320 | 160 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07018006 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07036764 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048077 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048132 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048407 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07052887 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07054109 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086015 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086018 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07090295 | 70 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07091558 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07108530 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07114616 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07120200 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07124653 | 100 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07126550 | 360 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 12000325-01 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000189-01 | 90 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000592-01 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000616-01 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000808-02 | 30 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000173-01 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000307-05 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000495-13 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000497-03 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000535-02 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000548-05 | 10 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42001369-01 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901223 | 160 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901225 | 160 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901289 | 160 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_24446 | 4724_24446 | AMS | BA | 86012328 | 10 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-B | 86006500 | 10 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07001792 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004272 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004276 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004328 | 320 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07004980 | 140 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07007365 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07014320 | 320 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07018006 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07036764 | 80 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048077 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048132 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07048407 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07052887 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07054109 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086015 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07086018 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07090295 | 140 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07091558 | 120 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07108530 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07114616 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07120200 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07124653 | 200 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 07126550 | 720 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 12000325-01 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000189-01 | 180 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000592-01 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000616-01 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 16000808-02 | 60 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000173-01 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000307-05 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000495-13 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000497-03 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000535-02 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42000548-05 | 20 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 42001369-01 | 40 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901223 | 320 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901225 | 320 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-07-25 | 2016-07-25 | RACK-ASM | HWKIT | 901289 | 320 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4724_26872 | 4724_26872 | AMS | BA | 86012328 | 20 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-B | 86006500 | 20 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4725_24450 | 4725_24450 | AMS | AC | 86012567 | 4 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 4 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-07-25 | 0
SERVER | NL | 2016-05-12 | 2016-08-08 | 2016W32 | 4725_26874 | 4725_26874 | AMS | AC | 86012567 | 16 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 16 | 0 | 0 | [5 empty] | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5238_26624 | 5238_26624 | CHS | VU | 86004187 | 1 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86004098 | 1 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5238_26624 | 5238_26624 | CHS | VU | 86004187 | 1 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86004099 | 1 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5238_26624 | 5238_26624 | CHS | VU | 86004187 | 1 | 2016-07-25 | 2016-07-25 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26767 | 5289_26767 | CBF | JB | 86012212 | 5 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86012207 | 5 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26767 | 5289_26767 | CBF | JB | 86012212 | 5 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86012208 | 5 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26767 | 5289_26767 | CBF | JB | 86012212 | 5 | 2016-07-25 | 2016-07-25 | BATTERY-BOX | ANTARES | 45000039-05 | 50 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26768 | 5289_26768 | CBF | JB | 86012076 | 2 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86008943 | 2 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26768 | 5289_26768 | CBF | JB | 86012076 | 2 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86008944 | 2 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26768 | 5289_26768 | CBF | JB | 86012076 | 2 | 2016-07-25 | 2016-07-25 | BATTERY-BOX | ANTARES | 45000039-05 | 36 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26769 | 5289_26769 | CBF | JB | 86012082 | 1 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86008943 | 1 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26769 | 5289_26769 | CBF | JB | 86012082 | 1 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.IKEA3 | 86008944 | 1 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26769 | 5289_26769 | CBF | JB | 86012082 | 1 | 2016-07-25 | 2016-07-25 | BATTERY-BOX | ANTARES | 45000039-05 | 18 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26770 | 5289_26770 | CBF | JB | 86012109 | 6 | 2016-07-18 | 2016-07-18 | BATTERY-BOX | PACK | 07017435 | 24 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26770 | 5289_26770 | CBF | JB | 86012109 | 6 | 2016-07-18 | 2016-07-18 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 12 | 0 | 0 | [5 empty] | N | 2016-07-23 |  | 0 |  |  |  | 2016-07-23 |  |  |  | 2016-07-25 | 0
SERVER | AT | 2016-05-12 | 2016-08-08 | 2016W32 | 5289_26770 | 5289_26770 | CBF | JB | 86012109 | 6 | 2016-07-25 | 2016-07-25 | BATTERY-BOX | PACK | 07000733 | 696 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-07-25 | 0
SERVER | SG | 2016-05-12 | 2016-08-15 | 2016W33 | 4769_24671 | 4769_24671 | CHG | TG | 86011089 | 55 | 2016-07-04 | 2016-07-04 | RACK-ASM | MRACK.IKEA3 | 86006078 | 55 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-08-01 | 0
SERVER | SG | 2016-05-12 | 2016-08-15 | 2016W33 | 4769_24671 | 4769_24671 | CHG | TG | 86011089 | 55 | 2016-07-04 | 2016-07-04 | RACK-ASM | MRACK.IKEA3 | 86007379 | 55 | 0 | 0 | [5 empty] | N | 2016-07-09 |  | 0 |  |  |  | 2016-07-09 |  |  |  | 2016-08-01 | 0
SERVER | SG | 2016-05-12 | 2016-08-15 | 2016W33 | 4769_24671 | 4769_24671 | CHG | TG | 86011089 | 55 | 2016-08-01 | 2016-08-01 | BATTERY-BOX | ANTARES | 45000039-05 | 770 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-01 | 0
SERVER | NL | 2016-05-12 | 2016-08-15 | 2016W33 | 5275_26705 | 5275_26705 | BRU | WO | 86010548 | 1 | 2016-07-25 | 2016-07-25 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-08-01 | 0
SERVER | NL | 2016-05-12 | 2016-08-15 | 2016W33 | 5275_26705 | 5275_26705 | BRU | WO | 86010548 | 1 | 2016-07-25 | 2016-07-25 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-08-01 | 0
SERVER | NL | 2016-05-12 | 2016-08-15 | 2016W33 | 5275_26705 | 5275_26705 | BRU | WO | 86010548 | 1 | 2016-08-01 | 2016-08-01 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-01 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4994_25697 | 4994_25697 | CBF | JN | 86011747 | 12 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEA3 | 86011748 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4994_25697 | 4994_25697 | CBF | JN | 86011747 | 12 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEA3 | 86011809 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4994_25697 | 4994_25697 | CBF | JN | 86011747 | 12 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEA3 | 86011810 | 12 | 0 | 0 |  |  |  |  | PVT | Y | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4994_25697 | 4994_25697 | CBF | JN | 86011747 | 12 | 2016-08-08 | 2016-08-08 | BATTERY-BOX | ANTARES | 45000039-05 | 300 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4995_25701 | 4995_25701 | CBF | JK | 86012104 | 1 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEA3 | 86012105 | 1 | 0 | 0 | [5 empty] | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4995_25701 | 4995_25701 | CBF | JK | 86012104 | 1 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEA3 | 86012106 | 1 | 0 | 0 | [5 empty] | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4995_25701 | 4995_25701 | CBF | JK | 86012104 | 1 | 2016-08-01 | 2016-08-01 | RACK-ASM | MRACK.IKEA3 | 86012107 | 1 | 0 | 0 | [5 empty] | N | 2016-08-06 |  | 0 |  |  |  | 2016-08-06 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-22 | 2016W34 | 4995_25701 | 4995_25701 | CBF | JK | 86012104 | 1 | 2016-08-08 | 2016-08-08 | BATTERY-BOX | ANTARES | 45000039-05 | 25 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-08 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 4413_25091 | 4413_25091 | ATL | YM | 86008649 | 3 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 4413_25091 | 4413_25091 | ATL | YM | 86008649 | 3 | 2016-08-15 | 2016-08-15 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-20 |  | 0 |  |  |  | 2016-08-20 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 4414_25092 | 4414_25092 | ATL | YN | 86008649 | 3 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 4414_25092 | 4414_25092 | ATL | YN | 86008649 | 3 | 2016-08-15 | 2016-08-15 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-20 |  | 0 |  |  |  | 2016-08-20 |  |  |  | 2016-08-15 | 0
SERVER | NL | 2016-05-12 | 2016-08-29 | 2016W35 | 4753_24613 | 4753_24613 | LPP | LI | 86010612 | 1 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | NL | 2016-05-12 | 2016-08-29 | 2016W35 | 4753_24613 | 4753_24613 | LPP | LI | 86010612 | 1 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | NL | 2016-05-12 | 2016-08-29 | 2016W35 | 4753_24613 | 4753_24613 | LPP | LI | 86010612 | 1 | 2016-08-15 | 2016-08-15 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-20 |  | 0 |  |  |  | 2016-08-20 |  |  |  | 2016-08-15 | 0
SERVER | NL | 2016-05-12 | 2016-08-29 | 2016W35 | 4753_24617 | 4753_24617 | LPP | LI | 86008828 | 1 | 2016-08-08 | 2016-08-08 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | NL | 2016-05-12 | 2016-08-29 | 2016W35 | 4753_24617 | 4753_24617 | LPP | LI | 86008828 | 1 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.CENTILIUM | 86003208-02 | 2 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | NL | 2016-05-12 | 2016-08-29 | 2016W35 | 4753_24617 | 4753_24617 | LPP | LI | 86008828 | 1 | 2016-08-15 | 2016-08-15 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-08-20 |  | 0 |  |  |  | 2016-08-20 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 5217_26578 | 5217_26578 | CHS | VW | 86012103 | 1 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEA3 | 86004101 | 1 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 5217_26578 | 5217_26578 | CHS | VW | 86012103 | 1 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.IKEA3 | 86004102 | 1 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 5217_26578 | 5217_26578 | CHS | VW | 86012103 | 1 | 2016-08-15 | 2016-08-15 | BATTERY-BOX | ANTARES | 45000039-05 | 12 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-20 |  | 0 |  |  |  | 2016-08-20 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 5217_26579 | 5217_26579 | CHS | VW | 86012109 | 1 | 2016-08-08 | 2016-08-08 | BATTERY-BOX | PACK | 07017435 | 4 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 5217_26579 | 5217_26579 | CHS | VW | 86012109 | 1 | 2016-08-08 | 2016-08-08 | RACK-ASM | MRACK.CENTILIUM | 86003208-01 | 2 | 0 | 0 | [5 empty] | N | 2016-08-13 |  | 0 |  |  |  | 2016-08-13 |  |  |  | 2016-08-15 | 0
SERVER | AT | 2016-05-12 | 2016-08-29 | 2016W35 | 5217_26579 | 5217_26579 | CHS | VW | 86012109 | 1 | 2016-08-15 | 2016-08-15 | BATTERY-BOX | PACK | 07000733 | 116 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-08-20 |  | 0 |  |  |  | 2016-08-20 |  |  |  | 2016-08-15 | 0
SERVER | SG | 2016-05-12 | 2016-09-05 | 2016W36 | 3836_21729 | 3836_21729 | CHG | TM | 86008649 | 3 | 2016-07-25 | 2016-07-25 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-08-22 | 0
SERVER | SG | 2016-05-12 | 2016-09-05 | 2016W36 | 3836_21729 | 3836_21729 | CHG | TM | 86008649 | 3 | 2016-08-22 | 2016-08-22 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-22 | 0
SERVER | SG | 2016-05-12 | 2016-09-05 | 2016W36 | 5250_26725 | 5250_26725 | CHG | TL | 86010447 | 3 | 2016-07-25 | 2016-07-25 | RACK-ASM | MRACK.IKEA3 | 86009168 | 3 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-08-22 | 0
SERVER | SG | 2016-05-12 | 2016-09-05 | 2016W36 | 5250_26725 | 5250_26725 | CHG | TL | 86010447 | 3 | 2016-07-25 | 2016-07-25 | RACK-ASM | MRACK.IKEA3 | 86009169 | 3 | 0 | 0 | [5 empty] | N | 2016-07-30 |  | 0 |  |  |  | 2016-07-30 |  |  |  | 2016-08-22 | 0
SERVER | SG | 2016-05-12 | 2016-09-05 | 2016W36 | 5250_26725 | 5250_26725 | CHG | TL | 86010447 | 3 | 2016-08-22 | 2016-08-22 | BATTERY-BOX | ANTARES | 45000039-05 | 42 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-22 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 3426_20242 | 3426_20242 | CHS | UC | 86010392 | 6 | 2016-08-22 | 2016-08-22 | RACK-ASM | MRACK.IKEA3 | 86010332 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 3426_20242 | 3426_20242 | CHS | UC | 86010392 | 6 | 2016-08-22 | 2016-08-22 | RACK-ASM | MRACK.IKEA3 | 86010333 | 6 | 0 | 0 |  |  |  |  | PVT | Y | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 3426_20242 | 3426_20242 | CHS | UC | 86010392 | 6 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 96 | 0 | 0 | Pull-from-Stock |  |  |  | PVT | Y | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26278 | 5115_26278 | IAD | XG | 86011669 | 12 | 2016-08-22 | 2016-08-22 | RACK-ASM | NRACK.IKEA3S | 86009609 | 12 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26278 | 5115_26278 | IAD | XG | 86011669 | 12 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26279 | 5115_26279 | IAD | XH | 86011669 | 12 | 2016-08-22 | 2016-08-22 | RACK-ASM | NRACK.IKEA3S | 86009609 | 12 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26279 | 5115_26279 | IAD | XH | 86011669 | 12 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26280 | 5115_26280 | IAD | XI | 86011669 | 12 | 2016-08-22 | 2016-08-22 | RACK-ASM | NRACK.IKEA3S | 86009609 | 12 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26280 | 5115_26280 | IAD | XI | 86011669 | 12 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26281 | 5115_26281 | IAD | XG | 86010320 | 2 | 2016-08-22 | 2016-08-22 | RACK-ASM | NRACK.IKEA3S | 86009609 | 2 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5115_26281 | 5115_26281 | IAD | XG | 86010320 | 2 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 8 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | NL | 2016-05-12 | 2016-09-12 | 2016W37 | 5336_26890 | 5336_26890 | BRU | WO | 86010548 | 1 | 2016-08-22 | 2016-08-22 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | NL | 2016-05-12 | 2016-09-12 | 2016W37 | 5336_26890 | 5336_26890 | BRU | WO | 86010548 | 1 | 2016-08-22 | 2016-08-22 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | NL | 2016-05-12 | 2016-09-12 | 2016W37 | 5336_26890 | 5336_26890 | BRU | WO | 86010548 | 1 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5340_26896 | 5340_26896 | MRN | QN | 86010548 | 1 | 2016-08-22 | 2016-08-22 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5340_26896 | 5340_26896 | MRN | QN | 86010548 | 1 | 2016-08-22 | 2016-08-22 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-08-27 |  | 0 |  |  |  | 2016-08-27 |  |  |  | 2016-08-29 | 0
SERVER | AT | 2016-05-12 | 2016-09-12 | 2016W37 | 5340_26896 | 5340_26896 | MRN | QN | 86010548 | 1 | 2016-08-29 | 2016-08-29 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-08-29 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5189_26534 | 5189_26534 | FRA | XJ | 86011669 | 6 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 6 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5189_26534 | 5189_26534 | FRA | XJ | 86011669 | 6 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5190_26537 | 5190_26537 | FRA | XK | 86011669 | 6 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 6 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5190_26537 | 5190_26537 | FRA | XK | 86011669 | 6 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5191_26540 | 5191_26540 | FRA | XM | 86011669 | 6 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 6 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5191_26540 | 5191_26540 | FRA | XM | 86011669 | 6 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 24 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26522 | 5202_26522 | FRA | XJ | 86011669 | 12 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 12 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26522 | 5202_26522 | FRA | XJ | 86011669 | 12 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26523 | 5202_26523 | FRA | XK | 86011669 | 12 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 12 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26523 | 5202_26523 | FRA | XK | 86011669 | 12 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26524 | 5202_26524 | FRA | XM | 86011669 | 12 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 12 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26524 | 5202_26524 | FRA | XM | 86011669 | 12 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 48 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26525 | 5202_26525 | FRA | XJ | 86010320 | 2 | 2016-08-29 | 2016-08-29 | RACK-ASM | NRACK.IKEA3S | 86009609 | 2 | 0 | 0 | [5 empty] | N | 2016-09-03 |  | 0 |  |  |  | 2016-09-03 |  |  |  | 2016-09-05 | 0
SERVER | NL | 2016-05-12 | 2016-09-19 | 2016W38 | 5202_26525 | 5202_26525 | FRA | XJ | 86010320 | 2 | 2016-09-05 | 2016-09-05 | BATTERY-BOX | ANTARES | 45000039-05 | 8 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-10 |  | 0 |  |  |  | 2016-09-10 |  |  |  | 2016-09-05 | 0
SERVER | AT | 2016-05-12 | 2016-10-03 | 2016W40 | 3749_25313 | 3749_25313 | TUL | NJ | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007203 | 6 | 0 | 6 | MIM-Shipped |  |  |  |  | N |  |  | 6 | DONE | MORSC3889075931 | 2016-03-07 | 2016-05-14 | 2016-03-07 |  | 2016-03-07 | 2016-09-19 | 0
SERVER | AT | 2016-05-12 | 2016-10-03 | 2016W40 | 3749_25313 | 3749_25313 | TUL | NJ | 86008863 | 6 | 2016-05-09 | 2016-05-09 | RACK-ASM | MRACK.IKEA3 | 86007204 | 6 | 0 | 6 | MIM-Shipped |  |  |  |  | N |  |  | 6 | DONE | MORSC3889075931 | 2016-03-07 | 2016-05-14 | 2016-03-07 |  | 2016-03-07 | 2016-09-19 | 0
SERVER | AT | 2016-05-12 | 2016-10-03 | 2016W40 | 3749_25313 | 3749_25313 | TUL | NJ | 86008863 | 6 | 2016-09-19 | 2016-09-19 | BATTERY-BOX | ANTARES | 45000039-05 | 72 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-09-24 |  | 0 |  |  |  | 2016-09-24 |  |  |  | 2016-09-19 | 0
FABRIC | NL | 2016-05-12 | 2016-10-03 | 2016W40 | 5189_26532 | 5189_26532 | FRA | XJ | 86010317 | 1 | 2016-09-12 | 2016-09-12 | RACK-ASM | NRACK.IKEA3S | 86010148 | 1 | 0 | 0 | [5 empty] | N | 2016-09-17 |  | 0 |  |  |  | 2016-09-17 |  |  |  | 2016-09-19 | 0
FABRIC | NL | 2016-05-12 | 2016-10-03 | 2016W40 | 5189_26533 | 5189_26533 | FRA | XJ | 86010007 | 4 | 2016-09-12 | 2016-09-12 | RACK-ASM | NRACK.IKEAS | 86010008 | 4 | 0 | 0 | [5 empty] | N | 2016-09-17 |  | 0 |  |  |  | 2016-09-17 |  |  |  | 2016-09-19 | 0
FABRIC | NL | 2016-05-12 | 2016-10-03 | 2016W40 | 5190_26535 | 5190_26535 | FRA | XK | 86010317 | 1 | 2016-09-12 | 2016-09-12 | RACK-ASM | NRACK.IKEA3S | 86010148 | 1 | 0 | 0 | [5 empty] | N | 2016-09-17 |  | 0 |  |  |  | 2016-09-17 |  |  |  | 2016-09-19 | 0
FABRIC | NL | 2016-05-12 | 2016-10-03 | 2016W40 | 5190_26536 | 5190_26536 | FRA | XK | 86010007 | 4 | 2016-09-12 | 2016-09-12 | RACK-ASM | NRACK.IKEAS | 86010008 | 4 | 0 | 0 | [5 empty] | N | 2016-09-17 |  | 0 |  |  |  | 2016-09-17 |  |  |  | 2016-09-19 | 0
FABRIC | NL | 2016-05-12 | 2016-10-03 | 2016W40 | 5191_26538 | 5191_26538 | FRA | XM | 86010317 | 1 | 2016-09-12 | 2016-09-12 | RACK-ASM | NRACK.IKEA3S | 86010148 | 1 | 0 | 0 | [5 empty] | N | 2016-09-17 |  | 0 |  |  |  | 2016-09-17 |  |  |  | 2016-09-19 | 0
FABRIC | NL | 2016-05-12 | 2016-10-03 | 2016W40 | 5191_26539 | 5191_26539 | FRA | XM | 86010007 | 4 | 2016-09-12 | 2016-09-12 | RACK-ASM | NRACK.IKEAS | 86010008 | 4 | 0 | 0 | [5 empty] | N | 2016-09-17 |  | 0 |  |  |  | 2016-09-17 |  |  |  | 2016-09-19 | 0
SERVER | AT | 2016-05-12 | 2016-10-17 | 2016W42 | 5337_26893 | 5337_26893 | TUL | ON | 86010548 | 1 | 2016-09-26 | 2016-09-26 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-10-01 |  | 0 |  |  |  | 2016-10-01 |  |  |  | 2016-10-03 | 0
SERVER | AT | 2016-05-12 | 2016-10-17 | 2016W42 | 5337_26893 | 5337_26893 | TUL | ON | 86010548 | 1 | 2016-09-26 | 2016-09-26 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-10-01 |  | 0 |  |  |  | 2016-10-01 |  |  |  | 2016-10-03 | 0
SERVER | AT | 2016-05-12 | 2016-10-17 | 2016W42 | 5337_26893 | 5337_26893 | TUL | ON | 86010548 | 1 | 2016-10-03 | 2016-10-03 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-10-08 |  | 0 |  |  |  | 2016-10-08 |  |  |  | 2016-10-03 | 0
SERVER | AT | 2016-05-12 | 2016-10-17 | 2016W42 | 5346_26899 | 5346_26899 | CBF | IX | 86010548 | 1 | 2016-09-26 | 2016-09-26 | RACK-ASM | MRACK.IKEA3 | 86009147 | 1 | 0 | 0 | [5 empty] | N | 2016-10-01 |  | 0 |  |  |  | 2016-10-01 |  |  |  | 2016-10-03 | 0
SERVER | AT | 2016-05-12 | 2016-10-17 | 2016W42 | 5346_26899 | 5346_26899 | CBF | IX | 86010548 | 1 | 2016-09-26 | 2016-09-26 | RACK-ASM | MRACK.IKEA3 | 86009148 | 1 | 0 | 0 | [5 empty] | N | 2016-10-01 |  | 0 |  |  |  | 2016-10-01 |  |  |  | 2016-10-03 | 0
SERVER | AT | 2016-05-12 | 2016-10-17 | 2016W42 | 5346_26899 | 5346_26899 | CBF | IX | 86010548 | 1 | 2016-10-03 | 2016-10-03 | BATTERY-BOX | ANTARES | 45000039-05 | 14 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-10-08 |  | 0 |  |  |  | 2016-10-08 |  |  |  | 2016-10-03 | 0
SERVER | SG | 2016-05-12 | 2016-11-07 | 2016W45 | 3838_21730 | 3838_21730 | CHG | TN | 86008649 | 3 | 2016-09-26 | 2016-09-26 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-10-01 |  | 0 |  |  |  | 2016-10-01 |  |  |  | 2016-10-24 | 0
SERVER | SG | 2016-05-12 | 2016-11-07 | 2016W45 | 3838_21730 | 3838_21730 | CHG | TN | 86008649 | 3 | 2016-10-24 | 2016-10-24 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | SG | 2016-05-12 | 2016-11-07 | 2016W45 | 3842_21732 | 3842_21732 | CHG | TO | 86008649 | 3 | 2016-09-26 | 2016-09-26 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-10-01 |  | 0 |  |  |  | 2016-10-01 |  |  |  | 2016-10-24 | 0
SERVER | SG | 2016-05-12 | 2016-11-07 | 2016W45 | 3842_21732 | 3842_21732 | CHG | TO | 86008649 | 3 | 2016-10-24 | 2016-10-24 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07001792 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07003764 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004272 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004276 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004328 | 736 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004980 | 322 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07007127 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07007365 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07009060 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07011143 | 1104 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07014320 | 736 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07018006 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07036764 | 184 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07048077 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07048132 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07048407 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07052887 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07053933-01 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07053934-01 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07054060 | 552 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07054109 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07054957 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07061299 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07073292 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07086015 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07086018 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07089141 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07089473 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07090295 | 322 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07091558 | 276 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07099933 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07099935 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07108530 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07114616 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07120200 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07124653 | 460 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07126550 | 1656 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 12000325-01 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 13000125-02 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000189-01 | 414 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000592-01 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000616-01 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000808-02 | 138 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000173-01 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000307-05 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000495-13 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000497-03 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000535-02 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000548-05 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42001369-01 | 92 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 86007919 | 46 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 901223 | 736 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 901225 | 736 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 901289 | 736 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4722_24440 | 4722_24440 | ATL | BA | 86012632 | 46 | 2016-11-07 | 2016-11-07 | RACK-ASM | MRACK.IKEAS-B | 86012672 | 46 | 0 | 0 | [5 empty] | N | 2016-11-12 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4723_24444 | 4723_24444 | ATL | AC | 86012567 | 12 | 2016-10-31 | 2016-11-07 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 12 | 0 | 0 | [5 empty] | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-10-24 | 0
SERVER | AT | 2016-05-12 | 2016-11-07 | 2016W45 | 4723_26878 | 4723_26878 | ATL | AC | 86012567 | 22 | 2016-10-24 | 2016-10-24 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 22 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07001792 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07003764 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004272 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004276 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004328 | 544 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07004980 | 238 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07007127 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07007365 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07009060 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07011143 | 816 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07014320 | 544 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07018006 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07036764 | 136 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07048077 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07048132 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07048407 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07052887 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07053933-01 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07053934-01 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07054060 | 408 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07054109 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07054957 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07061299 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07073292 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07086015 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07086018 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07089141 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07089473 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07090295 | 238 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07091558 | 204 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07099933 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07099935 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07108530 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07114616 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07120200 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07124653 | 340 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 07126550 | 1224 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 12000325-01 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 13000125-02 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000189-01 | 306 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000592-01 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000616-01 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 16000808-02 | 102 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000173-01 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000307-05 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000495-13 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000497-03 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000535-02 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42000548-05 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 42001369-01 | 68 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 86007919 | 34 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 901223 | 544 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 901225 | 544 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-10-24 | 2016-10-24 | RACK-ASM | HWKIT | 901289 | 544 | 0 | 0 | [5 empty] | N | 2016-10-29 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4724_24447 | 4724_24447 | AMS | BA | 86012632 | 34 | 2016-11-07 | 2016-11-07 | RACK-ASM | MRACK.IKEAS-B | 86012672 | 34 | 0 | 0 | [5 empty] | N | 2016-11-12 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4725_24451 | 4725_24451 | AMS | AC | 86012567 | 6 | 2016-10-31 | 2016-11-07 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 6 | 0 | 0 | [5 empty] | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-07 | 2016W45 | 4725_26875 | 4725_26875 | AMS | AC | 86012567 | 4 | 2016-10-31 | 2016-11-07 | RACK-ASM | MRACK.IKEAS-S | 86012707 | 4 | 0 | 0 | [5 empty] | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-10-24 | 0
SERVER | NL | 2016-05-12 | 2016-11-14 | 2016W46 | 3729_21738 | 3729_21738 | LPP | LV | 86008540 | 6 | 2016-10-17 | 2016-10-24 | RACK-ASM | MRACK.IKEA2 | 86008483 | 6 | 0 | 0 | [5 empty] | N | 2016-10-22 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-31 | 0
SERVER | NL | 2016-05-12 | 2016-11-14 | 2016W46 | 3729_21738 | 3729_21738 | LPP | LV | 86008540 | 6 | 2016-10-17 | 2016-10-24 | RACK-ASM | MRACK.IKEA2 | 86008484 | 6 | 0 | 0 | [5 empty] | N | 2016-10-22 |  | 0 |  |  |  | 2016-10-29 |  |  |  | 2016-10-31 | 0
SERVER | NL | 2016-05-12 | 2016-11-14 | 2016W46 | 3729_21738 | 3729_21738 | LPP | LV | 86008540 | 6 | 2016-10-31 | 2016-10-31 | BATTERY-BOX | JUICE-BOX | 45000031-04 | 120 | 0 | 0 | Built-to-Stock |  |  |  |  | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-05 |  |  |  | 2016-10-31 | 0
SERVER | NL | 2016-05-12 | 2016-11-21 | 2016W47 | 4155_24518 | 4155_24518 | GRQ | EL | 86008649 | 3 | 2016-10-31 | 2016-10-31 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-05 |  |  |  | 2016-11-07 | 0
SERVER | NL | 2016-05-12 | 2016-11-21 | 2016W47 | 4155_24518 | 4155_24518 | GRQ | EL | 86008649 | 3 | 2016-11-07 | 2016-11-07 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-11-12 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-11-07 | 0
SERVER | NL | 2016-05-12 | 2016-11-21 | 2016W47 | 4157_23368 | 4157_23368 | GRQ | EJ | 86008649 | 3 | 2016-10-31 | 2016-10-31 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-05 |  |  |  | 2016-11-07 | 0
SERVER | NL | 2016-05-12 | 2016-11-21 | 2016W47 | 4157_23368 | 4157_23368 | GRQ | EJ | 86008649 | 3 | 2016-11-07 | 2016-11-07 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-11-12 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-11-07 | 0
SERVER | NL | 2016-05-12 | 2016-11-21 | 2016W47 | 4241_24519 | 4241_24519 | GRQ | EK | 86008649 | 3 | 2016-10-31 | 2016-10-31 | RACK-ASM | MRACK.IKEA3 | 86008664 | 6 | 0 | 0 | [5 empty] | N | 2016-11-05 |  | 0 |  |  |  | 2016-11-05 |  |  |  | 2016-11-07 | 0
SERVER | NL | 2016-05-12 | 2016-11-21 | 2016W47 | 4241_24519 | 4241_24519 | GRQ | EK | 86008649 | 3 | 2016-11-07 | 2016-11-07 | BATTERY-BOX | ANTARES | 45000039-05 | 54 | 0 | 0 | Pull-from-Stock |  |  |  |  | N | 2016-11-12 |  | 0 |  |  |  | 2016-11-12 |  |  |  | 2016-11-07 | 0

## MIM Ship Detail
Ship Date | Status | Prod Site | Build ID | Order Num | Line Num | Part Number | Ship Qty | Ship Date | Status | Prod Site | Build ID | Order Num | Line Num | Part Number | Ship Qty
04/16/2016 | SHIPPED | AT | 4115_25054 | XABTOR690246 | 1 | 86010910 | 1
05/12/2016 | SHIPPED | AT | 4707_24349 | XABTOR704854 | 1 | 86012106 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682226 | 1 | 86009147 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664431 | 1 | 86009147 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682353 | 1 | 86009147 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR699999 | 1 | 86009147 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR699944 | 1 | 86009147 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR699967 | 1 | 86009147 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664614 | 1 | 86009147 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664441 | 1 | 86009147 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR699946 | 1 | 86009147 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR699994 | 1 | 86009147 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682245 | 1 | 86009147 | 1
03/30/2016 | SHIPPED | NL | 4760_24641 | XABTOR681628 | 1 | 86009147 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664439 | 1 | 86009147 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682244 | 1 | 86009147 | 1
01/07/2016 | SHIPPED | AT | 4667_24061 | XABTOR646373 | 1 | 86010634 | 1
01/08/2016 | SHIPPED | AT | 4667_24061 | XABTOR646823 | 1 | 86010634 | 1
01/07/2016 | SHIPPED | AT | 4667_24061 | XABTOR646382 | 1 | 86010634 | 1
01/06/2016 | SHIPPED | AT | 4667_24061 | XABTOR645548 | 1 | 86010634 | 1
04/01/2016 | SHIPPED | AT | 4883_25494 | XABTOR683256 | 1 | 86011470 | 1
03/31/2016 | SHIPPED | AT | 4883_25494 | XABTOR682560 | 1 | 86011470 | 1
04/15/2016 | SHIPPED | AT | 4988_25772 | XABTOR689709 | 1 | 86012211 | 1
05/06/2016 | SHIPPED | AT | 5099_26187 | XABTOR701525 | 1 | 86012211 | 1
04/29/2016 | SHIPPED | AT | 5099_26187 | XABTOR698110 | 1 | 86012211 | 1
05/06/2016 | SHIPPED | AT | 5099_26187 | XABTOR701526 | 1 | 86012211 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688011 | 1 | 86006117 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688147 | 1 | 86006117 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688282 | 1 | 86006117 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688371 | 1 | 86006117 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688280 | 1 | 86006117 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688223 | 1 | 86006117 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688273 | 1 | 86006117 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688284 | 1 | 86006117 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688155 | 1 | 86006117 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688006 | 1 | 86006117 | 1
01/30/2016 | SHIPPED | AT | 4840_24968 | XABTOR656461 | 1 | 86010992 | 1
04/21/2016 | SHIPPED | AT | 5049_25965 | XABTOR693157 | 1 | 86010992 | 1
04/20/2016 | SHIPPED | AT | 5049_25965 | XABTOR692038 | 1 | 86010992 | 1
04/21/2016 | SHIPPED | AT | 5049_25965 | XABTOR693162 | 1 | 86010992 | 1
05/03/2016 | SHIPPED | AT | 5049_25965 | XABTOR699446 | 1 | 86010992 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR657757 | 1 | 86010992 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR658050 | 1 | 86010992 | 1
02/04/2016 | SHIPPED | AT | 4840_24968 | XABTOR658465 | 1 | 86010992 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR658175 | 1 | 86010992 | 1
04/20/2016 | SHIPPED | AT | 5049_25965 | XABTOR692047 | 1 | 86010992 | 1
02/04/2016 | SHIPPED | AT | 4840_24968 | XABTOR659049 | 1 | 86010992 | 1
05/07/2016 | SHIPPED | AT | 4792_24771 | XABTOR701874 | 1 | 86012387 | 1
05/05/2016 | SHIPPED | AT | 4792_24771 | XABTOR701012 | 1 | 86012387 | 1
05/07/2016 | SHIPPED | AT | 4792_24771 | XABTOR701873 | 1 | 86012387 | 1
05/07/2016 | SHIPPED | AT | 4792_24771 | XABTOR701876 | 1 | 86012387 | 1
05/05/2016 | SHIPPED | AT | 4792_24771 | XABTOR701007 | 1 | 86012387 | 1
05/07/2016 | SHIPPED | AT | 4792_24771 | XABTOR701875 | 1 | 86012387 | 1
04/29/2016 | SHIPPED | AT | 4792_24771 | XABTOR697796 | 1 | 86012387 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692135 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692234 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692235 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692239 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692137 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692227 | 1 | 86010929 | 1
04/21/2016 | SHIPPED | AT | 5049_25966 | XABTOR693047 | 1 | 86010929 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691641 | 1 | 86010929 | 1
04/28/2016 | SHIPPED | AT | 5049_25966 | XABTOR697250 | 1 | 86010929 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691795 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692052 | 1 | 86010929 | 1
02/04/2016 | SHIPPED | AT | 4840_24954 | XABTOR658457 | 1 | 86010929 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691682 | 1 | 86010929 | 1
02/02/2016 | SHIPPED | AT | 4840_24969 | XABTOR657172 | 1 | 86010929 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691797 | 1 | 86010929 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692072 | 1 | 86010929 | 1
02/02/2016 | SHIPPED | AT | 4840_24954 | XABTOR657465 | 1 | 86010929 | 1
04/21/2016 | SHIPPED | AT | 5049_25966 | XABTOR693046 | 1 | 86010929 | 1
05/07/2016 | SHIPPED | AT | 4926_26401 | XABTOR702117 | 1 | 86012829 | 1
04/06/2016 | SHIPPED | AT | 4582_23767 | XABTOR685580 | 1 | 86009168 | 1
04/06/2016 | SHIPPED | AT | 4582_23767 | XABTOR685235 | 1 | 86009168 | 1
04/06/2016 | SHIPPED | AT | 4582_23767 | XABTOR685555 | 1 | 86009168 | 1
04/21/2016 | SHIPPED | AT | 4571_23756 | XABTOR693209 | 1 | 86009168 | 1
04/20/2016 | SHIPPED | AT | 4568_23753 | XABTOR692606 | 1 | 86009168 | 1
04/21/2016 | SHIPPED | AT | 4589_23783 | XABTOR693206 | 1 | 86009168 | 1
05/12/2016 | SHIPPED | AT | 5231_26599 | XABTOR705203 | 1 | 86009168 | 1
04/11/2016 | SHIPPED | NL | 4580_23765 | XABTOR687303 | 1 | 86009168 | 1
04/11/2016 | SHIPPED | NL | 4580_23765 | XABTOR687417 | 1 | 86009168 | 1
05/12/2016 | SHIPPED | AT | 5231_26599 | XABTOR705200 | 1 | 86009168 | 1
04/11/2016 | SHIPPED | NL | 4580_23765 | XABTOR687423 | 1 | 86009168 | 1
02/03/2016 | SHIPPED | AT | 4706_24348 | XABTOR658178 | 1 | 86009323 | 1
02/01/2016 | SHIPPED | AT | 4706_24348 | XABTOR656877 | 1 | 86009323 | 1
03/22/2016 | SHIPPED | AT | 3844_18929 | XABTOR677826 | 1 | 86009419 | 1
03/31/2016 | SHIPPED | AT | 3844_18929 | XABTOR682217 | 1 | 86009419 | 1
03/29/2016 | SHIPPED | AT | 3844_18929 | XABTOR681345 | 1 | 86009419 | 1
03/25/2016 | SHIPPED | AT | 3844_18929 | XABTOR679648 | 1 | 86009419 | 1
04/02/2016 | SHIPPED | AT | 3844_18929 | XABTOR683426 | 1 | 86009419 | 1
03/29/2016 | SHIPPED | AT | 3844_18929 | XABTOR680940 | 1 | 86009419 | 1
03/31/2016 | SHIPPED | AT | 3844_18929 | XABTOR682016 | 1 | 86009419 | 1
03/29/2016 | SHIPPED | AT | 3844_18929 | XABTOR681357 | 1 | 86009419 | 1
04/16/2016 | SHIPPED | AT | 4115_25054 | XABTOR690271 | 1 | 86010911 | 1
05/09/2016 | SHIPPED | AT | 5114_26230 | XABTOR702261 | 1 | 86012208 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688291 | 1 | 86006116 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688359 | 1 | 86006116 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688403 | 1 | 86006116 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688136 | 1 | 86006116 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688157 | 1 | 86006116 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688150 | 1 | 86006116 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688153 | 1 | 86006116 | 1
04/13/2016 | SHIPPED | AT | 4894_25212 | XABTOR688283 | 1 | 86006116 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688149 | 1 | 86006116 | 1
04/12/2016 | SHIPPED | AT | 4894_25212 | XABTOR688151 | 1 | 86006116 | 1
03/08/2016 | SHIPPED | AT | 4954_25517 | XABTOR672296 | 1 | 86008579 | 1
03/09/2016 | SHIPPED | AT | 4954_25517 | XABTOR673055 | 1 | 86008579 | 1
03/08/2016 | SHIPPED | AT | 4954_25517 | XABTOR672200 | 1 | 86008579 | 1
04/26/2016 | SHIPPED | AT | 5116_26238 | XABTOR695682 | 1 | 86008703 | 1
04/21/2016 | SHIPPED | AT | 4980_25696 | XABTOR693208 | 1 | 86008703 | 1
04/21/2016 | SHIPPED | AT | 4980_25696 | XABTOR693352 | 1 | 86008703 | 1
04/21/2016 | SHIPPED | AT | 4980_25696 | XABTOR693210 | 1 | 86008703 | 1
05/12/2016 | SHIPPED | SG | 5112_26228 | XABTOR704648 | 1 | 86008703 | 1
04/27/2016 | SHIPPED | AT | 5116_26239 | XABTOR696181 | 1 | 86008703 | 1
04/21/2016 | SHIPPED | AT | 4980_25696 | XABTOR693483 | 1 | 86008703 | 1
02/09/2016 | SHIPPED | NL | 4018_20050 | XABTOR660760 | 1 | 86009511 | 1
04/08/2016 | SHIPPED | AT | 3733_18264 | XABTOR686348 | 1 | 86009511 | 1
02/09/2016 | SHIPPED | NL | 4018_20050 | XABTOR660443 | 1 | 86009511 | 1
02/09/2016 | SHIPPED | NL | 4018_20050 | XABTOR660486 | 1 | 86009511 | 1
05/12/2016 | SHIPPED | NL | BTS_86009511_02_E_16W19 | XABTOR705131 | 1 | 86009511 | 1
02/08/2016 | SHIPPED | NL | 4018_20050 | XABTOR659825 | 1 | 86009511 | 1
02/09/2016 | SHIPPED | NL | 4018_20050 | XABTOR660700 | 1 | 86009511 | 1
02/09/2016 | SHIPPED | NL | 4018_20050 | XABTOR660445 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4021_20054 | XABTOR699303 | 1 | 86009511 | 1
04/04/2016 | SHIPPED | AT | 3733_18264 | XABTOR683694 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4020_20052 | XABTOR699157 | 1 | 86009511 | 1
05/12/2016 | SHIPPED | NL | BTS_86009511_02_E_16W19 | XABTOR705127 | 1 | 86009511 | 1
02/10/2016 | SHIPPED | NL | 4018_20050 | XABTOR661070 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4021_20054 | XABTOR699480 | 1 | 86009511 | 1
04/06/2016 | SHIPPED | AT | 3733_18264 | XABTOR685214 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4021_20054 | XABTOR699302 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4020_20052 | XABTOR699155 | 1 | 86009511 | 1
02/08/2016 | SHIPPED | NL | 4018_20050 | XABTOR659827 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4020_20052 | XABTOR699154 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4021_20054 | XABTOR699471 | 1 | 86009511 | 1
05/03/2016 | SHIPPED | NL | 4020_20052 | XABTOR699156 | 1 | 86009511 | 1
04/04/2016 | SHIPPED | AT | 3733_18264 | XABTOR684226 | 1 | 86009511 | 1
04/06/2016 | SHIPPED | AT | 3733_18264 | XABTOR685228 | 1 | 86009511 | 1
04/07/2016 | SHIPPED | AT | 3733_18264 | XABTOR685730 | 1 | 86009511 | 1
04/08/2016 | SHIPPED | AT | 3733_18264 | XABTOR686556 | 1 | 86009511 | 1
04/07/2016 | SHIPPED | AT | 3733_18264 | XABTOR686153 | 1 | 86009511 | 1
04/02/2016 | SHIPPED | AT | 4883_25494 | XABTOR683463 | 1 | 86011471 | 1
04/01/2016 | SHIPPED | AT | 4883_25494 | XABTOR683255 | 1 | 86011471 | 1
05/05/2015 | SHIPPED | AT | 4267_22104 | XABTOR552436 | 1 | 86003679 | 1
05/09/2016 | SHIPPED | AT | 5225_26590 | XABTOR702262 | 1 | 86003679 | 1
02/08/2016 | SHIPPED | AT | 4873_25110 | XABTOR659742 | 1 | 86003679 | 1
05/03/2015 | SHIPPED | AT | 4267_22104 | XABTOR551921 | 1 | 86003679 | 1
10/04/2015 | SHIPPED | AT | 3685_23437 | XABTOR612880 | 1 | 86003679 | 1
11/03/2015 | SHIPPED | AT | 4015_23979 | XABTOR623756 | 1 | 86003679 | 1
05/11/2016 | SHIPPED | AT | 5225_26590 | XABTOR703782 | 1 | 86003679 | 1
05/11/2016 | SHIPPED | AT | 5224_26588 | XABTOR703783 | 1 | 86003679 | 1
02/06/2016 | SHIPPED | AT | 4873_25110 | XABTOR659630 | 1 | 86003679 | 1
02/08/2016 | SHIPPED | AT | 4874_25112 | XABTOR659795 | 1 | 86003679 | 1
05/03/2016 | SHIPPED | AT | 5224_26588 | XABTOR699102 | 1 | 86003679 | 1
02/11/2016 | SHIPPED | AT | 4874_25112 | XABTOR662002 | 1 | 86003679 | 1
05/03/2015 | SHIPPED | AT | 4267_22104 | XABTOR551923 | 1 | 86003679 | 1
05/06/2016 | SHIPPED | AT | 5224_26588 | XABTOR701257 | 1 | 86003679 | 1
11/03/2015 | SHIPPED | AT | 4015_23979 | XABTOR623571 | 1 | 86003679 | 1
04/04/2016 | SHIPPED | AT | 4875_25115 | XABTOR683669 | 1 | 86003679 | 1
05/05/2015 | SHIPPED | AT | 4267_22104 | XABTOR552440 | 1 | 86003679 | 1
02/08/2016 | SHIPPED | AT | 4873_25110 | XABTOR659668 | 1 | 86003679 | 1
11/04/2015 | SHIPPED | AT | 4015_23979 | XABTOR623808 | 1 | 86003679 | 1
02/06/2016 | SHIPPED | AT | 4873_25110 | XABTOR659632 | 1 | 86003679 | 1
02/09/2016 | SHIPPED | AT | 4874_25112 | XABTOR660193 | 1 | 86003679 | 1
02/04/2016 | SHIPPED | AT | 4876_25117 | XABTOR658746 | 1 | 86003679 | 1
11/03/2015 | SHIPPED | AT | 4015_23979 | XABTOR623572 | 1 | 86003679 | 1
05/09/2016 | SHIPPED | AT | 5225_26590 | XABTOR702263 | 1 | 86003679 | 1
10/05/2015 | SHIPPED | AT | 3685_23437 | XABTOR613268 | 1 | 86003679 | 1
02/09/2016 | SHIPPED | AT | 4874_25112 | XABTOR660187 | 1 | 86003679 | 1
10/14/2015 | SHIPPED | AT | 4267_22104 | XABTOR617369 | 1 | 86003679 | 1
05/09/2016 | SHIPPED | AT | 5225_26590 | XABTOR702250 | 1 | 86003679 | 1
05/10/2016 | SHIPPED | AT | 5224_26588 | XABTOR703657 | 1 | 86003679 | 1
02/05/2016 | SHIPPED | AT | 4876_25117 | XABTOR659190 | 1 | 86003679 | 1
05/09/2016 | SHIPPED | AT | 5026_25883 | XABTOR702580 | 1 | 86010908 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691750 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691832 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690445 | 1 | 86003208-02 | 1
11/18/2015 | SHIPPED | NL | 4683_24144 | XABTOR628142 | 1 | 86003208-02 | 1
04/13/2016 | SHIPPED | NL | 5027_26120 | XABTOR688536 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 5027_26120 | XABTOR692169 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 5027_26120 | XABTOR692173 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24142 | XABTOR628790 | 1 | 86003208-02 | 1
03/29/2016 | SHIPPED | NL | 4939_25629 | XABTOR680866 | 1 | 86003208-02 | 1
11/18/2015 | SHIPPED | NL | 4683_24144 | XABTOR628136 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687844 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628580 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693710 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 4975_25597 | XABTOR692663 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 5027_26120 | XABTOR692236 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690900 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688067 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24143 | XABTOR628582 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24143 | XABTOR628812 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691572 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690385 | 1 | 86003208-02 | 1
04/11/2016 | SHIPPED | NL | 5027_26120 | XABTOR687294 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691423 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691491 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691683 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691380 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693711 | 1 | 86003208-02 | 1
04/14/2016 | SHIPPED | NL | 5027_26120 | XABTOR689165 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690386 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687895 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688065 | 1 | 86003208-02 | 1
04/11/2016 | SHIPPED | NL | 5027_26120 | XABTOR687297 | 1 | 86003208-02 | 1
04/21/2016 | SHIPPED | NL | 5080_26209 | XABTOR693394 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691507 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693709 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687893 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688068 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 4975_25597 | XABTOR692666 | 1 | 86003208-02 | 1
04/21/2016 | SHIPPED | NL | 5080_26209 | XABTOR693391 | 1 | 86003208-02 | 1
11/18/2015 | SHIPPED | NL | 4683_24144 | XABTOR628135 | 1 | 86003208-02 | 1
04/14/2016 | SHIPPED | NL | 5027_26120 | XABTOR689166 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687896 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688066 | 1 | 86003208-02 | 1
04/11/2016 | SHIPPED | NL | 5027_26120 | XABTOR687296 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628500 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628519 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690904 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691578 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688109 | 1 | 86003208-02 | 1
04/11/2016 | SHIPPED | NL | 5027_26120 | XABTOR687148 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 4940_25628 | XABTOR691503 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690650 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24143 | XABTOR628807 | 1 | 86003208-02 | 1
05/04/2016 | SHIPPED | NL | 4753_24614 | XABTOR700269 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691685 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690977 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628520 | 1 | 86003208-02 | 1
05/04/2016 | SHIPPED | NL | 4753_24614 | XABTOR700191 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690814 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693745 | 1 | 86003208-02 | 1
04/14/2016 | SHIPPED | NL | 5027_26120 | XABTOR689201 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690437 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687846 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688063 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628581 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24143 | XABTOR628806 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691764 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690446 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628499 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691422 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691767 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687906 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24143 | XABTOR628810 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691382 | 1 | 86003208-02 | 1
11/18/2015 | SHIPPED | NL | 4683_24144 | XABTOR628173 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690644 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690647 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24143 | XABTOR628808 | 1 | 86003208-02 | 1
04/28/2016 | SHIPPED | AT | 5019_25842 | XABTOR696599 | 1 | 86004100 | 1
04/28/2016 | SHIPPED | AT | 5019_25842 | XABTOR696605 | 1 | 86004100 | 1
04/28/2016 | SHIPPED | AT | 5019_25842 | XABTOR696604 | 1 | 86004100 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR696755 | 1 | 86007203 | 1
02/11/2016 | SHIPPED | AT | 3992_22256 | XABTOR661908 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660515 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611546 | 1 | 86007203 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR696954 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611488 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611707 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3993_22257 | XABTOR659762 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | AT | 3993_22257 | XABTOR660631 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 4015_21526 | XABTOR660727 | 1 | 86007203 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661047 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611746 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659755 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611540 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611704 | 1 | 86007203 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR696754 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611539 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611203 | 1 | 86007203 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR696951 | 1 | 86007203 | 1
02/10/2016 | SHIPPED | AT | 3993_22257 | XABTOR660879 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611742 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660404 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660421 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3993_22257 | XABTOR659870 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611536 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 4015_21526 | XABTOR660769 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659728 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611204 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 4015_21526 | XABTOR660684 | 1 | 86007203 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661045 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3993_22257 | XABTOR659763 | 1 | 86007203 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661049 | 1 | 86007203 | 1
02/11/2016 | SHIPPED | AT | 3992_22256 | XABTOR661903 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659759 | 1 | 86007203 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611541 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659754 | 1 | 86007203 | 1
02/08/2016 | SHIPPED | AT | 3993_22257 | XABTOR659786 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660405 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660422 | 1 | 86007203 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660520 | 1 | 86007203 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR697020 | 1 | 86007203 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR696909 | 1 | 86007203 | 1
03/15/2016 | SHIPPED | AT | 3844_18929 | XABTOR674753 | 1 | 86007921 | 1
03/16/2016 | SHIPPED | AT | 3844_18929 | XABTOR675383 | 1 | 86007921 | 1
03/15/2016 | SHIPPED | AT | 3844_18929 | XABTOR674754 | 1 | 86007921 | 1
03/16/2016 | SHIPPED | AT | 3844_18929 | XABTOR675240 | 1 | 86007921 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699299 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699574 | 1 | 86008944 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692575 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699629 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699142 | 1 | 86008944 | 1
04/12/2016 | SHIPPED | AT | 4972_26389 | XABTOR687942 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699575 | 1 | 86008944 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692579 | 1 | 86008944 | 1
05/12/2016 | SHIPPED | NL | BTS_86008944_01_E_16W19 | XABTOR705192 | 1 | 86008944 | 1
05/12/2016 | SHIPPED | NL | BTS_86008944_01_E_16W19 | XABTOR704960 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699670 | 1 | 86008944 | 1
05/02/2016 | SHIPPED | AT | 5083_26131 | XABTOR698172 | 1 | 86008944 | 1
04/12/2016 | SHIPPED | AT | 4972_26389 | XABTOR687937 | 1 | 86008944 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692669 | 1 | 86008944 | 1
05/12/2016 | SHIPPED | NL | BTS_86008944_01_E_16W19 | XABTOR704962 | 1 | 86008944 | 1
04/29/2016 | SHIPPED | AT | 5083_26131 | XABTOR698125 | 1 | 86008944 | 1
04/13/2016 | SHIPPED | AT | 4972_26388 | XABTOR688404 | 1 | 86008944 | 1
05/12/2016 | SHIPPED | NL | BTS_86008944_01_E_16W19 | XABTOR705174 | 1 | 86008944 | 1
05/02/2016 | SHIPPED | NL | 5081_26126 | XABTOR698456 | 1 | 86008944 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692573 | 1 | 86008944 | 1
04/07/2016 | SHIPPED | AT | 4841_24957 | XABTOR685741 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699094 | 1 | 86008944 | 1
04/26/2016 | SHIPPED | NL | 5081_26125 | XABTOR695873 | 1 | 86008944 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699281 | 1 | 86008944 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682163 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682018 | 1 | 86010988 | 1
04/02/2016 | SHIPPED | AT | 4862_25070 | XABTOR683431 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682015 | 1 | 86010988 | 1
04/02/2016 | SHIPPED | AT | 4862_25070 | XABTOR683429 | 1 | 86010988 | 1
04/04/2016 | SHIPPED | AT | 4862_25070 | XABTOR683693 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682017 | 1 | 86010988 | 1
04/01/2016 | SHIPPED | AT | 4862_25070 | XABTOR683017 | 1 | 86010988 | 1
04/02/2016 | SHIPPED | AT | 4862_25070 | XABTOR683451 | 1 | 86010988 | 1
04/04/2016 | SHIPPED | AT | 4862_25070 | XABTOR683671 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682162 | 1 | 86010988 | 1
04/02/2016 | SHIPPED | AT | 4862_25070 | XABTOR683430 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682014 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682165 | 1 | 86010988 | 1
04/02/2016 | SHIPPED | AT | 4862_25070 | XABTOR683452 | 1 | 86010988 | 1
03/31/2016 | SHIPPED | AT | 4862_25070 | XABTOR682172 | 1 | 86010988 | 1
04/28/2016 | SHIPPED | AT | 5022_25874 | XABTOR697176 | 1 | 86011349 | 1
05/05/2016 | SHIPPED | AT | 5022_25873 | XABTOR700972 | 1 | 86011349 | 1
05/05/2016 | SHIPPED | AT | 5022_25873 | XABTOR700661 | 1 | 86011349 | 1
05/05/2016 | SHIPPED | AT | 5022_25873 | XABTOR700558 | 1 | 86011349 | 1
04/28/2016 | SHIPPED | AT | 5167_26434 | XABTOR696601 | 1 | 86012647 | 1
04/28/2016 | SHIPPED | AT | 5026_25885 | XABTOR696870 | 1 | 86003383 | 1
05/07/2016 | SHIPPED | AT | 5026_25885 | XABTOR702022 | 1 | 86003383 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701753 | 1 | 86003383 | 1
05/05/2016 | SHIPPED | AT | 5026_25884 | XABTOR701009 | 1 | 86003383 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701208 | 1 | 86003383 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701752 | 1 | 86003383 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701185 | 1 | 86003383 | 1
05/05/2016 | SHIPPED | AT | 5026_25884 | XABTOR701016 | 1 | 86003383 | 1
05/09/2016 | SHIPPED | NL | 4725_24449 | XABTOR702231 | 1 | 86004295 | 1
05/09/2016 | SHIPPED | NL | 4725_24449 | XABTOR702312 | 1 | 86004295 | 1
05/10/2016 | SHIPPED | NL | 4725_24449 | XABTOR703439 | 1 | 86004295 | 1
05/12/2016 | SHIPPED | NL | 4725_24449 | XABTOR704868 | 1 | 86004295 | 1
05/12/2016 | SHIPPED | NL | 4725_24449 | XABTOR705125 | 1 | 86004295 | 1
05/10/2016 | SHIPPED | NL | 4725_24449 | XABTOR703392 | 1 | 86004295 | 1
05/10/2016 | SHIPPED | NL | 4725_24449 | XABTOR703304 | 1 | 86004295 | 1
05/12/2016 | SHIPPED | NL | 4725_24449 | XABTOR704754 | 1 | 86004295 | 1
05/09/2016 | SHIPPED | NL | 4725_24449 | XABTOR702221 | 1 | 86004295 | 1
05/10/2016 | SHIPPED | NL | 4725_24449 | XABTOR703380 | 1 | 86004295 | 1
05/11/2016 | SHIPPED | NL | 4725_24449 | XABTOR704149 | 1 | 86004295 | 1
05/10/2016 | SHIPPED | NL | 4725_24449 | XABTOR703031 | 1 | 86004295 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661485 | 1 | 86006052 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR697242 | 1 | 86006052 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661402 | 1 | 86006052 | 1
02/11/2016 | SHIPPED | NL | 4016_21697 | XABTOR661627 | 1 | 86006052 | 1
04/23/2016 | SHIPPED | AT | 4982_25648 | XABTOR694361 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662967 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662897 | 1 | 86006052 | 1
04/26/2016 | SHIPPED | AT | 4982_25648 | XABTOR695391 | 1 | 86006052 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR697327 | 1 | 86006052 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR697324 | 1 | 86006052 | 1
04/29/2016 | SHIPPED | AT | 4982_25647 | XABTOR697607 | 1 | 86006052 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661480 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR663008 | 1 | 86006052 | 1
04/27/2016 | SHIPPED | AT | 4982_25647 | XABTOR696117 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR663012 | 1 | 86006052 | 1
04/25/2016 | SHIPPED | AT | 4982_25648 | XABTOR695032 | 1 | 86006052 | 1
04/29/2016 | SHIPPED | AT | 4982_25647 | XABTOR698108 | 1 | 86006052 | 1
04/23/2016 | SHIPPED | AT | 4982_25648 | XABTOR694363 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662915 | 1 | 86006052 | 1
04/26/2016 | SHIPPED | AT | 4982_25648 | XABTOR695408 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662971 | 1 | 86006052 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR697248 | 1 | 86006052 | 1
04/23/2016 | SHIPPED | AT | 4982_25648 | XABTOR694365 | 1 | 86006052 | 1
04/23/2016 | SHIPPED | AT | 4982_25648 | XABTOR694367 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR663062 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR663010 | 1 | 86006052 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR663063 | 1 | 86006052 | 1
04/26/2016 | SHIPPED | AT | 4982_25647 | XABTOR695720 | 1 | 86006052 | 1
04/28/2016 | SHIPPED | AT | 4982_26317 | XABTOR697322 | 1 | 86006052 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661477 | 1 | 86006052 | 1
04/25/2016 | SHIPPED | AT | 4982_25648 | XABTOR695031 | 1 | 86006052 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661442 | 1 | 86006052 | 1
04/28/2016 | SHIPPED | AT | 4982_26317 | XABTOR697325 | 1 | 86006052 | 1
12/15/2015 | SHIPPED | SG | 3836_18921 | XABTOR637380 | 1 | 86006102 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701790 | 1 | 86003384 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701511 | 1 | 86003384 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701522 | 1 | 86003384 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701788 | 1 | 86003384 | 1
05/05/2016 | SHIPPED | AT | 5026_25885 | XABTOR700998 | 1 | 86003384 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701510 | 1 | 86003384 | 1
04/28/2016 | SHIPPED | AT | 5026_25885 | XABTOR696816 | 1 | 86003384 | 1
05/06/2016 | SHIPPED | AT | 5026_25884 | XABTOR701602 | 1 | 86003384 | 1
04/21/2016 | SHIPPED | AT | 4980_25744 | XABTOR693231 | 1 | 86003988 | 1
05/12/2016 | SHIPPED | AT | BTS_86004099_01_A_16W18 | XABTOR705094 | 1 | 86004099 | 1
05/12/2016 | SHIPPED | AT | BTS_86004099_01_A_16W18 | XABTOR705096 | 1 | 86004099 | 1
04/11/2016 | SHIPPED | AT | 4894_25210 | XABTOR687487 | 1 | 86004099 | 1
04/11/2016 | SHIPPED | AT | 4894_25210 | XABTOR687483 | 1 | 86004099 | 1
05/12/2016 | SHIPPED | AT | BTS_86004099_01_A_16W18 | XABTOR705199 | 1 | 86004099 | 1
05/12/2016 | SHIPPED | AT | BTS_86004099_01_A_16W18 | XABTOR705046 | 1 | 86004099 | 1
04/08/2016 | SHIPPED | AT | 4894_25210 | XABTOR686197 | 1 | 86004099 | 1
04/07/2016 | SHIPPED | AT | 4894_25210 | XABTOR686150 | 1 | 86004099 | 1
04/08/2016 | SHIPPED | AT | 4894_25210 | XABTOR686196 | 1 | 86004099 | 1
04/07/2016 | SHIPPED | AT | 4894_25210 | XABTOR686148 | 1 | 86004099 | 1
05/12/2016 | SHIPPED | AT | BTS_86004099_01_A_16W18 | XABTOR705202 | 1 | 86004099 | 1
05/29/2015 | SHIPPED | AT | 4225_21856 | XABTOR560447 | 1 | 86004103 | 1
04/21/2016 | SHIPPED | AT | 4991_25756 | XABTOR693413 | 1 | 86008383 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681067 | 1 | 86008383 | 1
04/29/2016 | SHIPPED | AT | 5109_26407 | XABTOR698003 | 1 | 86008383 | 1
05/11/2016 | SHIPPED | NL | BTS_86008383_01_E_16W19 | XABTOR703966 | 1 | 86008383 | 1
04/29/2016 | SHIPPED | AT | 5099_26185 | XABTOR698107 | 1 | 86008383 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681003 | 1 | 86008383 | 1
04/21/2016 | SHIPPED | NL | 5081_26124 | XABTOR692948 | 1 | 86008383 | 1
04/29/2016 | SHIPPED | AT | 5109_26406 | XABTOR698105 | 1 | 86008383 | 1
05/02/2016 | SHIPPED | AT | 5109_26407 | XABTOR698264 | 1 | 86008383 | 1
04/21/2016 | SHIPPED | AT | 4991_25756 | XABTOR693475 | 1 | 86008383 | 1
05/10/2016 | SHIPPED | NL | BTS_86008383_01_E_16W19 | XABTOR703591 | 1 | 86008383 | 1
04/21/2016 | SHIPPED | AT | 4991_25756 | XABTOR693414 | 1 | 86008383 | 1
04/29/2016 | SHIPPED | AT | 5099_26185 | XABTOR698007 | 1 | 86008383 | 1
05/02/2016 | SHIPPED | AT | 5109_26406 | XABTOR698260 | 1 | 86008383 | 1
04/29/2016 | SHIPPED | AT | 5109_26406 | XABTOR698004 | 1 | 86008383 | 1
04/21/2016 | SHIPPED | AT | 4991_25756 | XABTOR693477 | 1 | 86008383 | 1
04/26/2016 | SHIPPED | AT | 5082_26127 | XABTOR695383 | 1 | 86008383 | 1
04/20/2016 | SHIPPED | AT | 5082_26210 | XABTOR692508 | 1 | 86008383 | 1
04/21/2016 | SHIPPED | NL | 5080_26121 | XABTOR692927 | 1 | 86008383 | 1
03/23/2016 | SHIPPED | NL | 4991_25755 | XABTOR678274 | 1 | 86008383 | 1
04/26/2016 | SHIPPED | AT | 5082_26127 | XABTOR695307 | 1 | 86008383 | 1
05/10/2016 | SHIPPED | NL | BTS_86008383_01_E_16W19 | XABTOR703567 | 1 | 86008383 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681151 | 1 | 86008383 | 1
04/21/2016 | SHIPPED | NL | 5081_26124 | XABTOR692947 | 1 | 86008383 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681018 | 1 | 86008383 | 1
03/23/2016 | SHIPPED | NL | 4991_25754 | XABTOR678278 | 1 | 86008383 | 1
04/29/2016 | SHIPPED | AT | 5099_26185 | XABTOR697793 | 1 | 86008383 | 1
05/10/2016 | SHIPPED | NL | BTS_86008383_01_E_16W19 | XABTOR703614 | 1 | 86008383 | 1
02/03/2016 | SHIPPED | AT | 4706_24348 | XABTOR658177 | 1 | 86009243 | 1
02/01/2016 | SHIPPED | AT | 4706_24348 | XABTOR657023 | 1 | 86009243 | 1
04/28/2016 | SHIPPED | AT | 5082_26213 | XABTOR696597 | 1 | 86003208-01 | 1
04/29/2016 | SHIPPED | AT | 5109_26219 | XABTOR698083 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25581 | XABTOR688303 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25581 | XABTOR688353 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687703 | 1 | 86003208-01 | 1
04/14/2016 | SHIPPED | AT | 4941_25620 | XABTOR688989 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687486 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687716 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687886 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687218 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692605 | 1 | 86003208-01 | 1
04/22/2016 | SHIPPED | AT | 5082_26213 | XABTOR693718 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687702 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687018 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685110 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692607 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692514 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692262 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692264 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685058 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685441 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692559 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25579 | XABTOR688498 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4971_25578 | XABTOR688551 | 1 | 86003208-01 | 1
04/22/2016 | SHIPPED | AT | 5082_26213 | XABTOR693648 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4938_25630 | XABTOR687021 | 1 | 86003208-01 | 1
04/29/2016 | SHIPPED | AT | 5109_26219 | XABTOR698084 | 1 | 86003208-01 | 1
04/19/2016 | SHIPPED | AT | 5001_25864 | XABTOR691809 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685057 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692350 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687406 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692309 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687285 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692583 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692608 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4941_25620 | XABTOR688614 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687726 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687776 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692406 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25579 | XABTOR688462 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25581 | XABTOR688469 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685510 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687484 | 1 | 86003208-01 | 1
04/15/2016 | SHIPPED | AT | 4941_25619 | XABTOR689624 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692407 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685290 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692410 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692412 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687413 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5019_25841 | XABTOR692893 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4971_25578 | XABTOR688549 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5019_25841 | XABTOR692805 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4938_25630 | XABTOR688697 | 1 | 86003208-01 | 1
04/14/2016 | SHIPPED | AT | 4941_25620 | XABTOR688988 | 1 | 86003208-01 | 1
04/22/2016 | SHIPPED | AT | 5082_26213 | XABTOR693651 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687492 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR684993 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685525 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692552 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692302 | 1 | 86003208-01 | 1
05/02/2016 | SHIPPED | AT | 5109_26219 | XABTOR698451 | 1 | 86003208-01 | 1
04/19/2016 | SHIPPED | AT | 5001_25864 | XABTOR691806 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687494 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4938_25630 | XABTOR687126 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687365 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692263 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687740 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685351 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687372 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5019_25841 | XABTOR692935 | 1 | 86003208-01 | 1
05/04/2016 | SHIPPED | AT | 5001_25864 | XABTOR700255 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687606 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685499 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692554 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5019_25841 | XABTOR692936 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5004_25766 | XABTOR692937 | 1 | 86003208-01 | 1
04/27/2016 | SHIPPED | AT | 5082_26213 | XABTOR696445 | 1 | 86003208-01 | 1
04/29/2016 | SHIPPED | AT | 5109_26219 | XABTOR698134 | 1 | 86003208-01 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703907 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685550 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700441 | 1 | 86004102 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693594 | 1 | 86004102 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690243 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4942_25398 | XABTOR690082 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685546 | 1 | 86004102 | 1
03/21/2016 | SHIPPED | SG | 4931_25845 | XABTOR676787 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686082 | 1 | 86004102 | 1
04/25/2016 | SHIPPED | AT | 5047_25950 | XABTOR695040 | 1 | 86004102 | 1
05/10/2016 | SHIPPED | NL | 5047_25926 | XABTOR703016 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703877 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700970 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693416 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693459 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4904_26033 | XABTOR691176 | 1 | 86004102 | 1
04/20/2016 | SHIPPED | NL | 4975_25596 | XABTOR692297 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689063 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689065 | 1 | 86004102 | 1
05/10/2016 | SHIPPED | NL | 5047_25926 | XABTOR703454 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688861 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704512 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693315 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR688914 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4904_26033 | XABTOR691386 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685543 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693412 | 1 | 86004102 | 1
03/22/2016 | SHIPPED | SG | 4931_25845 | XABTOR677843 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677875 | 1 | 86004102 | 1
04/27/2016 | SHIPPED | AT | 4903_25252 | XABTOR696286 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703905 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685549 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690164 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704577 | 1 | 86004102 | 1
05/10/2016 | SHIPPED | NL | 5047_25926 | XABTOR703030 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690028 | 1 | 86004102 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690270 | 1 | 86004102 | 1
05/10/2016 | SHIPPED | NL | 5047_25926 | XABTOR703438 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689067 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685545 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689114 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689196 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689239 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690132 | 1 | 86004102 | 1
04/26/2016 | SHIPPED | AT | 5062_26045 | XABTOR695387 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4903_25252 | XABTOR689800 | 1 | 86004102 | 1
03/21/2016 | SHIPPED | SG | 4931_25845 | XABTOR676789 | 1 | 86004102 | 1
04/09/2016 | SHIPPED | AT | 4942_25399 | XABTOR686793 | 1 | 86004102 | 1
03/22/2016 | SHIPPED | SG | 4931_25845 | XABTOR677840 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677922 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703930 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689066 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689300 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689302 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4893_25209 | XABTOR685590 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677877 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703935 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690166 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704546 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693324 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677924 | 1 | 86004102 | 1
11/25/2015 | SHIPPED | NL | 4683_24140 | XABTOR631060 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4989_25672 | XABTOR691295 | 1 | 86004102 | 1
04/25/2016 | SHIPPED | AT | 4980_26410 | XABTOR694853 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703929 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689195 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693275 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677923 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4904_26033 | XABTOR691296 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700663 | 1 | 86004102 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693732 | 1 | 86004102 | 1
04/09/2016 | SHIPPED | AT | 4942_25399 | XABTOR686746 | 1 | 86004102 | 1
05/06/2016 | SHIPPED | NL | 4753_24610 | XABTOR701482 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689301 | 1 | 86004102 | 1
03/22/2016 | SHIPPED | SG | 4931_25845 | XABTOR677842 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677925 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25947 | XABTOR700850 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690130 | 1 | 86004102 | 1
04/25/2016 | SHIPPED | AT | 5062_26045 | XABTOR695042 | 1 | 86004102 | 1
04/25/2016 | SHIPPED | AT | 5062_26045 | XABTOR695043 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689062 | 1 | 86004102 | 1
04/20/2016 | SHIPPED | AT | 3846_18931 | XABTOR692271 | 1 | 86010993 | 1
05/02/2016 | SHIPPED | AT | 3846_18931 | XABTOR698387 | 1 | 86010993 | 1
04/12/2016 | SHIPPED | AT | 3844_18929 | XABTOR688042 | 1 | 86010993 | 1
04/08/2016 | SHIPPED | AT | 3844_18929 | XABTOR686691 | 1 | 86010993 | 1
04/19/2016 | SHIPPED | AT | 3846_18931 | XABTOR691834 | 1 | 86010993 | 1
04/19/2016 | SHIPPED | AT | 3846_18931 | XABTOR691691 | 1 | 86010993 | 1
05/06/2016 | SHIPPED | AT | 3846_18931 | XABTOR701419 | 1 | 86010993 | 1
04/11/2016 | SHIPPED | AT | 3844_18929 | XABTOR686893 | 1 | 86010993 | 1
05/11/2016 | SHIPPED | AT | 3846_18931 | XABTOR704215 | 1 | 86010993 | 1
04/08/2016 | SHIPPED | AT | 3844_18929 | XABTOR686690 | 1 | 86010993 | 1
04/19/2016 | SHIPPED | AT | 3846_18931 | XABTOR691394 | 1 | 86010993 | 1
04/12/2016 | SHIPPED | AT | 3844_18929 | XABTOR688005 | 1 | 86010993 | 1
04/04/2016 | SHIPPED | AT | 3844_18929 | XABTOR684016 | 1 | 86010993 | 1
04/09/2016 | SHIPPED | AT | 3844_18929 | XABTOR686774 | 1 | 86010993 | 1
04/12/2016 | SHIPPED | AT | 3844_18929 | XABTOR688025 | 1 | 86010993 | 1
04/20/2016 | SHIPPED | AT | 3846_18931 | XABTOR692269 | 1 | 86010993 | 1
04/16/2016 | SHIPPED | AT | 3846_18931 | XABTOR690337 | 1 | 86010993 | 1
04/11/2016 | SHIPPED | AT | 3844_18929 | XABTOR686895 | 1 | 86010993 | 1
04/13/2016 | SHIPPED | AT | 3844_18929 | XABTOR688501 | 1 | 86010993 | 1
04/19/2016 | SHIPPED | AT | 3846_18931 | XABTOR691977 | 1 | 86010993 | 1
04/11/2016 | SHIPPED | AT | 3844_18929 | XABTOR686894 | 1 | 86010993 | 1
04/21/2016 | SHIPPED | AT | 3846_18931 | XABTOR692863 | 1 | 86010993 | 1
04/12/2016 | SHIPPED | AT | 3844_18929 | XABTOR687741 | 1 | 86010993 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700345 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698462 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_25622 | XABTOR698832 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699696 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699697 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700016 | 1 | 86011506 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702252 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698639 | 1 | 86011506 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700777 | 1 | 86011506 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702050 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700153 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700177 | 1 | 86011506 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700976 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699455 | 1 | 86011506 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702681 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_25622 | XABTOR698837 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699145 | 1 | 86011506 | 1
04/21/2016 | SHIPPED | AT | 4767_25622 | XABTOR692900 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699316 | 1 | 86011506 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702254 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699695 | 1 | 86011506 | 1
05/06/2016 | SHIPPED | AT | 4767_24666 | XABTOR701191 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699322 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698851 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_25622 | XABTOR699151 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698640 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699883 | 1 | 86011506 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700780 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699101 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700176 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700344 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699106 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699292 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699635 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700017 | 1 | 86011506 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702051 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699146 | 1 | 86011506 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702722 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24667 | XABTOR698578 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_25622 | XABTOR698642 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698644 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699880 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699882 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699147 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699313 | 1 | 86011506 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702723 | 1 | 86011506 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702028 | 1 | 86011506 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702029 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698853 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699870 | 1 | 86011506 | 1
05/10/2016 | SHIPPED | AT | 4767_25779 | XABTOR703535 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699148 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699291 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700020 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700154 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700254 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698214 | 1 | 86011506 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702130 | 1 | 86011506 | 1
02/09/2016 | SHIPPED | AT | 4875_25115 | XABTOR660370 | 1 | 86003678 | 1
05/10/2016 | SHIPPED | AT | 5225_26590 | XABTOR703660 | 1 | 86003678 | 1
05/09/2016 | SHIPPED | AT | 5225_26590 | XABTOR702819 | 1 | 86003678 | 1
05/06/2016 | SHIPPED | AT | 5224_26588 | XABTOR701256 | 1 | 86003678 | 1
11/04/2015 | SHIPPED | AT | 4015_23979 | XABTOR623851 | 1 | 86003678 | 1
10/14/2015 | SHIPPED | AT | 4267_22104 | XABTOR617504 | 1 | 86003678 | 1
05/05/2015 | SHIPPED | AT | 4267_22104 | XABTOR552435 | 1 | 86003678 | 1
10/14/2015 | SHIPPED | AT | 4267_22104 | XABTOR617503 | 1 | 86003678 | 1
11/04/2015 | SHIPPED | AT | 4267_22104 | XABTOR623938 | 1 | 86003678 | 1
02/09/2016 | SHIPPED | AT | 4874_25112 | XABTOR660327 | 1 | 86003678 | 1
05/03/2015 | SHIPPED | AT | 4267_22104 | XABTOR551926 | 1 | 86003678 | 1
11/04/2015 | SHIPPED | AT | 4015_23979 | XABTOR623807 | 1 | 86003678 | 1
05/05/2015 | SHIPPED | AT | 4267_22104 | XABTOR552429 | 1 | 86003678 | 1
02/09/2016 | SHIPPED | AT | 4875_25115 | XABTOR660625 | 1 | 86003678 | 1
10/02/2015 | SHIPPED | AT | 3685_23436 | XABTOR612393 | 1 | 86003678 | 1
02/09/2016 | SHIPPED | AT | 4875_25115 | XABTOR660619 | 1 | 86003678 | 1
11/03/2015 | SHIPPED | AT | 4015_23979 | XABTOR623574 | 1 | 86003678 | 1
02/09/2016 | SHIPPED | AT | 4874_25112 | XABTOR660189 | 1 | 86003678 | 1
02/05/2016 | SHIPPED | AT | 4876_25117 | XABTOR659187 | 1 | 86003678 | 1
05/09/2016 | SHIPPED | AT | 5224_26588 | XABTOR702266 | 1 | 86003678 | 1
05/11/2016 | SHIPPED | AT | 5224_26588 | XABTOR703781 | 1 | 86003678 | 1
02/08/2016 | SHIPPED | AT | 4873_25110 | XABTOR659710 | 1 | 86003678 | 1
02/08/2016 | SHIPPED | AT | 4874_25112 | XABTOR659779 | 1 | 86003678 | 1
10/02/2015 | SHIPPED | AT | 3685_23436 | XABTOR612414 | 1 | 86003678 | 1
05/09/2016 | SHIPPED | AT | 5225_26590 | XABTOR702260 | 1 | 86003678 | 1
02/05/2016 | SHIPPED | AT | 4873_25110 | XABTOR659338 | 1 | 86003678 | 1
05/03/2015 | SHIPPED | AT | 4267_22104 | XABTOR551925 | 1 | 86003678 | 1
02/05/2016 | SHIPPED | AT | 4876_25117 | XABTOR659188 | 1 | 86003678 | 1
02/08/2016 | SHIPPED | AT | 4873_25110 | XABTOR659741 | 1 | 86003678 | 1
05/09/2016 | SHIPPED | AT | 5225_26590 | XABTOR702407 | 1 | 86003678 | 1
11/04/2015 | SHIPPED | AT | 4015_23979 | XABTOR623809 | 1 | 86003678 | 1
02/09/2016 | SHIPPED | AT | 4874_25112 | XABTOR660237 | 1 | 86003678 | 1
02/06/2016 | SHIPPED | AT | 4873_25110 | XABTOR659631 | 1 | 86003678 | 1
05/03/2016 | SHIPPED | AT | 5224_26588 | XABTOR699100 | 1 | 86003678 | 1
04/20/2016 | SHIPPED | AT | 4980_25744 | XABTOR692139 | 1 | 86003986 | 1
11/17/2015 | SHIPPED | NL | 4018_20050 | XABTOR627702 | 1 | 86004453 | 1
12/09/2015 | SHIPPED | SG | 3836_18921 | XABTOR635176 | 1 | 86004453 | 1
11/19/2015 | SHIPPED | NL | 4018_20050 | XABTOR628551 | 1 | 86004453 | 1
12/10/2015 | SHIPPED | SG | 3836_18921 | XABTOR635909 | 1 | 86004453 | 1
12/14/2015 | SHIPPED | NL | 4018_20050 | XABTOR636957 | 1 | 86004453 | 1
12/04/2015 | SHIPPED | SG | 3836_18921 | XABTOR633431 | 1 | 86004453 | 1
11/17/2015 | SHIPPED | NL | 4018_20050 | XABTOR627658 | 1 | 86004453 | 1
12/04/2015 | SHIPPED | SG | 3836_18921 | XABTOR633482 | 1 | 86004453 | 1
12/14/2015 | SHIPPED | NL | 4018_20050 | XABTOR636955 | 1 | 86004453 | 1
12/09/2015 | SHIPPED | SG | 3836_18921 | XABTOR635190 | 1 | 86004453 | 1
12/07/2015 | SHIPPED | SG | 3836_18921 | XABTOR634018 | 1 | 86004453 | 1
12/08/2015 | SHIPPED | SG | 3836_18921 | XABTOR634586 | 1 | 86004453 | 1
12/10/2015 | SHIPPED | SG | 3836_18921 | XABTOR635876 | 1 | 86004453 | 1
12/10/2015 | SHIPPED | NL | 4018_20050 | XABTOR635911 | 1 | 86004453 | 1
11/18/2015 | SHIPPED | NL | 4018_20050 | XABTOR628028 | 1 | 86004453 | 1
12/14/2015 | SHIPPED | NL | 4018_20050 | XABTOR636961 | 1 | 86004453 | 1
12/04/2015 | SHIPPED | SG | 3836_18921 | XABTOR633483 | 1 | 86004453 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697581 | 1 | 86007600 | 1
04/28/2016 | SHIPPED | SG | 4769_25780 | XABTOR696776 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697583 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697573 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697551 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697569 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697572 | 1 | 86007600 | 1
04/28/2016 | SHIPPED | SG | 4769_25780 | XABTOR696753 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697552 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697368 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697367 | 1 | 86007600 | 1
04/28/2016 | SHIPPED | SG | 4769_24673 | XABTOR696749 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697582 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697366 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697364 | 1 | 86007600 | 1
04/29/2016 | SHIPPED | SG | 4769_25780 | XABTOR697570 | 1 | 86007600 | 1
05/11/2016 | SHIPPED | AT | 4631_24176 | XABTOR704364 | 1 | 86009609 | 1
05/11/2016 | SHIPPED | AT | 4631_24176 | XABTOR704363 | 1 | 86009609 | 1
02/15/2016 | SHIPPED | AT | 4883_25356 | XABTOR663015 | 1 | 86009609 | 1
05/09/2016 | SHIPPED | AT | 4631_24173 | XABTOR702797 | 1 | 86009609 | 1
05/12/2016 | SHIPPED | AT | 4631_24176 | XABTOR705004 | 1 | 86009609 | 1
05/09/2016 | SHIPPED | AT | 4631_24173 | XABTOR702788 | 1 | 86009609 | 1
05/09/2016 | SHIPPED | AT | 4631_24173 | XABTOR702741 | 1 | 86009609 | 1
05/06/2016 | SHIPPED | AT | 4631_24173 | XABTOR701812 | 1 | 86009609 | 1
05/05/2016 | SHIPPED | AT | 4631_24173 | XABTOR700565 | 1 | 86009609 | 1
05/05/2016 | SHIPPED | AT | 4631_24173 | XABTOR700566 | 1 | 86009609 | 1
05/06/2016 | SHIPPED | AT | 4631_24173 | XABTOR701785 | 1 | 86009609 | 1
02/15/2016 | SHIPPED | AT | 4883_25356 | XABTOR663067 | 1 | 86009609 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697672 | 1 | 86010229 | 1
04/13/2016 | SHIPPED | AT | 4594_23789 | XABTOR688458 | 1 | 86006660 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR688152 | 1 | 86006660 | 1
04/12/2016 | SHIPPED | AT | 4567_23752 | XABTOR687780 | 1 | 86006660 | 1
03/17/2016 | SHIPPED | AT | 4675_24096 | XABTOR675841 | 1 | 86006660 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR688274 | 1 | 86006660 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR688114 | 1 | 86006660 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700470 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700472 | 1 | 86007619 | 1
05/04/2016 | SHIPPED | SG | 4769_25780 | XABTOR699872 | 1 | 86007619 | 1
04/28/2016 | SHIPPED | SG | 4769_24673 | XABTOR696750 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700567 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700569 | 1 | 86007619 | 1
05/04/2016 | SHIPPED | SG | 4769_25780 | XABTOR699935 | 1 | 86007619 | 1
05/04/2016 | SHIPPED | SG | 4769_25780 | XABTOR699871 | 1 | 86007619 | 1
05/04/2016 | SHIPPED | SG | 4769_25780 | XABTOR699873 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700463 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700450 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700568 | 1 | 86007619 | 1
05/04/2016 | SHIPPED | SG | 4769_25780 | XABTOR699874 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700464 | 1 | 86007619 | 1
05/04/2016 | SHIPPED | SG | 4769_25780 | XABTOR699936 | 1 | 86007619 | 1
05/05/2016 | SHIPPED | SG | 4769_25780 | XABTOR700452 | 1 | 86007619 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690703 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690760 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688463 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690704 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690757 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688366 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688474 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688286 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688288 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690433 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690818 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688285 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690482 | 1 | 86009246 | 1
04/16/2016 | SHIPPED | AT | 4917_25293 | XABTOR690312 | 1 | 86009246 | 1
04/16/2016 | SHIPPED | AT | 4917_25293 | XABTOR690313 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690652 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690702 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690762 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690763 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688362 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690815 | 1 | 86009246 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688277 | 1 | 86009246 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690485 | 1 | 86009246 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR682820 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR682822 | 1 | 86009488 | 1
03/30/2016 | SHIPPED | AT | 4932_25379 | XABTOR681540 | 1 | 86009488 | 1
04/18/2016 | SHIPPED | AT | 4932_25379 | XABTOR690637 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695370 | 1 | 86009488 | 1
04/04/2016 | SHIPPED | AT | 4965_25534 | XABTOR683668 | 1 | 86009488 | 1
03/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR679854 | 1 | 86009488 | 1
04/19/2016 | SHIPPED | AT | 4932_25379 | XABTOR691393 | 1 | 86009488 | 1
03/25/2016 | SHIPPED | AT | 4932_25379 | XABTOR679342 | 1 | 86009488 | 1
04/14/2016 | SHIPPED | AT | 4932_25379 | XABTOR689115 | 1 | 86009488 | 1
03/24/2016 | SHIPPED | AT | 4932_25379 | XABTOR678842 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR683299 | 1 | 86009488 | 1
04/02/2016 | SHIPPED | AT | 4965_25534 | XABTOR683424 | 1 | 86009488 | 1
04/14/2016 | SHIPPED | AT | 4932_25379 | XABTOR689116 | 1 | 86009488 | 1
03/23/2016 | SHIPPED | AT | 4932_25379 | XABTOR678291 | 1 | 86009488 | 1
04/02/2016 | SHIPPED | AT | 4965_25534 | XABTOR683425 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695376 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR683158 | 1 | 86009488 | 1
03/31/2016 | SHIPPED | AT | 4965_25534 | XABTOR682458 | 1 | 86009488 | 1
04/18/2016 | SHIPPED | AT | 4932_25379 | XABTOR690635 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR683242 | 1 | 86009488 | 1
04/02/2016 | SHIPPED | AT | 4965_25534 | XABTOR683428 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695378 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR683241 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695373 | 1 | 86009488 | 1
03/23/2016 | SHIPPED | AT | 4932_25379 | XABTOR678060 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695372 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695374 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695379 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695381 | 1 | 86009488 | 1
03/31/2016 | SHIPPED | AT | 4965_25534 | XABTOR682606 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR682818 | 1 | 86009488 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695176 | 1 | 86009488 | 1
03/24/2016 | SHIPPED | AT | 4932_25379 | XABTOR678846 | 1 | 86009488 | 1
03/23/2016 | SHIPPED | AT | 4932_25379 | XABTOR678083 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR682819 | 1 | 86009488 | 1
11/03/2015 | SHIPPED | AT | 3685_23881 | XABTOR623491 | 1 | 86003680 | 1
11/04/2015 | SHIPPED | AT | 3685_23881 | XABTOR623989 | 1 | 86003680 | 1
11/03/2015 | SHIPPED | AT | 3685_23881 | XABTOR623665 | 1 | 86003680 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703038 | 1 | 86004101 | 1
04/20/2016 | SHIPPED | AT | 4980_26410 | XABTOR692267 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674658 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675176 | 1 | 86004101 | 1
11/25/2015 | SHIPPED | NL | 4683_24140 | XABTOR631018 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703029 | 1 | 86004101 | 1
05/02/2016 | SHIPPED | AT | 5047_25947 | XABTOR698174 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689109 | 1 | 86004101 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693467 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693803 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689112 | 1 | 86004101 | 1
04/16/2016 | SHIPPED | AT | 4942_25398 | XABTOR690316 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674723 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674741 | 1 | 86004101 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693460 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4942_25398 | XABTOR688744 | 1 | 86004101 | 1
05/05/2016 | SHIPPED | AT | 5047_25947 | XABTOR700680 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693599 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685504 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690134 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689780 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689791 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4903_25252 | XABTOR689798 | 1 | 86004101 | 1
05/05/2016 | SHIPPED | AT | 5047_25947 | XABTOR700681 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685554 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689173 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685386 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4927_25350 | XABTOR685497 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688862 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689005 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689012 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4927_25350 | XABTOR685553 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690165 | 1 | 86004101 | 1
04/09/2016 | SHIPPED | AT | 4942_25399 | XABTOR686789 | 1 | 86004101 | 1
04/09/2016 | SHIPPED | AT | 4942_25399 | XABTOR686791 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685046 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702157 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675183 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 5047_25926 | XABTOR701737 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 5047_25926 | XABTOR701739 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693598 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693813 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693830 | 1 | 86004101 | 1
04/16/2016 | SHIPPED | AT | 4942_25398 | XABTOR690239 | 1 | 86004101 | 1
04/18/2016 | SHIPPED | AT | 4989_25672 | XABTOR690420 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675180 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703025 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 5047_25926 | XABTOR701499 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689554 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689801 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702161 | 1 | 86004101 | 1
04/26/2016 | SHIPPED | AT | 5019_25842 | XABTOR695398 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675182 | 1 | 86004101 | 1
11/25/2015 | SHIPPED | NL | 4683_24140 | XABTOR631019 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689376 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675177 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689008 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689009 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690135 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690167 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689622 | 1 | 86004101 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR685987 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675181 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689999 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689106 | 1 | 86004101 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690315 | 1 | 86004101 | 1
04/18/2016 | SHIPPED | AT | 4989_25672 | XABTOR690817 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 5047_25926 | XABTOR701732 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690131 | 1 | 86004101 | 1
04/26/2016 | SHIPPED | AT | 5019_25842 | XABTOR695406 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685053 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702155 | 1 | 86004101 | 1
04/29/2016 | SHIPPED | AT | 5047_25947 | XABTOR698112 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693595 | 1 | 86004101 | 1
04/26/2016 | SHIPPED | AT | 5019_25842 | XABTOR695552 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688634 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703028 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 4980_26410 | XABTOR693754 | 1 | 86004101 | 1
09/27/2015 | SHIPPED | AT | 4466_23599 | XABTOR610047 | 1 | 86002489 | 1
09/29/2015 | SHIPPED | AT | 4466_23599 | XABTOR611134 | 1 | 86002489 | 1
09/30/2015 | SHIPPED | AT | 4466_23599 | XABTOR611207 | 1 | 86002489 | 1
09/28/2015 | SHIPPED | AT | 4466_23599 | XABTOR610593 | 1 | 86002489 | 1
08/25/2015 | SHIPPED | AT | 3674_18450 | XABTOR596485 | 1 | 86006045 | 1
08/25/2015 | SHIPPED | AT | 3674_18450 | XABTOR596496 | 1 | 86006045 | 1
08/24/2015 | SHIPPED | AT | 3674_18450 | XABTOR596130 | 1 | 86006045 | 1
08/27/2015 | SHIPPED | AT | 3676_18451 | XABTOR597869 | 1 | 86006045 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596129 | 1 | 86006045 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596161 | 1 | 86006045 | 1
08/26/2015 | SHIPPED | AT | 3674_18450 | XABTOR597017 | 1 | 86006045 | 1
08/24/2015 | SHIPPED | AT | 3674_18450 | XABTOR596134 | 1 | 86006045 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596155 | 1 | 86006045 | 1
08/27/2015 | SHIPPED | AT | 3676_18451 | XABTOR597871 | 1 | 86006045 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596167 | 1 | 86006045 | 1
08/26/2015 | SHIPPED | AT | 3674_18450 | XABTOR597018 | 1 | 86006045 | 1
02/09/2016 | SHIPPED | AT | 3993_22257 | XABTOR660637 | 1 | 86007204 | 1
10/01/2015 | SHIPPED | AT | 3846_22247 | XABTOR611835 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661088 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661092 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661307 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611744 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | AT | 3993_22257 | XABTOR660876 | 1 | 86007204 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659756 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | AT | 3993_22257 | XABTOR660647 | 1 | 86007204 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR697229 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660524 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661046 | 1 | 86007204 | 1
02/12/2016 | SHIPPED | AT | 3992_22256 | XABTOR662390 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611710 | 1 | 86007204 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659757 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660692 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 3731_21742 | XABTOR661090 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660672 | 1 | 86007204 | 1
02/08/2016 | SHIPPED | AT | 3993_22257 | XABTOR659872 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660673 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | AT | 3993_22257 | XABTOR660234 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | AT | 3992_22256 | XABTOR660645 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611745 | 1 | 86007204 | 1
02/09/2016 | SHIPPED | NL | 3731_21742 | XABTOR660674 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611743 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611750 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661181 | 1 | 86007204 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR696996 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611713 | 1 | 86007204 | 1
02/12/2016 | SHIPPED | AT | 3992_22256 | XABTOR662086 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611632 | 1 | 86007204 | 1
10/01/2015 | SHIPPED | AT | 3846_22247 | XABTOR611832 | 1 | 86007204 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR697231 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611631 | 1 | 86007204 | 1
02/10/2016 | SHIPPED | NL | 4015_21526 | XABTOR661094 | 1 | 86007204 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR697258 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3846_22247 | XABTOR611711 | 1 | 86007204 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR697230 | 1 | 86007204 | 1
04/28/2016 | SHIPPED | NL | 4018_21725 | XABTOR697030 | 1 | 86007204 | 1
09/30/2015 | SHIPPED | AT | 3844_22248 | XABTOR611714 | 1 | 86007204 | 1
02/08/2016 | SHIPPED | AT | 3992_22256 | XABTOR659818 | 1 | 86007204 | 1
02/08/2016 | SHIPPED | AT | 3993_22257 | XABTOR660108 | 1 | 86007204 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691709 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691798 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691800 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691868 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691651 | 1 | 86010927 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692051 | 1 | 86010927 | 1
02/02/2016 | SHIPPED | AT | 4840_24954 | XABTOR657586 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691875 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691804 | 1 | 86010927 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692136 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691710 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691645 | 1 | 86010927 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692138 | 1 | 86010927 | 1
04/20/2016 | SHIPPED | AT | 5049_25966 | XABTOR692073 | 1 | 86010927 | 1
02/03/2016 | SHIPPED | AT | 4840_24954 | XABTOR657755 | 1 | 86010927 | 1
04/19/2016 | SHIPPED | AT | 5049_25966 | XABTOR691805 | 1 | 86010927 | 1
02/01/2016 | SHIPPED | AT | 4840_24969 | XABTOR657027 | 1 | 86010927 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697669 | 1 | 86010229 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697670 | 1 | 86010229 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697668 | 1 | 86010229 | 1
05/12/2016 | SHIPPED | AT | 5026_25883 | XABTOR705058 | 1 | 86010907 | 1
05/05/2016 | SHIPPED | AT | 5026_25883 | XABTOR701011 | 1 | 86010907 | 1
05/02/2016 | SHIPPED | AT | 5099_26187 | XABTOR698365 | 1 | 86012210 | 1
04/29/2016 | SHIPPED | AT | 5099_26187 | XABTOR698128 | 1 | 86012210 | 1
05/02/2016 | SHIPPED | AT | 5099_26187 | XABTOR698364 | 1 | 86012210 | 1
04/20/2016 | SHIPPED | AT | 4988_25772 | XABTOR692480 | 1 | 86012210 | 1
05/10/2016 | SHIPPED | AT | 4767_25779 | XABTOR703537 | 1 | 86011506 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702131 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699318 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700018 | 1 | 86011506 | 1
05/10/2016 | SHIPPED | AT | 4767_25779 | XABTOR702894 | 1 | 86011506 | 1
05/03/2016 | SHIPPED | AT | 4767_25622 | XABTOR699149 | 1 | 86011506 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700253 | 1 | 86011506 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702682 | 1 | 86011506 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698449 | 1 | 86011506 | 1
05/12/2016 | SHIPPED | NL | BTS_86011588_01_E_16W18 | XABTOR705167 | 1 | 86011588 | 1
05/12/2016 | SHIPPED | NL | BTS_86011588_01_E_16W18 | XABTOR705193 | 1 | 86011588 | 1
05/12/2016 | SHIPPED | NL | BTS_86011588_01_E_16W18 | XABTOR705172 | 1 | 86011588 | 1
05/09/2016 | SHIPPED | AT | 4883_25858 | XABTOR702597 | 1 | 86011707 | 1
05/09/2016 | SHIPPED | AT | 4883_25858 | XABTOR702419 | 1 | 86011707 | 1
05/09/2016 | SHIPPED | AT | 4883_25858 | XABTOR702392 | 1 | 86011707 | 1
05/09/2016 | SHIPPED | AT | 4883_25858 | XABTOR702394 | 1 | 86011707 | 1
03/31/2016 | SHIPPED | AT | 4883_25858 | XABTOR682622 | 1 | 86011707 | 1
04/21/2016 | SHIPPED | NL | 5080_26209 | XABTOR693337 | 1 | 86003208-02 | 1
03/29/2016 | SHIPPED | NL | 4939_25629 | XABTOR680901 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691415 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691416 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693708 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690434 | 1 | 86003208-02 | 1
11/20/2015 | SHIPPED | NL | 4683_24143 | XABTOR628811 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691492 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 5027_26120 | XABTOR692326 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693752 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690701 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687843 | 1 | 86003208-02 | 1
04/11/2016 | SHIPPED | NL | 5027_26120 | XABTOR687418 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24143 | XABTOR628597 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690901 | 1 | 86003208-02 | 1
04/14/2016 | SHIPPED | NL | 5027_26120 | XABTOR689202 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 4940_25628 | XABTOR691689 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691757 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690572 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687845 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR688064 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 4975_25597 | XABTOR692578 | 1 | 86003208-02 | 1
11/19/2015 | SHIPPED | NL | 4683_24142 | XABTOR628549 | 1 | 86003208-02 | 1
04/13/2016 | SHIPPED | NL | 5027_26120 | XABTOR688530 | 1 | 86003208-02 | 1
04/22/2016 | SHIPPED | NL | 5080_26209 | XABTOR693774 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691829 | 1 | 86003208-02 | 1
04/18/2016 | SHIPPED | NL | 5027_26120 | XABTOR690700 | 1 | 86003208-02 | 1
04/12/2016 | SHIPPED | NL | 5027_26120 | XABTOR687849 | 1 | 86003208-02 | 1
04/11/2016 | SHIPPED | NL | 5027_26120 | XABTOR687049 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 4975_25597 | XABTOR692674 | 1 | 86003208-02 | 1
04/19/2016 | SHIPPED | NL | 5027_26120 | XABTOR691504 | 1 | 86003208-02 | 1
04/20/2016 | SHIPPED | NL | 5027_26120 | XABTOR692270 | 1 | 86003208-02 | 1
04/07/2016 | SHIPPED | AT | 4894_25210 | XABTOR686011 | 1 | 86004098 | 1
04/07/2016 | SHIPPED | AT | 4894_25210 | XABTOR686002 | 1 | 86004098 | 1
04/08/2016 | SHIPPED | AT | 4894_25210 | XABTOR686374 | 1 | 86004098 | 1
05/12/2016 | SHIPPED | AT | BTS_86004098_01_A_16W18 | XABTOR705050 | 1 | 86004098 | 1
04/07/2016 | SHIPPED | AT | 4894_25210 | XABTOR686004 | 1 | 86004098 | 1
04/08/2016 | SHIPPED | AT | 4894_25210 | XABTOR686377 | 1 | 86004098 | 1
04/07/2016 | SHIPPED | AT | 4894_25210 | XABTOR686012 | 1 | 86004098 | 1
05/12/2016 | SHIPPED | AT | BTS_86004098_01_A_16W18 | XABTOR705053 | 1 | 86004098 | 1
04/08/2016 | SHIPPED | AT | 3733_18264 | XABTOR686369 | 1 | 86005420 | 1
04/08/2016 | SHIPPED | AT | 3733_18264 | XABTOR686305 | 1 | 86005420 | 1
12/11/2015 | SHIPPED | NL | 4018_20050 | XABTOR636509 | 1 | 86005420 | 1
04/15/2016 | SHIPPED | AT | 4932_25379 | XABTOR689699 | 1 | 86005420 | 1
12/11/2015 | SHIPPED | NL | 4018_20050 | XABTOR636532 | 1 | 86005420 | 1
04/13/2016 | SHIPPED | AT | 3733_18264 | XABTOR688710 | 1 | 86005420 | 1
04/13/2016 | SHIPPED | AT | 3733_18264 | XABTOR688721 | 1 | 86005420 | 1
04/11/2016 | SHIPPED | AT | 4932_25379 | XABTOR686995 | 1 | 86005420 | 1
03/31/2016 | SHIPPED | AT | 4965_25534 | XABTOR682599 | 1 | 86005420 | 1
12/11/2015 | SHIPPED | NL | 4018_20050 | XABTOR636526 | 1 | 86005420 | 1
03/31/2016 | SHIPPED | AT | 4965_25534 | XABTOR682214 | 1 | 86005420 | 1
03/30/2016 | SHIPPED | AT | 4965_25534 | XABTOR681538 | 1 | 86005420 | 1
12/11/2015 | SHIPPED | NL | 4018_20050 | XABTOR636508 | 1 | 86005420 | 1
04/04/2016 | SHIPPED | AT | 4965_25534 | XABTOR683670 | 1 | 86005420 | 1
04/11/2016 | SHIPPED | NL | 4580_23765 | XABTOR687419 | 1 | 86009169 | 1
04/06/2016 | SHIPPED | AT | 4582_23767 | XABTOR685501 | 1 | 86009169 | 1
04/11/2016 | SHIPPED | NL | 4580_23765 | XABTOR687425 | 1 | 86009169 | 1
04/11/2016 | SHIPPED | NL | 4580_23765 | XABTOR687424 | 1 | 86009169 | 1
04/21/2016 | SHIPPED | AT | 4571_23756 | XABTOR693349 | 1 | 86009169 | 1
04/26/2016 | SHIPPED | AT | 4589_23783 | XABTOR695189 | 1 | 86009169 | 1
04/06/2016 | SHIPPED | AT | 4582_23767 | XABTOR685507 | 1 | 86009169 | 1
04/21/2016 | SHIPPED | AT | 4568_23753 | XABTOR693155 | 1 | 86009169 | 1
04/06/2016 | SHIPPED | AT | 4582_23767 | XABTOR685115 | 1 | 86009169 | 1
04/16/2016 | SHIPPED | AT | 4697_24298 | XABTOR690272 | 1 | 86009207 | 1
04/29/2016 | SHIPPED | AT | 4698_24272 | XABTOR697580 | 1 | 86009207 | 1
04/29/2016 | SHIPPED | AT | 4698_24272 | XABTOR697585 | 1 | 86009207 | 1
03/01/2016 | SHIPPED | AT | 4697_24254 | XABTOR669148 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24269 | XABTOR696733 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24288 | XABTOR667502 | 1 | 86009207 | 1
04/23/2016 | SHIPPED | AT | 4697_24263 | XABTOR694413 | 1 | 86009207 | 1
03/01/2016 | SHIPPED | AT | 4697_24254 | XABTOR669336 | 1 | 86009207 | 1
03/08/2016 | SHIPPED | NL | 4697_24296 | XABTOR672366 | 1 | 86009207 | 1
02/17/2016 | SHIPPED | NL | 4697_24261 | XABTOR663989 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24271 | XABTOR696731 | 1 | 86009207 | 1
04/27/2016 | SHIPPED | AT | 4697_24301 | XABTOR696013 | 1 | 86009207 | 1
05/07/2016 | SHIPPED | AT | 4697_24264 | XABTOR701996 | 1 | 86009207 | 1
03/17/2016 | SHIPPED | AT | 3844_18929 | XABTOR675757 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24281 | XABTOR667500 | 1 | 86009207 | 1
05/11/2016 | SHIPPED | AT | 4697_24297 | XABTOR704361 | 1 | 86009207 | 1
02/02/2016 | SHIPPED | AT | 4685_24164 | XABTOR657195 | 1 | 86009207 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690241 | 1 | 86004102 | 1
03/21/2016 | SHIPPED | SG | 4931_25845 | XABTOR676788 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686147 | 1 | 86004102 | 1
05/03/2016 | SHIPPED | AT | 5047_25947 | XABTOR699644 | 1 | 86004102 | 1
04/18/2016 | SHIPPED | AT | 4989_25672 | XABTOR690902 | 1 | 86004102 | 1
04/20/2016 | SHIPPED | NL | 4975_25596 | XABTOR692299 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4942_25398 | XABTOR690030 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685572 | 1 | 86004102 | 1
04/26/2016 | SHIPPED | AT | 5062_26045 | XABTOR695389 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704514 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688687 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677874 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700662 | 1 | 86004102 | 1
05/10/2016 | SHIPPED | NL | 5047_25926 | XABTOR703267 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693321 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4942_25398 | XABTOR688690 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688691 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688859 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690077 | 1 | 86004102 | 1
05/06/2016 | SHIPPED | AT | 5047_25947 | XABTOR701644 | 1 | 86004102 | 1
05/06/2016 | SHIPPED | AT | 5047_25947 | XABTOR701645 | 1 | 86004102 | 1
04/22/2016 | SHIPPED | AT | 4980_26410 | XABTOR693555 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689110 | 1 | 86004102 | 1
03/21/2016 | SHIPPED | SG | 4931_25845 | XABTOR676797 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693272 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4989_25672 | XABTOR691297 | 1 | 86004102 | 1
04/25/2016 | SHIPPED | AT | 5047_25950 | XABTOR695044 | 1 | 86004102 | 1
05/10/2016 | SHIPPED | NL | 5047_25926 | XABTOR703015 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690029 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700707 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4942_25398 | XABTOR688767 | 1 | 86004102 | 1
03/23/2016 | SHIPPED | SG | 4931_25845 | XABTOR677876 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689303 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4904_26033 | XABTOR691409 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700975 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689579 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4942_25398 | XABTOR688692 | 1 | 86004102 | 1
04/18/2016 | SHIPPED | AT | 4989_25672 | XABTOR691047 | 1 | 86004102 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690242 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686005 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704511 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR688911 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR688913 | 1 | 86004102 | 1
05/03/2016 | SHIPPED | AT | 5047_25947 | XABTOR699643 | 1 | 86004102 | 1
05/02/2016 | SHIPPED | NL | 5005_25767 | XABTOR698415 | 1 | 86004102 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685552 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689064 | 1 | 86004102 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690318 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704544 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 5062_26045 | XABTOR693415 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686149 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688771 | 1 | 86004102 | 1
11/25/2015 | SHIPPED | NL | 4683_24140 | XABTOR631037 | 1 | 86004102 | 1
11/25/2015 | SHIPPED | NL | 4683_24140 | XABTOR631080 | 1 | 86004102 | 1
05/05/2016 | SHIPPED | AT | 5047_25957 | XABTOR700847 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703876 | 1 | 86004102 | 1
05/11/2016 | SHIPPED | SG | 5112_26227 | XABTOR703932 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690138 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704583 | 1 | 86004102 | 1
04/13/2016 | SHIPPED | AT | 4942_25398 | XABTOR688834 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4904_26033 | XABTOR691389 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689238 | 1 | 86004102 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690317 | 1 | 86004102 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689547 | 1 | 86004102 | 1
04/15/2016 | SHIPPED | AT | 4903_25252 | XABTOR689874 | 1 | 86004102 | 1
05/12/2016 | SHIPPED | SG | 5112_26227 | XABTOR704513 | 1 | 86004102 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693325 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686064 | 1 | 86004102 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686071 | 1 | 86004102 | 1
03/22/2016 | SHIPPED | SG | 4931_25845 | XABTOR677841 | 1 | 86004102 | 1
04/19/2016 | SHIPPED | AT | 4904_26033 | XABTOR691387 | 1 | 86004102 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596125 | 1 | 86006044 | 1
08/26/2015 | SHIPPED | AT | 3674_18450 | XABTOR597261 | 1 | 86006044 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596154 | 1 | 86006044 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596117 | 1 | 86006044 | 1
08/25/2015 | SHIPPED | AT | 3674_18450 | XABTOR596303 | 1 | 86006044 | 1
08/25/2015 | SHIPPED | AT | 3674_18450 | XABTOR596398 | 1 | 86006044 | 1
08/25/2015 | SHIPPED | AT | 3674_18450 | XABTOR596400 | 1 | 86006044 | 1
08/25/2015 | SHIPPED | AT | 3674_18450 | XABTOR596399 | 1 | 86006044 | 1
08/25/2015 | SHIPPED | AT | 3676_18451 | XABTOR596397 | 1 | 86006044 | 1
08/27/2015 | SHIPPED | AT | 3674_18450 | XABTOR597337 | 1 | 86006044 | 1
05/02/2016 | SHIPPED | AT | 5109_26219 | XABTOR698284 | 1 | 86003208-01 | 1
05/02/2016 | SHIPPED | AT | 5109_26219 | XABTOR698452 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687614 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685442 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692577 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5001_25864 | XABTOR692894 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5001_25864 | XABTOR692896 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25581 | XABTOR688514 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25581 | XABTOR688550 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4938_25630 | XABTOR688699 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR684992 | 1 | 86003208-01 | 1
04/30/2016 | SHIPPED | AT | 5109_26219 | XABTOR698139 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4971_25578 | XABTOR688292 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4972_25581 | XABTOR688356 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687607 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4938_25630 | XABTOR687003 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685066 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692418 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4938_25630 | XABTOR687288 | 1 | 86003208-01 | 1
04/14/2016 | SHIPPED | AT | 4941_25619 | XABTOR689578 | 1 | 86003208-01 | 1
04/21/2016 | SHIPPED | AT | 5004_25766 | XABTOR693004 | 1 | 86003208-01 | 1
04/14/2016 | SHIPPED | AT | 4941_25620 | XABTOR689010 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692300 | 1 | 86003208-01 | 1
05/02/2016 | SHIPPED | AT | 5109_26219 | XABTOR698285 | 1 | 86003208-01 | 1
04/11/2016 | SHIPPED | AT | 4971_25578 | XABTOR687485 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687717 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685377 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685524 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692260 | 1 | 86003208-01 | 1
04/22/2016 | SHIPPED | AT | 5082_26213 | XABTOR693650 | 1 | 86003208-01 | 1
04/12/2016 | SHIPPED | AT | 4971_25578 | XABTOR687715 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4941_25620 | XABTOR688698 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692174 | 1 | 86003208-01 | 1
04/14/2016 | SHIPPED | AT | 4941_25620 | XABTOR689170 | 1 | 86003208-01 | 1
04/06/2016 | SHIPPED | AT | 4893_25208 | XABTOR685296 | 1 | 86003208-01 | 1
04/20/2016 | SHIPPED | AT | 5001_25864 | XABTOR692555 | 1 | 86003208-01 | 1
04/13/2016 | SHIPPED | AT | 4971_25578 | XABTOR688402 | 1 | 86003208-01 | 1
04/26/2016 | SHIPPED | AT | 4982_25648 | XABTOR695188 | 1 | 86006051 | 1
04/29/2016 | SHIPPED | AT | 4982_26317 | XABTOR697605 | 1 | 86006051 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661439 | 1 | 86006051 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR697326 | 1 | 86006051 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR696703 | 1 | 86006051 | 1
04/25/2016 | SHIPPED | AT | 4982_25648 | XABTOR694897 | 1 | 86006051 | 1
02/12/2016 | SHIPPED | NL | 4016_25076 | XABTOR662527 | 1 | 86006051 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661314 | 1 | 86006051 | 1
02/12/2016 | SHIPPED | NL | 4016_25076 | XABTOR662517 | 1 | 86006051 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662673 | 1 | 86006051 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661484 | 1 | 86006051 | 1
02/12/2016 | SHIPPED | NL | 4016_25076 | XABTOR662529 | 1 | 86006051 | 1
04/27/2016 | SHIPPED | AT | 4982_25647 | XABTOR696118 | 1 | 86006051 | 1
04/25/2016 | SHIPPED | AT | 4982_25648 | XABTOR695046 | 1 | 86006051 | 1
02/12/2016 | SHIPPED | NL | 4016_25076 | XABTOR662516 | 1 | 86006051 | 1
04/27/2016 | SHIPPED | AT | 4982_25647 | XABTOR696310 | 1 | 86006051 | 1
04/28/2016 | SHIPPED | AT | 4982_25647 | XABTOR697321 | 1 | 86006051 | 1
04/25/2016 | SHIPPED | AT | 4982_25648 | XABTOR694898 | 1 | 86006051 | 1
04/29/2016 | SHIPPED | AT | 4982_26317 | XABTOR697602 | 1 | 86006051 | 1
04/29/2016 | SHIPPED | AT | 4982_25647 | XABTOR697606 | 1 | 86006051 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661400 | 1 | 86006051 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662695 | 1 | 86006051 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661408 | 1 | 86006051 | 1
04/26/2016 | SHIPPED | AT | 4982_25648 | XABTOR695386 | 1 | 86006051 | 1
04/29/2016 | SHIPPED | AT | 4982_25647 | XABTOR697609 | 1 | 86006051 | 1
04/29/2016 | SHIPPED | AT | 4982_25647 | XABTOR697610 | 1 | 86006051 | 1
04/25/2016 | SHIPPED | AT | 4982_25648 | XABTOR695047 | 1 | 86006051 | 1
02/12/2016 | SHIPPED | NL | 4016_25076 | XABTOR662472 | 1 | 86006051 | 1
04/26/2016 | SHIPPED | AT | 4982_25648 | XABTOR695306 | 1 | 86006051 | 1
02/10/2016 | SHIPPED | NL | 4016_21697 | XABTOR661271 | 1 | 86006051 | 1
04/26/2016 | SHIPPED | AT | 4982_25648 | XABTOR695187 | 1 | 86006051 | 1
02/12/2016 | SHIPPED | NL | 4016_25076 | XABTOR662487 | 1 | 86006051 | 1
02/15/2016 | SHIPPED | NL | 4016_25076 | XABTOR662770 | 1 | 86006051 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR687873 | 1 | 86006659 | 1
03/16/2016 | SHIPPED | AT | 4675_24096 | XABTOR675384 | 1 | 86006659 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR688044 | 1 | 86006659 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR687887 | 1 | 86006659 | 1
04/11/2016 | SHIPPED | AT | 4567_23752 | XABTOR687371 | 1 | 86006659 | 1
04/12/2016 | SHIPPED | AT | 4594_23789 | XABTOR688043 | 1 | 86006659 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664434 | 1 | 86009148 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR700185 | 1 | 86009148 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682355 | 1 | 86009148 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR700190 | 1 | 86009148 | 1
04/26/2016 | SHIPPED | AT | 4932_25379 | XABTOR695371 | 1 | 86009488 | 1
04/01/2016 | SHIPPED | AT | 4965_25534 | XABTOR682821 | 1 | 86009488 | 1
04/21/2016 | SHIPPED | AT | 4932_25379 | XABTOR692806 | 1 | 86009488 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR658049 | 1 | 86010991 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR657823 | 1 | 86010991 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR657961 | 1 | 86010991 | 1
04/21/2016 | SHIPPED | AT | 5049_25965 | XABTOR693165 | 1 | 86010991 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR657960 | 1 | 86010991 | 1
04/21/2016 | SHIPPED | AT | 5049_25965 | XABTOR693043 | 1 | 86010991 | 1
04/21/2016 | SHIPPED | AT | 5049_25965 | XABTOR693042 | 1 | 86010991 | 1
01/30/2016 | SHIPPED | AT | 4840_24968 | XABTOR656456 | 1 | 86010991 | 1
04/21/2016 | SHIPPED | AT | 5049_25965 | XABTOR693211 | 1 | 86010991 | 1
02/03/2016 | SHIPPED | AT | 4840_24968 | XABTOR657819 | 1 | 86010991 | 1
05/04/2016 | SHIPPED | AT | 5022_25874 | XABTOR699881 | 1 | 86011356 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691408 | 1 | 86011472 | 1
04/14/2016 | SHIPPED | AT | 4944_25405 | XABTOR688910 | 1 | 86011472 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691520 | 1 | 86011472 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691521 | 1 | 86011472 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691174 | 1 | 86011472 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691175 | 1 | 86011472 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691522 | 1 | 86011472 | 1
04/19/2016 | SHIPPED | AT | 4944_25405 | XABTOR691410 | 1 | 86011472 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702140 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25621 | XABTOR702986 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702334 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702253 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25621 | XABTOR702806 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR702891 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR703360 | 1 | 86011499 | 1
05/12/2016 | SHIPPED | AT | 4767_26251 | XABTOR705198 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702807 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702164 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702368 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702118 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25621 | XABTOR702729 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702611 | 1 | 86011499 | 1
05/11/2016 | SHIPPED | AT | 4767_25515 | XABTOR704184 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR702893 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR703229 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702021 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702119 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702121 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR702892 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702258 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702268 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702045 | 1 | 86011499 | 1
05/11/2016 | SHIPPED | AT | 4767_25515 | XABTOR704185 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702123 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702348 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702562 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702048 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702259 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702273 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702020 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702120 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702143 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25621 | XABTOR702896 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702609 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702144 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702162 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25621 | XABTOR702898 | 1 | 86011499 | 1
05/02/2016 | SHIPPED | AT | 4767_25621 | XABTOR698836 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702255 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702336 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702047 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702542 | 1 | 86011499 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702768 | 1 | 86011499 | 1
05/12/2016 | SHIPPED | AT | 4767_26251 | XABTOR705201 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702139 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702052 | 1 | 86011499 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702122 | 1 | 86011499 | 1
05/10/2016 | SHIPPED | AT | 4767_25621 | XABTOR702897 | 1 | 86011499 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690129 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674742 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675179 | 1 | 86004101 | 1
04/20/2016 | SHIPPED | AT | 4980_26410 | XABTOR692268 | 1 | 86004101 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690269 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688835 | 1 | 86004101 | 1
04/20/2016 | SHIPPED | NL | 4975_25596 | XABTOR692294 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693944 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685388 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703036 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702154 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703026 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693597 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693831 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693946 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689385 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689704 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702160 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702156 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675184 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703039 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 5047_25926 | XABTOR701560 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689795 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689893 | 1 | 86004101 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR686067 | 1 | 86004101 | 1
05/10/2016 | SHIPPED | SG | 5112_26227 | XABTOR703037 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674725 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674743 | 1 | 86004101 | 1
03/16/2016 | SHIPPED | SG | 4931_25845 | XABTOR675178 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689007 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4904_26033 | XABTOR689011 | 1 | 86004101 | 1
04/22/2016 | SHIPPED | AT | 5062_26045 | XABTOR693596 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 4753_24610 | XABTOR701486 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689384 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689386 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702159 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4942_25398 | XABTOR688765 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690003 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685502 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4903_25252 | XABTOR689582 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4903_25252 | XABTOR689782 | 1 | 86004101 | 1
04/20/2016 | SHIPPED | NL | 4975_25596 | XABTOR692273 | 1 | 86004101 | 1
04/06/2016 | SHIPPED | AT | 4893_25209 | XABTOR685503 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689172 | 1 | 86004101 | 1
04/18/2016 | SHIPPED | AT | 4989_25672 | XABTOR690483 | 1 | 86004101 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693323 | 1 | 86004101 | 1
04/21/2016 | SHIPPED | AT | 4980_26410 | XABTOR693350 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688636 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689004 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689013 | 1 | 86004101 | 1
11/25/2015 | SHIPPED | NL | 4683_24140 | XABTOR631038 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR690136 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689619 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689802 | 1 | 86004101 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR685690 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | SG | 5112_26227 | XABTOR702158 | 1 | 86004101 | 1
03/15/2016 | SHIPPED | SG | 4931_25845 | XABTOR674720 | 1 | 86004101 | 1
05/02/2016 | SHIPPED | NL | 5005_25767 | XABTOR698407 | 1 | 86004101 | 1
05/06/2016 | SHIPPED | NL | 5047_25926 | XABTOR701734 | 1 | 86004101 | 1
04/14/2016 | SHIPPED | AT | 4942_25398 | XABTOR689113 | 1 | 86004101 | 1
04/16/2016 | SHIPPED | AT | 4904_26033 | XABTOR690240 | 1 | 86004101 | 1
04/15/2016 | SHIPPED | AT | 4904_26033 | XABTOR689781 | 1 | 86004101 | 1
04/07/2016 | SHIPPED | AT | 4927_25350 | XABTOR685637 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688702 | 1 | 86004101 | 1
04/13/2016 | SHIPPED | AT | 4903_25252 | XABTOR688704 | 1 | 86004101 | 1
04/18/2016 | SHIPPED | AT | 4989_25672 | XABTOR690821 | 1 | 86004101 | 1
05/05/2016 | SHIPPED | AT | 5047_25947 | XABTOR700679 | 1 | 86004101 | 1
05/09/2016 | SHIPPED | NL | 4724_24445 | XABTOR702787 | 1 | 86006500 | 1
05/06/2016 | SHIPPED | NL | 4724_24445 | XABTOR701387 | 1 | 86006500 | 1
05/06/2016 | SHIPPED | NL | 4724_24445 | XABTOR701175 | 1 | 86006500 | 1
05/06/2016 | SHIPPED | NL | 4724_24445 | XABTOR701494 | 1 | 86006500 | 1
05/09/2016 | SHIPPED | NL | 4724_24445 | XABTOR702490 | 1 | 86006500 | 1
05/12/2016 | SHIPPED | AT | 4722_24438 | XABTOR704786 | 1 | 86006500 | 1
05/12/2016 | SHIPPED | AT | 4722_24438 | XABTOR704812 | 1 | 86006500 | 1
05/12/2016 | SHIPPED | AT | 4722_24438 | XABTOR704784 | 1 | 86006500 | 1
05/09/2016 | SHIPPED | NL | 4724_24445 | XABTOR702528 | 1 | 86006500 | 1
05/09/2016 | SHIPPED | NL | 4724_24445 | XABTOR702695 | 1 | 86006500 | 1
05/12/2016 | SHIPPED | AT | 4722_24438 | XABTOR704813 | 1 | 86006500 | 1
05/06/2016 | SHIPPED | NL | 4724_24445 | XABTOR701481 | 1 | 86006500 | 1
05/09/2016 | SHIPPED | NL | 4724_24445 | XABTOR702740 | 1 | 86006500 | 1
05/09/2016 | SHIPPED | NL | 4724_24445 | XABTOR702714 | 1 | 86006500 | 1
03/30/2016 | SHIPPED | NL | 4760_24641 | XABTOR681640 | 1 | 86009148 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR700187 | 1 | 86009148 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664809 | 1 | 86009148 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664435 | 1 | 86009148 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682413 | 1 | 86009148 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR700142 | 1 | 86009148 | 1
02/18/2016 | SHIPPED | AT | 4792_24771 | XABTOR664442 | 1 | 86009148 | 1
05/04/2016 | SHIPPED | NL | 5038_25912 | XABTOR700001 | 1 | 86009148 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682412 | 1 | 86009148 | 1
03/31/2016 | SHIPPED | NL | 4362_22768 | XABTOR682471 | 1 | 86009148 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691796 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691706 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691713 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691727 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691707 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691799 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691735 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691802 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691801 | 1 | 86012031 | 1
04/12/2016 | SHIPPED | AT | 4977_25601 | XABTOR687739 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691708 | 1 | 86012031 | 1
04/19/2016 | SHIPPED | AT | 4977_25601 | XABTOR691712 | 1 | 86012031 | 1
05/12/2016 | SHIPPED | AT | 4707_24349 | XABTOR704849 | 1 | 86012105 | 1
05/11/2016 | SHIPPED | AT | 4707_24349 | XABTOR704337 | 1 | 86012107 | 1
02/16/2016 | SHIPPED | AT | 4685_24165 | XABTOR663247 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24269 | XABTOR696785 | 1 | 86009207 | 1
03/29/2016 | SHIPPED | SG | 4698_24274 | XABTOR680797 | 1 | 86009207 | 1
04/29/2016 | SHIPPED | AT | 4698_24272 | XABTOR697578 | 1 | 86009207 | 1
05/09/2016 | SHIPPED | AT | 4697_24297 | XABTOR702265 | 1 | 86009207 | 1
04/29/2016 | SHIPPED | AT | 4698_24269 | XABTOR697577 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | NL | 4697_24295 | XABTOR667888 | 1 | 86009207 | 1
02/05/2016 | SHIPPED | AT | 4685_24164 | XABTOR659180 | 1 | 86009207 | 1
05/12/2016 | SHIPPED | AT | 4697_24299 | XABTOR704497 | 1 | 86009207 | 1
05/03/2016 | SHIPPED | AT | 4697_24262 | XABTOR699169 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4697_24300 | XABTOR696615 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24269 | XABTOR696647 | 1 | 86009207 | 1
01/29/2016 | SHIPPED | NL | 4685_24163 | XABTOR656085 | 1 | 86009207 | 1
05/04/2016 | SHIPPED | AT | 4697_24264 | XABTOR700390 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24265 | XABTOR702899 | 1 | 86009207 | 1
04/06/2016 | SHIPPED | SG | 4698_24274 | XABTOR685037 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | NL | 4697_24295 | XABTOR667887 | 1 | 86009207 | 1
04/15/2016 | SHIPPED | AT | 4697_24298 | XABTOR689739 | 1 | 86009207 | 1
03/29/2016 | SHIPPED | SG | 4698_24274 | XABTOR680798 | 1 | 86009207 | 1
03/01/2016 | SHIPPED | AT | 4697_24254 | XABTOR669144 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24288 | XABTOR667501 | 1 | 86009207 | 1
03/08/2016 | SHIPPED | NL | 4697_24296 | XABTOR672092 | 1 | 86009207 | 1
02/02/2016 | SHIPPED | AT | 4685_24164 | XABTOR657197 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24261 | XABTOR668161 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4697_24300 | XABTOR696606 | 1 | 86009207 | 1
02/15/2016 | SHIPPED | NL | 4697_24256 | XABTOR662864 | 1 | 86009207 | 1
04/15/2016 | SHIPPED | AT | 4697_24298 | XABTOR689700 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24266 | XABTOR668123 | 1 | 86009207 | 1
03/18/2016 | SHIPPED | NL | 4697_26067 | XABTOR676286 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24299 | XABTOR703636 | 1 | 86009207 | 1
03/09/2016 | SHIPPED | NL | 4697_24267 | XABTOR672869 | 1 | 86009207 | 1
03/29/2016 | SHIPPED | SG | 4698_24274 | XABTOR680796 | 1 | 86009207 | 1
05/02/2016 | SHIPPED | AT | 4697_24300 | XABTOR698190 | 1 | 86009207 | 1
02/15/2016 | SHIPPED | NL | 4697_24256 | XABTOR662698 | 1 | 86009207 | 1
01/29/2016 | SHIPPED | NL | 4685_24163 | XABTOR656079 | 1 | 86009207 | 1
05/04/2016 | SHIPPED | AT | 4697_24264 | XABTOR700027 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24295 | XABTOR668114 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24299 | XABTOR703613 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | NL | 4697_24266 | XABTOR667886 | 1 | 86009207 | 1
05/07/2016 | SHIPPED | AT | 4697_24264 | XABTOR702023 | 1 | 86009207 | 1
02/15/2016 | SHIPPED | NL | 4697_24256 | XABTOR662709 | 1 | 86009207 | 1
03/17/2016 | SHIPPED | NL | 4697_26067 | XABTOR675808 | 1 | 86009207 | 1
05/09/2016 | SHIPPED | AT | 4697_24297 | XABTOR702256 | 1 | 86009207 | 1
01/29/2016 | SHIPPED | NL | 4685_24163 | XABTOR656089 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | NL | 4697_24295 | XABTOR667796 | 1 | 86009207 | 1
04/27/2016 | SHIPPED | AT | 4697_24301 | XABTOR695957 | 1 | 86009207 | 1
04/27/2016 | SHIPPED | AT | 4698_24272 | XABTOR696014 | 1 | 86009207 | 1
02/23/2016 | SHIPPED | NL | 4697_24261 | XABTOR666393 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24271 | XABTOR697137 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24271 | XABTOR697162 | 1 | 86009207 | 1
03/01/2016 | SHIPPED | AT | 4697_24254 | XABTOR669064 | 1 | 86009207 | 1
02/02/2016 | SHIPPED | AT | 4685_24164 | XABTOR657247 | 1 | 86009207 | 1
04/06/2016 | SHIPPED | SG | 4698_24274 | XABTOR685045 | 1 | 86009207 | 1
03/17/2016 | SHIPPED | NL | 4697_26067 | XABTOR675812 | 1 | 86009207 | 1
05/11/2016 | SHIPPED | AT | 4698_24268 | XABTOR704360 | 1 | 86009207 | 1
03/09/2016 | SHIPPED | NL | 4697_24296 | XABTOR672687 | 1 | 86009207 | 1
03/21/2016 | SHIPPED | NL | 4697_26067 | XABTOR676804 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24266 | XABTOR668155 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24281 | XABTOR667499 | 1 | 86009207 | 1
03/09/2016 | SHIPPED | NL | 4697_24267 | XABTOR672863 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24271 | XABTOR696609 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4697_24301 | XABTOR696734 | 1 | 86009207 | 1
01/29/2016 | SHIPPED | NL | 4685_24163 | XABTOR656080 | 1 | 86009207 | 1
05/02/2016 | SHIPPED | AT | 4697_24262 | XABTOR698338 | 1 | 86009207 | 1
02/16/2016 | SHIPPED | AT | 4685_24165 | XABTOR663298 | 1 | 86009207 | 1
05/02/2016 | SHIPPED | AT | 4697_24300 | XABTOR698337 | 1 | 86009207 | 1
05/02/2016 | SHIPPED | AT | 4698_24269 | XABTOR698339 | 1 | 86009207 | 1
01/26/2016 | SHIPPED | AT | 4685_24162 | XABTOR654485 | 1 | 86009207 | 1
03/09/2016 | SHIPPED | NL | 4697_24296 | XABTOR672684 | 1 | 86009207 | 1
04/15/2016 | SHIPPED | AT | 4697_24298 | XABTOR689815 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24262 | XABTOR703655 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24266 | XABTOR668163 | 1 | 86009207 | 1
02/23/2016 | SHIPPED | NL | 4697_24261 | XABTOR666389 | 1 | 86009207 | 1
03/12/2016 | SHIPPED | AT | 3844_18929 | XABTOR674162 | 1 | 86009207 | 1
03/09/2016 | SHIPPED | NL | 4697_25898 | XABTOR672739 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24288 | XABTOR667498 | 1 | 86009207 | 1
04/25/2016 | SHIPPED | AT | 4697_24263 | XABTOR694867 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24265 | XABTOR702887 | 1 | 86009207 | 1
02/29/2016 | SHIPPED | AT | 4697_24254 | XABTOR668957 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | NL | 4697_24261 | XABTOR667865 | 1 | 86009207 | 1
05/12/2016 | SHIPPED | AT | 4697_24297 | XABTOR704785 | 1 | 86009207 | 1
08/25/2015 | SHIPPED | AT | 3676_18451 | XABTOR596305 | 1 | 86006044 | 1
08/24/2015 | SHIPPED | AT | 3676_18451 | XABTOR596202 | 1 | 86006044 | 1
03/24/2016 | SHIPPED | NL | 4991_25754 | XABTOR678887 | 1 | 86008385 | 1
04/21/2016 | SHIPPED | NL | 5080_26121 | XABTOR692923 | 1 | 86008385 | 1
05/11/2016 | SHIPPED | NL | BTS_86008385_01_E_16W19 | XABTOR703993 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5109_26407 | XABTOR697791 | 1 | 86008385 | 1
04/21/2016 | SHIPPED | NL | 5081_26124 | XABTOR693009 | 1 | 86008385 | 1
04/21/2016 | SHIPPED | AT | 4991_25756 | XABTOR693478 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5099_26185 | XABTOR697788 | 1 | 86008385 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681250 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5099_26185 | XABTOR698109 | 1 | 86008385 | 1
05/11/2016 | SHIPPED | NL | BTS_86008385_01_E_16W19 | XABTOR704147 | 1 | 86008385 | 1
04/22/2016 | SHIPPED | AT | 4991_25756 | XABTOR693834 | 1 | 86008385 | 1
04/19/2016 | SHIPPED | AT | 5082_26210 | XABTOR691866 | 1 | 86008385 | 1
05/11/2016 | SHIPPED | NL | BTS_86008385_01_E_16W19 | XABTOR703975 | 1 | 86008385 | 1
05/11/2016 | SHIPPED | NL | BTS_86008385_01_E_16W19 | XABTOR704131 | 1 | 86008385 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681157 | 1 | 86008385 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681257 | 1 | 86008385 | 1
04/23/2016 | SHIPPED | AT | 5082_26127 | XABTOR694355 | 1 | 86008385 | 1
03/29/2016 | SHIPPED | NL | 4682_24136 | XABTOR681155 | 1 | 86008385 | 1
04/22/2016 | SHIPPED | AT | 4991_25756 | XABTOR693832 | 1 | 86008385 | 1
03/24/2016 | SHIPPED | NL | 4991_25755 | XABTOR678905 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5109_26406 | XABTOR698002 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5109_26406 | XABTOR698001 | 1 | 86008385 | 1
04/23/2016 | SHIPPED | AT | 5082_26127 | XABTOR694358 | 1 | 86008385 | 1
04/21/2016 | SHIPPED | NL | 5081_26124 | XABTOR693008 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5109_26407 | XABTOR697792 | 1 | 86008385 | 1
04/21/2016 | SHIPPED | AT | 4991_25756 | XABTOR693476 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5109_26406 | XABTOR698106 | 1 | 86008385 | 1
04/29/2016 | SHIPPED | AT | 5099_26185 | XABTOR698005 | 1 | 86008385 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692572 | 1 | 86008943 | 1
05/12/2016 | SHIPPED | NL | BTS_86008943_01_E_16W19 | XABTOR704683 | 1 | 86008943 | 1
05/02/2016 | SHIPPED | NL | 4976_25651 | XABTOR698617 | 1 | 86008943 | 1
05/12/2016 | SHIPPED | NL | BTS_86008943_01_E_16W19 | XABTOR704731 | 1 | 86008943 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699428 | 1 | 86008943 | 1
05/12/2016 | SHIPPED | NL | BTS_86008943_01_E_16W19 | XABTOR704726 | 1 | 86008943 | 1
04/13/2016 | SHIPPED | AT | 4972_26388 | XABTOR688465 | 1 | 86008943 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699572 | 1 | 86008943 | 1
04/26/2016 | SHIPPED | NL | 5081_26125 | XABTOR695728 | 1 | 86008943 | 1
03/02/2016 | SHIPPED | AT | 4841_24957 | XABTOR669985 | 1 | 86008943 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692328 | 1 | 86008943 | 1
05/12/2016 | SHIPPED | NL | BTS_86008943_01_E_16W19 | XABTOR704685 | 1 | 86008943 | 1
04/29/2016 | SHIPPED | AT | 5083_26131 | XABTOR697600 | 1 | 86008943 | 1
05/02/2016 | SHIPPED | NL | 5081_26126 | XABTOR698455 | 1 | 86008943 | 1
04/12/2016 | SHIPPED | AT | 4972_26389 | XABTOR688008 | 1 | 86008943 | 1
04/29/2016 | SHIPPED | AT | 5083_26131 | XABTOR697604 | 1 | 86008943 | 1
05/02/2016 | SHIPPED | NL | 4976_25651 | XABTOR698737 | 1 | 86008943 | 1
05/02/2016 | SHIPPED | NL | 4976_25651 | XABTOR698621 | 1 | 86008943 | 1
04/12/2016 | SHIPPED | AT | 4972_26389 | XABTOR688014 | 1 | 86008943 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692576 | 1 | 86008943 | 1
04/20/2016 | SHIPPED | NL | 4976_25650 | XABTOR692327 | 1 | 86008943 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699339 | 1 | 86008943 | 1
05/02/2016 | SHIPPED | NL | 4976_25651 | XABTOR698820 | 1 | 86008943 | 1
05/03/2016 | SHIPPED | NL | 4976_25651 | XABTOR699570 | 1 | 86008943 | 1
01/06/2016 | SHIPPED | AT | 4667_24061 | XABTOR645644 | 1 | 86010633 | 1
01/06/2016 | SHIPPED | AT | 4667_24061 | XABTOR645921 | 1 | 86010633 | 1
01/07/2016 | SHIPPED | AT | 4667_24061 | XABTOR646365 | 1 | 86010633 | 1
01/06/2016 | SHIPPED | AT | 4667_24061 | XABTOR645908 | 1 | 86010633 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702049 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699875 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699143 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698831 | 1 | 86011505 | 1
05/06/2016 | SHIPPED | AT | 4767_25779 | XABTOR701789 | 1 | 86011505 | 1
05/06/2016 | SHIPPED | AT | 4767_24666 | XABTOR701183 | 1 | 86011505 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702053 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699410 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698205 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698839 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699411 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698579 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698833 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699108 | 1 | 86011505 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700444 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699104 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699055 | 1 | 86011505 | 1
04/22/2016 | SHIPPED | AT | 4767_25622 | XABTOR693878 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700008 | 1 | 86011505 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702141 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_25622 | XABTOR698838 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700146 | 1 | 86011505 | 1
04/21/2016 | SHIPPED | AT | 4980_25696 | XABTOR693488 | 1 | 86008704 | 1
04/26/2016 | SHIPPED | AT | 5116_26238 | XABTOR695639 | 1 | 86008704 | 1
05/12/2016 | SHIPPED | SG | 5112_26228 | XABTOR704646 | 1 | 86008704 | 1
04/22/2016 | SHIPPED | AT | 4980_25696 | XABTOR693653 | 1 | 86008704 | 1
04/26/2016 | SHIPPED | AT | 5116_26239 | XABTOR695384 | 1 | 86008704 | 1
04/20/2016 | SHIPPED | AT | 4980_25696 | XABTOR692134 | 1 | 86008704 | 1
04/26/2016 | SHIPPED | AT | 5116_26239 | XABTOR695395 | 1 | 86008704 | 1
04/20/2016 | SHIPPED | AT | 4980_25696 | XABTOR692141 | 1 | 86008704 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688471 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690585 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR691051 | 1 | 86009254 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688466 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690589 | 1 | 86009254 | 1
04/19/2016 | SHIPPED | AT | 4917_25293 | XABTOR691177 | 1 | 86009254 | 1
04/12/2016 | SHIPPED | AT | 4985_25690 | XABTOR688272 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690481 | 1 | 86009254 | 1
04/12/2016 | SHIPPED | AT | 4985_25690 | XABTOR688239 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690764 | 1 | 86009254 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688278 | 1 | 86009254 | 1
04/19/2016 | SHIPPED | AT | 4917_25294 | XABTOR691173 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR691007 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25294 | XABTOR690598 | 1 | 86009254 | 1
04/19/2016 | SHIPPED | AT | 4917_25294 | XABTOR691411 | 1 | 86009254 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688360 | 1 | 86009254 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688363 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690903 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690583 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690588 | 1 | 86009254 | 1
04/19/2016 | SHIPPED | AT | 4917_25293 | XABTOR691413 | 1 | 86009254 | 1
04/13/2016 | SHIPPED | AT | 4985_25690 | XABTOR688287 | 1 | 86009254 | 1
04/18/2016 | SHIPPED | AT | 4917_25293 | XABTOR690480 | 1 | 86009254 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701008 | 1 | 86011498 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702163 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700782 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700784 | 1 | 86011498 | 1
05/06/2016 | SHIPPED | AT | 4767_25515 | XABTOR701627 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700830 | 1 | 86011498 | 1
05/04/2016 | SHIPPED | AT | 4767_25515 | XABTOR700162 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700829 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700969 | 1 | 86011498 | 1
05/04/2016 | SHIPPED | AT | 4767_25515 | XABTOR700161 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701013 | 1 | 86011498 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR703481 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700446 | 1 | 86011498 | 1
04/27/2016 | SHIPPED | AT | 4767_25621 | XABTOR696319 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700439 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700783 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700968 | 1 | 86011498 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702804 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700996 | 1 | 86011498 | 1
05/06/2016 | SHIPPED | AT | 4767_25515 | XABTOR701207 | 1 | 86011498 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR703479 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701014 | 1 | 86011498 | 1
05/06/2016 | SHIPPED | AT | 4767_25515 | XABTOR701418 | 1 | 86011498 | 1
05/04/2016 | SHIPPED | AT | 4767_25515 | XABTOR700338 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700974 | 1 | 86011498 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR702882 | 1 | 86011498 | 1
05/10/2016 | SHIPPED | AT | 4767_25515 | XABTOR702880 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701010 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701000 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701015 | 1 | 86011498 | 1
05/06/2016 | SHIPPED | AT | 4767_25515 | XABTOR701417 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700443 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR701006 | 1 | 86011498 | 1
05/07/2016 | SHIPPED | AT | 4767_25515 | XABTOR702142 | 1 | 86011498 | 1
05/09/2016 | SHIPPED | AT | 4767_25515 | XABTOR702257 | 1 | 86011498 | 1
05/04/2016 | SHIPPED | AT | 4767_25515 | XABTOR700336 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700445 | 1 | 86011498 | 1
05/05/2016 | SHIPPED | AT | 4767_25515 | XABTOR700779 | 1 | 86011498 | 1
05/09/2016 | SHIPPED | AT | 4767_25779 | XABTOR702839 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699144 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699444 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700007 | 1 | 86011505 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702046 | 1 | 86011505 | 1
05/11/2016 | SHIPPED | AT | 4767_25779 | XABTOR704413 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699694 | 1 | 86011505 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700447 | 1 | 86011505 | 1
05/11/2016 | SHIPPED | AT | 4767_25779 | XABTOR704408 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699878 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_25622 | XABTOR698967 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700148 | 1 | 86011505 | 1
05/06/2016 | SHIPPED | AT | 4767_25779 | XABTOR701786 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699869 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699876 | 1 | 86011505 | 1
05/06/2016 | SHIPPED | AT | 4767_24666 | XABTOR701188 | 1 | 86011505 | 1
05/10/2016 | SHIPPED | AT | 4767_25779 | XABTOR703656 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699884 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699050 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699059 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700150 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_25622 | XABTOR698969 | 1 | 86011505 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700440 | 1 | 86011505 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702054 | 1 | 86011505 | 1
05/11/2016 | SHIPPED | AT | 4767_25779 | XABTOR704411 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699637 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_25622 | XABTOR699640 | 1 | 86011505 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702132 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700009 | 1 | 86011505 | 1
05/12/2016 | SHIPPED | AT | 4767_25779 | XABTOR704780 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_25622 | XABTOR699435 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700010 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700178 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699057 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR700152 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698577 | 1 | 86011505 | 1
05/04/2016 | SHIPPED | AT | 4767_24666 | XABTOR699879 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699445 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699698 | 1 | 86011505 | 1
05/07/2016 | SHIPPED | AT | 4767_25779 | XABTOR702129 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699103 | 1 | 86011505 | 1
05/03/2016 | SHIPPED | AT | 4767_24666 | XABTOR699053 | 1 | 86011505 | 1
05/05/2016 | SHIPPED | AT | 4767_24666 | XABTOR700442 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24666 | XABTOR698216 | 1 | 86011505 | 1
05/02/2016 | SHIPPED | AT | 4767_24667 | XABTOR698835 | 1 | 86011505 | 1
04/26/2016 | SHIPPED | AT | 5167_26434 | XABTOR695776 | 1 | 86012648 | 1
03/09/2016 | SHIPPED | NL | 4697_25898 | XABTOR672729 | 1 | 86009207 | 1
05/11/2016 | SHIPPED | AT | 4697_24297 | XABTOR704336 | 1 | 86009207 | 1
02/03/2016 | SHIPPED | AT | 4685_24164 | XABTOR657855 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24299 | XABTOR703615 | 1 | 86009207 | 1
03/21/2016 | SHIPPED | AT | 3844_18929 | XABTOR676874 | 1 | 86009207 | 1
04/27/2016 | SHIPPED | AT | 4697_24301 | XABTOR695962 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24265 | XABTOR703621 | 1 | 86009207 | 1
02/15/2016 | SHIPPED | AT | 4685_24165 | XABTOR663066 | 1 | 86009207 | 1
04/26/2016 | SHIPPED | AT | 4697_24263 | XABTOR695177 | 1 | 86009207 | 1
12/23/2015 | SHIPPED | AT | 4685_24162 | XABTOR641378 | 1 | 86009207 | 1
02/17/2016 | SHIPPED | AT | 4685_24165 | XABTOR663725 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24266 | XABTOR668119 | 1 | 86009207 | 1
04/23/2016 | SHIPPED | AT | 4697_24263 | XABTOR694409 | 1 | 86009207 | 1
02/15/2016 | SHIPPED | NL | 4697_24256 | XABTOR662771 | 1 | 86009207 | 1
02/15/2016 | SHIPPED | NL | 4697_24256 | XABTOR662818 | 1 | 86009207 | 1
03/09/2016 | SHIPPED | NL | 4697_24296 | XABTOR672813 | 1 | 86009207 | 1
01/26/2016 | SHIPPED | AT | 4685_24162 | XABTOR654396 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24288 | XABTOR667358 | 1 | 86009207 | 1
01/29/2016 | SHIPPED | NL | 4685_24163 | XABTOR656084 | 1 | 86009207 | 1
04/23/2016 | SHIPPED | AT | 4697_24263 | XABTOR694406 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24281 | XABTOR667497 | 1 | 86009207 | 1
03/16/2016 | SHIPPED | NL | 4697_24267 | XABTOR675202 | 1 | 86009207 | 1
05/03/2016 | SHIPPED | AT | 4697_24262 | XABTOR699226 | 1 | 86009207 | 1
04/28/2016 | SHIPPED | AT | 4698_24271 | XABTOR696636 | 1 | 86009207 | 1
01/26/2016 | SHIPPED | AT | 4685_24162 | XABTOR654395 | 1 | 86009207 | 1
01/26/2016 | SHIPPED | AT | 4685_24162 | XABTOR654484 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24281 | XABTOR667353 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24281 | XABTOR667503 | 1 | 86009207 | 1
03/15/2016 | SHIPPED | NL | 4697_24267 | XABTOR674998 | 1 | 86009207 | 1
05/06/2016 | SHIPPED | AT | 4697_24264 | XABTOR701755 | 1 | 86009207 | 1
02/17/2016 | SHIPPED | AT | 4685_24165 | XABTOR663894 | 1 | 86009207 | 1
02/26/2016 | SHIPPED | NL | 4697_24295 | XABTOR668164 | 1 | 86009207 | 1
03/18/2016 | SHIPPED | AT | 3844_18929 | XABTOR676562 | 1 | 86009207 | 1
05/10/2016 | SHIPPED | AT | 4697_24299 | XABTOR703638 | 1 | 86009207 | 1
04/26/2016 | SHIPPED | AT | 4697_24300 | XABTOR695664 | 1 | 86009207 | 1
03/17/2016 | SHIPPED | AT | 3844_18929 | XABTOR675837 | 1 | 86009207 | 1
04/15/2016 | SHIPPED | AT | 4697_24298 | XABTOR689809 | 1 | 86009207 | 1
04/27/2016 | SHIPPED | AT | 4697_24301 | XABTOR696119 | 1 | 86009207 | 1
02/25/2016 | SHIPPED | SG | 4698_24288 | XABTOR667492 | 1 | 86009207 | 1
05/04/2016 | SHIPPED | AT | 4697_24262 | XABTOR700391 | 1 | 86009207 | 1
05/02/2016 | SHIPPED | AT | 4698_24272 | XABTOR698201 | 1 | 86009207 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697762 | 1 | 86010230 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697676 | 1 | 86010230 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697758 | 1 | 86010230 | 1
04/29/2016 | SHIPPED | NL | 5171_26445 | XABTOR697764 | 1 | 86010230 | 1
01/22/2016 | SHIPPED | AT | 4350_25082 | XABTOR652913 | 1 | 86010807 | 1
01/22/2016 | SHIPPED | AT | 4350_25082 | XABTOR652923 | 1 | 86010807 | 1
01/22/2016 | SHIPPED | AT | 4350_25082 | XABTOR652924 | 1 | 86010807 | 1
01/20/2016 | SHIPPED | AT | 4350_25082 | XABTOR652368 | 1 | 86010807 | 1
01/22/2016 | SHIPPED | AT | 4350_25082 | XABTOR653079 | 1 | 86010807 | 1
01/21/2016 | SHIPPED | AT | 4350_25082 | XABTOR652883 | 1 | 86010807 | 1